## Main_qry
SELECT | Main_tbl_PROJECT | PHASE | Main_tbl_struct | TRACT | OWNER | HTRW / ASBEST REQ | ASBEST COMP | ASBEST DETECT | HTRW COMP | HTRW DETECT | APPL HOLD | APPL REL | SITE VISIT | EVAL RESULT | RE NOTIFY | GPS TO PDS | GPS TO OWNER | CONSTR PROP DUE | FP EST COMP | FP EST - W O PROFIT | CONSTR PROP REC | PROP 1 | PROP 2 | OFFER TO OWNER | OFFER AMOUNT + TH | TH | FP AGRMT REQ | FP AGRMT EXEC | FP AGRMT ACC | PRE-CON MEETING | CHANGE ORDER | FINAL FP COST | PRE-FINAL REC | CONSTR PKT REC | CHECK REQ | CLOSING | ASSIGN TO SPONSOR | NOTES | FollowUp | PCA | TRIB | ADDRESS | RM | ZIPCODE | FFELEV | LGELEV | SQFT | DESGNFFELEV | FLDLEVEL | FLDLVLDISC | VELOCITY | SEPTICREQ | SEPTICREC | SEPTICRES | STRUCTNOTES | CHAIRLFTREG | CHAIRLFTDOC | CORPLIMITS | BUYUPELIG | TENANTOCC | SEPTICREG | VERTDATUM | Contacts_tbl_PROJECT | Contacts_tbl_struct | phone 1 | phone 2 | phone 3 | phone 4 | disc 1 | disc 2 | disc 3 | disc 4 | contractor | mailingaddr
FALSE | McDowell County | Phase III | BD0012 | 3732FP | Harrison, Elby W. | [7 empty] | 2004-06-17 | AC | 2004-08-18 | [23 empty] | TRUE | FALSE |  |  | 0.3 |  | 1185.6 | 1180.2 | 0 | 0 | 1189.4 | 1977 | 0 | [7 empty] | N |  |  | NGVD | McDowell County | BD0012 | 3049677125 |  |  |  | Home |  |  |  | 0
FALSE | McDowell County | Phase III | BD0156 | 4007FP | Hatfield, Sherri L. | [6 empty] | 2011-03-03 | 2014-03-19 | OT | 2015-08-18 | 2017-02-15 | 2017-02-17 | 2017-03-10 | 2016-08-02 | 93130 |  |  |  | 2016-08-16 | 93000 | [12 empty] | Mrs. Hatfield has requested the Buy-Up to floodproofing option. Buy-Up package delivered to her on 16 August 2016. SHH Delivered Ms. Hatfield's Buy-Up to floodproofing option and she was receptive to the offer. She was disappointed it wasn’t better but is going to make an attempt to do something. Her only request we that she have 60 days to decide instead of 30 days since she has waited on us for 10 years to get there. I approved her 30 day extension and told her to let us know. She agreed and will try and make some decisions as soon as she can. SHH 17 August 2016 Steve Harris returned a call to Ms. Hatfield with Dawn Haynes and Christy Hutchinson in attendance. Ms. Hatifield had questions regarding timelines and logistics of the Buy up to FP option. Ms. Hatfield asked if she would be able to wait until spring (Mar/Apr), to begin the process of moving. She asked if she could put a doublewide on a contiguous piece of property she owned and Mr. Harris answered with advising her that the ground level of her new habitable space would have to be 1333.13, which includes the 2 ft freeboard required by McDowell County. Mr. Harris also explained what the crawl space could only be used for limited storage, vehicle parking (if enough space) and access to the structure. He also stated that any HVAC equipment would have to be above the 77 flood level. She asked how she would procure a doublewide (if she chooses) and get a contractor to lay her block foundation without paying them upfront to which Mr. Harris advised her that USACE would issue her an official offer letter with the approved BUTFP amount, which she could show her chosen contractor or mobile home dealer, but that USACE does not make payment upfront, only at closing/completion. Ms. Hatfield said she would let us know of her decision by the end of her 60 day period. Mr. Harris also asked Ms. Hatfield if she would be interested in having her beauty shop trailer acquired, if possible, to which she indicated she is interested. DH 12SEP2016 Steve Harris, Dawn Haynes and Christy Hutchinson met with Sherri 2/17/17 to deliver GP&S for foundation, block and other FP requirements a re-build. Sherri stated that she had visited mobile home dealers and had priced one at 67k, but anything over 8 or 9 blocks would require a crane at additional expense. She also discussed having excavation work done to the site prior to re-build. Steve explained to Sherri that a block is only 8 inches high and to reach the minimum elevation would require approximately 14 or more block from the LG point of her house. Steve also encouraged her to ensure she fully understands all of the elements proposed by her chosen contractor because she seemed to underestimate cost of the foundation and block required to raise her to the required height. Steve also pointed out that if any dirt was moved or added to the site that the foundation would still have to be built on undisturbed ground, which could add additional cost. Sherri once again voiced her displeasure about the amount she has been offered in comparison to other landowners in the project and Steve again addressed the concept of fair market value, appraisal review, etc. and how the amount was formulated. We then asked her if she found the deed to the beauty shop so it could be considered to which she informed us that she found that the deal was apparently "word of mouth" and never actually written. Steve clarified that we would not be able to consider it without the deed and she indicated that she understood. Sherri also said that she had talked to several local contractors and friends about laying block and the demo of her house and is expecting another contractor to do a site visit in a couple of weeks. Steve reminded her that no matter what contractor she chooses, payment will not be made until closing, when all work and inspections are completed. Sherri will followup with us after the site visit from the other contractor in a couple of weeks. 2/21/17 dh. Sherri Hatfield was called with Dawn Haynes, Michelle Sabotchick and Christy Hutchinson were present for the conversation. Ms. Hatfield discussed that no contractor could take her job without being compensated up front. She let us know that the beauty shop is not hers, her trailer just sits on the property so she cannot get a deed to that property. She stated she had not been able to contact Dave Bailey. She asked about contractors and Dawn discussed how contractor meetings were held to find contractors that were capable of completing floodproofing work and we had proveded the list of those contractors. Dawn then brought to her attention how long ago she signed the agreement and the floodproofing was originally supposed to start in Spring. She stated once again that she was just not receiving enough money to take care of everything. Ms Hatfield said she would contact us and lt us know something more after she spoke with Mr Bailey. CH 03/30/17 Called Sherri to follow up on our last conversation. She said that she had been in touch with Contractor Dave Bailey, who said he would be out one evening this week to take a look at it and let her know if he could propose anything or refer her to another contractor. We agreed that it will be good to know what he thinks is feasible. I advised her that we would be sending her a letter giving her a deadline by which she must chose a contractor or we will have to move on. I explained that we have given her much more time than normal and I asked her to call and update us after her meeting with Mr. Bailey and she said that she would. 4/4/17 dh Steve Harris and team tried to call Sherri regarding concerning tax related issues that were discovered during the owner verification process. She did not answer, Steve left a voice mail message stating that he needed to talk to her right away and to call anytime between 7 and 3:30. 4/6/17 dh Steve Harris had not received a call back from Sherri and her number is not on anyones missed call list. Steve and team tried to call her again, no answer, left another message on her voicemail. 4/7/17 dh Steve tried again to reach Sherri. No answer, left voice mail message. 4/10/17 dh Steve Harris and Christy Hutchinson called Ms Hatfield to make her aware that our Attorneys found tax issues when they done her review. Ms Hatfield informed us that she was unaware of any tax issues and she believed she was exempt due to Homestead. She stated she had went to Welch and got the paperwork for the Homestead, filled it out, and had it notarized. Mr Harris gave her the Account number she needed to reference when she calls the courthouse (20989) to see what is needed to be done to fix her 2015 and 2016 taxes. He also informed her she would need to purchase the bill and pay any penalties. He let her know she only had 18 months and she is close to running out of time. Ms Hatfield asked if Mr Bailey had contacted us yet and Mr Harris informed her he had not. CH 04/11/2017 Sherri has confirmed that she has paid the back taxes and is expecting a receipt from the Charleston office and she will forward us a copy as soon as she receives it. She said that they also committed to correct her information so that she will be truly exempt going forward and will not owe any taxes for 2016. She also said that she is expecting contractor Dave Bailey for a site visit before Monday. 4/13/17 dh Received HTRW results from Frank Albert on 04/26/2017 CH Drop letter sent 04/14/2017. Ms. Hatfieild was given until 6/15/2017 to submit contractor proposal. No contractor proposals were submitted. Ms. Hatfield also failed to provide documentation that her tax issue was resolved. Structure BD0156 has been withdrawn from the program. MS 2/21/2018 Memo outlining CIAD costs sent to Program Manager, Rebecca Bennett. MS | FALSE | FALSE |  |  | 2.71 |  | 1328 | 1327.3 | 0 | 0 | 1331.15 | 1977 | 0 | [10 empty] | NGVD | McDowell County | BD0156 | 3049675522 | [7 empty] | 0
FALSE | McDowell County | Phase III | BD0008 | 3728FP | Roberts, Carol Sue (AKA Stanley) | [6 empty] | 2011-03-06 | 2011-03-14 | HR |  | 2011-08-15 | 2011-08-29 | 2011-09-12 | 2011-10-17 | 117097 | 2012-09-10 | 127757 |  | 2012-09-10 | 127757 | 2400 | 2012-09-11 | 2012-09-25 | 2012-09-28 | 2012-10-31 |  | 127757 | 2012-10-31 | 2013-07-29 | 2013-07-29 | 2013-11-13 |  | Job has been obligated (30 Sept 2012) and pre-con completed 31 Oct 2012. Waiting on official contract before construction can start. SHH 1 Nov 2012. Got left a message from Mr. Bailey (Ms. Stanley's contractor) that said that Ms. Stanley had called him and said she was being cheated out of 10 feet 4 inches and that if he couldn’t give her the 10 feet 4 inches that she would find a new contractor. Mr. Bailey said he told her to find a new contractor. Mr. Bailey said he would not be doing this job and to take him off as her contractor. SHH 11-8-12 Contacte Ms. Stanley and she informed me that she had contacted Mr. Bailey and that she did not tell him he was cheating her and she wanted a list of contractors. One was not included in the GP&S because she had already talked to Mr. Bailey before and I thought she had already picked a contractor. I will mail her a list of contractors today and she will see if she can find another contractor to do her job. SHH 11-13-12 Have meeting with homeowner, Mr. Bailey (contractor), Judy Heath, Dan Riley and myself set up for 9:00am 15 November 20012. SH 11-14-12 SHH 11-19-12 - Meeting did not go well! Ms. Stanley will be finding another contractor. Ms. Stanley was told she had 60 days from the time she recieves a letter telling her the options available to her. I will prepare a letter right away. Please see letter in folder for more details on meeting and future requirements. Ms. Roberts Stanley called and left a message on 20 Nov 2012 and I returned her call on 21 Nov 2012 with no answer and I did leave a message on her answering machine that I just stopped in to finish her letter up and get it out to her in the mail about what happened at meeting and what I need to proceed with project. I informed her that I will be off until 3 Dec 2012 and that I would contact her then. SHH I contacted Ms. Stanley the morning of 3rd December 2012 and she gave me 2 contractor's names and phone numbers to call. She also reqeusted some additional GP&S as soon as possible. I had planned on being in the area of McDowell and Grundy leaving later today the 3rd. I told Ms. Stanley I would contact the contractors and answer their questions and then I would drop off her additional later this evening and I would discuss their questions with her when I got there. SHH 3 December 2012 I contacted Robert Barrett from Tazwell VA, phone number 276-970-6760 and discussed any issues about the construction of Ms. Stanley's home. He was very positive about the project and was going to contact Ms. Stanley and work out the details. SHH 5 December 2012 I contacted John Bailey of Southern Homes of Pineville to discuss Ms. Stanley's project on the morning of 3rd December 2012. I agreed to met Mr. Bailey at 4pm this day and we would discuss all the issues. I met with Mr. Bailey and his wife at his office in Pineville WV at 4pm. We discussed the issues and he was to contact Ms. Stanley the following day and discuss her project with her. He seemed positive about the project and indicated he would be bidding on the project. SHH 5 December 2012 Delivered 5 sets of GP&S off at Ms. Stanley's home the evening of 3rd December 2012 and discussed what her contractors asked about her project. SHH 5 December 2012. Tried to call Ms. Stanley on 7 December to see if she had any luck with her contractors that I met with and talked to. She did not answer the phone and I will try again on Monday the 10th December 2012. SHH 7 December 2012 | FALSE | FALSE |  |  | 0.27 |  | 1183.1 | 1182.2 | 0 | 0 | 1189 | 1977 | 0 | [11 empty] | McDowell County | BD0008 | 3049675611 |  |  |  | Home |  |  |  | 0
FALSE | McDowell County | Phase III | DF-160-1 | 2908 | Ernest Reed | [7 empty] | 2013-08-09 | NE | [23 empty] | Structure burned in July 2013 and site has been cleared and prepared for future use. Not Eligible - Complete | FALSE | FALSE |  | 4110 Mountaineer Highway | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
FALSE | McDowell County |  | CW0001 |  | Conley, Landsford | [33 empty] | FALSE | FALSE
FALSE | McDowell County | Phase IV | B0002 | 4601FP | Raymond C. Payne | [33 empty] | FALSE | FALSE |  |  | 0.11 |  | 1319.6 | 1320.8 |  |  | 1323.83 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0005 | 4603FP | Raymond C. Payne | [33 empty] | FALSE | FALSE |  |  | 0.191 |  | 1330.5 | 1327.4 |  |  | 1329.34 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0010 | 4606FP | Alvanna Simpkins | [33 empty] | FALSE | FALSE |  |  | 0.51 |  | 1363.45 | 1360.75 |  |  | 1364.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0021 | 4700FP | Daniel Ray Riley | [33 empty] | FALSE | FALSE |  |  | 1.45 |  | 1444.85 | 1442.25 |  |  | 1447.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0026 | 4703FP | Gerald & Allene Smith | [33 empty] | FALSE | FALSE |  |  | 1.65 |  | 1456.15 | 1454.75 |  |  | 1460.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0027 | 4704FP | Dennis C. & Drema J. Altizer | [33 empty] | FALSE | FALSE |  |  | 1.66 |  | 1457.05 | 1454.85 |  |  | 1461.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0028 | 4705FP | Big Creek People in Action | [33 empty] | FALSE | FALSE |  |  | 1.67 |  | 1457.85 | 1455.65 |  |  | 1462.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0030 | 4707FP | Walter Edward Rutherford | [33 empty] | FALSE | FALSE |  |  | 1.7 |  | 1459.75 | 1457.05 |  |  | 1463.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0032 | 4708FP | Clarence Hughes | [33 empty] | FALSE | FALSE |  |  | 1.72 |  | 1457.45 | 1461.45 |  |  | 1462.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0220 | 2537FP | Meyhew, John & Judy | 2003-05-15 | [5 empty] | 2003-02-19 | 2003-02-20 | AC | 2003-07-01 | [23 empty] | TRUE | FALSE |  |  | 110.9 |  | 984.05 | 980.75 |  |  | 982.39 | [9 empty] | Y |  |  | NGVD
FALSE | McDowell County | Phase II | MC0094 | 2603FP | Mills, Doris M. | [5 empty] | 2002-09-28 | 2003-02-24 | [26 empty] | FALSE | FALSE |  |  | 0.5 |  | 979.65 | 977.25 |  |  | 982.55 | 1977 | [11 empty] | NGVD | McDowell County | MC0094 | 7572295671 |  |  |  | Home
FALSE | McDowell County | Phase II | MC0095 | 2603FP | Mills, Doris M. | [33 empty] | FALSE | FALSE |  |  | 0.5 |  | 976.25 | 970.25 |  |  | 982.55 | 1977 | [11 empty] | NGVD | McDowell County | MC0095 | 7572295671 |  |  |  | Home
FALSE | McDowell County | Phase III | DF0219 | 3707FP | Burlie Kay Brown | [8 empty] | AC | 2003-11-26 | [23 empty] | FALSE | FALSE |  |  | 0.135 |  | 1175.2 | 1175 |  |  | 1179.6 | 1977 | [8 empty] | N |  |  | NGVD
FALSE | McDowell County | Phase II | MC0275 | 3212FP | Rice, Phyllis | 2003-05-15 | 2003-10-06 | N | 2003-11-06 | N | 2002-08-01 | 2003-05-05 | 2002-08-19 | GR |  | 2003-03-26 | 2003-07-09 | 2003-07-23 | 2003-10-31 | 116548 | 2003-09-24 | 119832 | 126081 | 2003-11-06 | 126081 | 900 | 2003-11-07 | 2003-11-20 | 2003-12-23 | 2003-12-17 |  | 126081 |  | 2004-03-29 | 2004-04-01 | 2004-04-16 |  | h 304 938-5065 Asbeston info will be worked on the week of 2003-08-25 and the report should be done by 2003-09-12 Contractor - Sam White 304-752-0792 Need foundation plan w/ramp and water softener - JT 2003-09-09 Proposal from Sammie White had an addition error and was resubmitted due to 12" block anatated on the approved foundation plan - JT Had heart attack - 2003-09-25 - JT Contacted home owner 10/09/03 and Phyllis indicated that she was ready to procede. Sent foundation plan to EC and also informed them that the asbestos was negative and that we needed to procede. - Joe Trimboli PR&C - W81F8E33116145 | TRUE | FALSE |  |  | 112.3 |  | 990.35 | 986.35 |  |  | 988.44 | 1977 | [11 empty] | NGVD | McDowell County | MC0275 | 3049385065 | 3047520792 |  |  | Home | Contractor - Sammy White |  |  | 74
FALSE | McDowell County | Phase II | MC0278 | 3213FP | Cline, Rachel | 2003-05-15 |  |  |  |  | 2002-07-29 | 2003-05-21 | 2002-08-21 | OT |  | 2003-08-12 | 2003-08-20 | [20 empty] | h (304) 938-5314 w (304) 938-5774 Rachel D. Cline and Larry F. Cline are on application Send memo to RE requesting owner verification of deed we received at the GPS delivery. Mrs Cline did not like the GPS and wants to put the addition on the other side of her home. Need to find out how to amend guide plans so that if the plan is not followed the protection level is reduced - JT 2003-09-09 Helping neighbor, Phylis Rice, with heart attack, structure has been put on hold - 2003-09-25 - JT Rachel Cline is undecided about how to procede - I have told EC not to do anymore work on her untill I let them know something different - joe Trimboli 2003-10-10 | TRUE | FALSE |  |  | 112.3 |  | 990.05 | 984.25 |  |  | 988.44 | 1977 | [11 empty] | NGVD | McDowell County | MC0278 | 3049385314 | 3049385774 |  |  | home | work
FALSE | McDowell County | Phase II | DF0020 | 2610FP | Hunt, William | 2003-05-15 |  |  |  |  | 2000-09-26 | 2003-05-06 | 2003-08-27 | GR |  | 2006-03-20 | 2006-03-20 | 2006-04-05 | 2008-11-13 | 191137 | 2008-07-20 | 291160 |  | 2009-01-05 | 215000 | 0 | 2009-01-07 | 2009-02-20 | 2009-02-27 | 2009-03-24 |  | 215000 |  | 2009-09-21 | 2009-10-15 | 2009-11-23 |  | Union City, WV 304-938-3187 wife Tammy Joe - Went with Donna, MarryAnne, and Steve O'leary to look at this house again because it has been added onto numeriois times and is questionable to be lifted. Talked with Steve O'Leary and asked about doing a ringwall. | TRUE | FALSE |  |  | 2.76 |  | 1003.7 | 1001.4 |  |  | 1004.26 | 1977 | [11 empty] | NGVD | McDowell County | DF0020 | 3049383187 |  |  |  | Home |  |  |  | 7
FALSE | McDowell County | Phase III | DF0234 | 3738FP | Muncy, Robert & Shelia | 2003-05-15 | [5 empty] | 2003-05-06 |  | GR |  | 2008-07-14 | 2006-03-20 | 2006-04-05 | 2008-08-26 | 126208 | 2008-09-10 | 161207 | 166701 | 2008-09-17 | 151800 | 1800 | 2008-09-17 | 2008-09-24 | 2008-09-29 | 2008-12-16 |  | 151800 |  | 2009-02-17 | 2009-02-20 | 2009-03-10 |  | Gene, Just got off the phone with Mrs. Muncy, (304-436-2872), and she was upset that we giving her a new government replacement home!!!!! She wants to be bought out and is upset that we are not doing that. I informed her that the program is voluntary and that she could drop out any time. She said she was going to talk with Gordon and see what she could do. She said that when me and you were there that we told her and her husbanc that they would have all kind of options and that now we are forcing them to build back. I told her I thought she miss understood and we told her that we did not know what she was eligible for at this time but that these are the options that they could possibly be eligible for. I told her we did not know what her options were until we did a site visit. She said that you (Mr. Barr) told them they could be relocated and bought out. She still wants me to deliver the GP&S on Monday and she will do what ever she can to be bought out!!!!!!!!!!! Thanks Steve Harris - emailed 3/16/06 | TRUE | FALSE |  |  | 0.1 |  | 1173.2 | 1171.8 |  |  | 1177.3 | 1977 | [11 empty] | NGVD | McDowell County | DF0234 | 3049675243 |  | 3049677370 |  | Home |  | Work |  | 0
FALSE | McDowell County | Phase IV | B0033 | 4709FP | Caretta Community Methodist Church | [33 empty] | FALSE | FALSE |  |  | 1.73 |  | 1457.95 | 1460.75 |  |  | 1462.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0036 | 4712FP | Walter Richardson | [33 empty] | FALSE | FALSE |  |  | 1.84 |  | 1468.55 | 1465.95 |  |  | 1469.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0037 | 4713FP | Bernice Richardson | [33 empty] | FALSE | FALSE |  |  | 1.87 |  | 1469.05 | 1467.05 |  |  | 1471.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0038 | 4714FP | Hilda Hockett | [33 empty] | FALSE | FALSE |  |  | 1.89 |  | 1471.55 | 1469.45 |  |  | 1472.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0039 | 4715FP | Sean T. Timmons | [33 empty] | FALSE | FALSE |  |  | 1.9 |  | 1472.25 | 1470.45 |  |  | 1473.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0040 | 4716FP | Danny & Sandra Kennedy | [33 empty] | FALSE | FALSE |  |  | 1.93 |  | 1473.25 | 1470.45 |  |  | 1474.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0041 | 4717FP | Harry L. & Frances Ann Patton | [33 empty] | FALSE | FALSE |  |  | 1.93 |  | 1473.75 | 1471.55 |  |  | 1474.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0042 | 4718FP | Anita Adams | [33 empty] | FALSE | FALSE |  |  | 1.94 |  | 1474.45 | 1472.55 |  |  | 1475.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0046 | 4721FP | Timothy & Diedra Renee Addair | [33 empty] | FALSE | FALSE |  |  | 1.92 |  | 1473.65 | 1471.25 |  |  | 1473.95 | [12 empty] | NGVD
FALSE | McDowell County | Phase IV | B0047 | 4722FP | Ona Whitt | [33 empty] | FALSE | FALSE |  |  | 1.94 |  | 1474.95 | 1472.45 |  |  | 1475.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0063 | 4724FP | Karen Blankenship | [33 empty] | FALSE | FALSE |  |  | 2.15 |  | 1489.75 | 1487.15 |  |  | 1489.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0064 | 4725FP | Elsie Crigger Wolfe | [33 empty] | FALSE | FALSE |  |  | 2.17 |  | 1489.95 | 1487.75 |  |  | 1492.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0065 | 4726FP | Freewill Baptist Church | [33 empty] | FALSE | FALSE |  |  | 2.36 |  | 1501.95 | 1503.55 |  |  | 1508.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | B0069 | 4727FP | Alawest | [33 empty] | FALSE | FALSE |  |  | 2.42 |  | 1513.65 | 1509.95 |  |  | 1514.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BC0002 | 4711FP | Alawest | [33 empty] | FALSE | FALSE |  |  | 0.06 |  | 1473.65 | 1477.75 |  |  | 1474.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BC0017 | 4730FP | Lee W. & Ester Richardson | [33 empty] | FALSE | FALSE |  |  | 0.22 |  | 1497.45 | 1500.95 |  |  | 1500.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BC0018 | 4731FP | Jerry & Barbara Keene | [33 empty] | FALSE | FALSE |  |  | 0.24 |  | 1499.35 | 1501.75 |  |  | 1504.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0001 | 3722FP | Marcum, William | [6 empty] | 2011-03-03 | 2011-03-14 | OT |  | 2015-12-11 | 2015-12-18 | 2016-01-15 | [19 empty] | Rerturned Application to Real Estate on 10 Apr 2015 to update application. Memo was sent to Mr. Marcum end of August 2016 informing Mr. Marcum he would have to work out a deal with his neighbor to floodproof his home. We gave him until October 1, 2016 to get this done or he would be dropped from the program. He did not provide any information as required and a drop letter was sent out middle of October notifying Mr. Marcum he was being removed from the program. SHH 4 Nov 2016 2/21/2018 Memo outlining CIAD costs was sent to Program Manager, Rebeccca Bennett. MS | FALSE | FALSE | Levisa Fork |  | 0.19 |  | 1180.1 | 1177.2 |  |  | 1183 | 1977 | [11 empty] | NGVD | McDowell County | BD0001 | 3049679181 | 4234708897 |  |  | Home |  |  |  | 0
FALSE | McDowell County | Phase III | BD0002 | 3723FP | Burl & Glenna Laxton | [33 empty] | FALSE | FALSE |  |  | 0.2 |  | 1181.1 | 1177.8 |  |  | 1183.1 | [12 empty] | NGVD
FALSE | McDowell County | Phase III | BD0009 | 3729FP | Johnny W. Pocrnick | [32 empty] | Application - Ricky Kennedy | FALSE | FALSE |  |  | 0.28 |  | 1183.4 | 1181.9 |  |  | 1188.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0010 | 3730FP | Cook Jimmy Ray & Rosemary | [6 empty] | 2010-03-24 | 2010-03-30 | AC |  | 2010-04-08 | 2010-11-08 | 2010-11-23 | [20 empty] | FALSE | FALSE |  |  | 0.29 |  | 1185.5 | 1182.9 |  |  | 1189.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0011 | 3731FP | Harrison, Elby W. | [33 empty] | FALSE | FALSE |  |  | 0.3 |  | 1185.8 | 1184.1 |  |  | 1189.4 | 1977 | [11 empty] | NGVD | McDowell County | BD0011 | 3049677125 |  |  |  | Home |  |  |  | 0
FALSE | McDowell County | Phase III | BD0013 | 3732FP-1 | Harrison, Elby W. & John T. | 2003-05-15 |  | Y |  | N | 2002-07-01 |  | 2002-08-29 | FP |  | 2004-02-09 | 2004-02-18 | 2004-03-05 | 2004-04-06 |  | 2004-04-02 | 149600 | 142300 | 2004-04-22 | 141365 | 0 | 2004-04-22 | 2004-06-10 | 2004-07-06 | 2004-07-08 |  | 141365 | 2005-01-10 | 2005-01-12 | 2005-01-21 | 2005-03-11 |  | h 304-967-7125 wife Margret Talked with Mrs. Harrison on 16 September 2004 and informed her that the modification had been approved and it was okay to start construction. SH Wrote check request memo but have not sent. - JT 2005-01-12 | TRUE | FALSE |  |  | 0.31 |  | 1180.4 | 1182.4 |  |  | 1189.4 | 1977 | [11 empty] | NGVD | McDowell County | BD0013 | 3049677125 |  |  |  | Home |  |  |  | 74
FALSE | McDowell County | Phase III | BD0015 | 3732FP-2 | Harrison, Elby W. & John T. | [5 empty] | 2002-07-01 |  | 2003-08-28 | NE | [23 empty] | h 304-967-7125 wife Margret | TRUE | FALSE |  |  | 0.33 |  | 1188.4 | 1184.8 |  |  | 1189.4 | 1977 | [11 empty] | NGVD | McDowell County | BD0015 | 3049677125 |  |  |  | Home
FALSE | McDowell County | Phase III | BD0016 | 3733FP | Ellen & Margaret Harrison | [33 empty] | FALSE | FALSE |  |  | 0.35 |  | 1183.1 | 1184.8 |  |  | 1189.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0017 | 3734FP | Margaret A. Sebastian | [33 empty] | FALSE | FALSE |  |  | 0.38 |  | 1193.17 | 1189.55 |  |  | 1196.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0019 | 3736FP | Church of God | [33 empty] | FALSE | FALSE |  |  | 0.46 |  | 1189.7 | 1188.8 |  |  | 1194.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0021 | 3737FP | Douglas M. Smallwood | [33 empty] | FALSE | FALSE |  |  | 0.48 |  | 1197.03 | 1192.86 |  |  | 1199.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0030 | 3800FP | Carolyn Sue Horne | [7 empty] | 2015-06-30 | AC | 2015-07-08 | [22 empty] | Converted to Acquisition, no buy-up to floorpfoofing options. SHH 8 Jul 15 | FALSE | FALSE |  |  | 0.69 |  | 1205.5 | 1205.4 |  |  | 1209.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0033 | 3803FP | Peggy P. Crigger | [33 empty] | FALSE | FALSE |  |  | 0.73 |  | 1207.6 | 1206.7 |  |  | 1211.6 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0035 | 3804FP | Harvey J. & Lula Mullins | [33 empty] | FALSE | FALSE |  |  | 0.75 |  | 1206.9 | 1206.5 |  |  | 1213.1 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0039 | 3806FP | McDonald & Lassie Hess | [33 empty] | FALSE | FALSE |  |  | 0.84 |  | 1213 | 1212.7 |  |  | 1220.7 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0046 | 3807FP-1 | Homer Wimmer | [33 empty] | FALSE | FALSE |  |  | 0.85 |  | 1218.7 | 1216.7 |  |  | 1221.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0047 | 3807FP-2 | Homer & Flora Wimmer | [33 empty] | FALSE | FALSE |  |  | 0.89 |  | 1222 | 1217.8 |  |  | 1223.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0048 | 3808FP | Earmele Lester | [33 empty] | FALSE | FALSE |  |  | 0.91 |  | 1222 | 1219 |  |  | 1225.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0051 | 3810FP | Myrtle Y. Gregory | [33 empty] | FALSE | FALSE |  |  | 0.94 |  | 1225.1 | 1221.3 |  |  | 1226.7 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0055 | 3812FP-1 | Douglas & Tina Smallwood | [33 empty] | FALSE | FALSE |  |  | 0.95 |  | 1223.9 | 1221.7 |  |  | 1227.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0056 | 3812FP-2 | Douglas & Tina Smallwood | [33 empty] | FALSE | FALSE |  |  | 0.96 |  | 1224.6 | 1222.8 |  |  | 1227.7 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0058 | 3812FP-3 | Douglas & Tina Smallwood | [33 empty] | FALSE | FALSE |  |  | 0.97 |  | 1222.2 | 1224.2 |  |  | 1228.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0059 | 3813FP | Paul Dale | [33 empty] | FALSE | FALSE |  |  | 0.97 |  | 1224.5 | 1221.3 |  |  | 1228.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0064 | 3816FP | Delmer Mullins | [33 empty] | FALSE | FALSE |  |  | 1 |  | 1230.42 | 1226.58 |  |  | 1230.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0071 | 3821FP | Otis & Irene Hagerman | [33 empty] | FALSE | FALSE |  |  | 1.07 |  | 1237.48 | 1234.65 |  |  | 1238.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0073 | 3822FP | Cathy Reed | [33 empty] | FALSE | FALSE |  |  | 1.1 |  | 1236.5 | 1234 |  |  | 1237.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0074 | 3823FP | Paul & Sharlene McIntosh | [33 empty] | FALSE | FALSE |  |  | 1.1 |  | 1237.2 | 1234.4 |  |  | 1237.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0076 | 3825FP | Billy Gene Poore | [33 empty] | FALSE | FALSE |  |  | 1.14 |  | 1238.76 | 1236.698 |  |  | 1242.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0077 | 3826FP-1 | Ray & Janice Fay Blankenship | [33 empty] | FALSE | FALSE |  |  | 1.16 |  | 1241.49 | 1238.252 |  |  | 1242.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0078 | 3826FP-2 | Ray & Janice Fay Blankenship | [33 empty] | FALSE | FALSE |  |  | 1.17 |  | 1243.31 | 1238.92 |  |  | 1243.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0085 | 3827FP | Verner & Lou Emma Payne | [33 empty] | FALSE | FALSE |  |  | 1.25 |  | 1252.55 | 1248.429 |  |  | 1246.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0086 | 3828FP | Connie Stanley | [33 empty] | FALSE | FALSE |  |  | 1.27 |  | 1245.7 | 1241.83 |  |  | 1248.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0088 | 3829FP | Verner & Lou Emma Payne | [33 empty] | FALSE | FALSE |  |  | 1.3 |  | 1243.1 | 1245.5 |  |  | 1247.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0090 | 3830FP | Verner Payne | [33 empty] | FALSE | FALSE |  |  | 1.42 |  | 1257.77 | 1254.7 |  |  | 1258.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0093 | 3832FP | James & Juanita Payne | [33 empty] | FALSE | FALSE |  |  | 1.47 |  | 1259.18 | 1257.297 |  |  | 1261.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0094 | 3832FP | James & Juanita Payne | [33 empty] | FALSE | FALSE |  |  | 1.48 |  | 1261.11 | 1259.108 |  |  | 1261.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0095 | 3832FP | James & Juanita Payne | [33 empty] | FALSE | FALSE |  |  | 1.49 |  | 1256.7 | 1259.7 |  |  | 1262.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0117 | 3905FP | Thomas E. Lovas | [33 empty] | FALSE | FALSE |  |  | 1.83 |  | 1284.33 | 1287.626 |  |  | 1288.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0120 | 3907FP | Jennifer Jo McClay Mullins | [33 empty] | FALSE | FALSE |  |  | 1.96 |  | 1292.45 | 1296.044 |  |  | 1293.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0138 | 3910FP | Von Thornsberry | [33 empty] | FALSE | FALSE |  |  | 2.2 |  | 1308.1 | 1303.4 |  |  | 1309.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0139 | [35 empty] | FALSE | FALSE |  |  | 2.3 |  | 1317.05 | 1312.497 |  |  | 1318.78 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0143 | 4002FP | Kimberly Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.51 |  | 1320.5 | 1316.6 |  |  | 1321.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0145 | 4003FP | Milda Hicks | [33 empty] | FALSE | FALSE |  |  | 2.58 |  | 1321.7 | 1319 |  |  | 1326.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0024 | 405FP | Blankenship, Mattie Lucille | [5 empty] | 2002-05-18 | [27 empty] | TRUE | FALSE |  |  | 2.7 |  | 1334.1 | 1330.6 |  |  | 1338.55 | 100 year | [11 empty] | NGVD | McDowell County | EC0024 | 3044366347 |  |  |  | Home
FALSE | McDowell County | Phase I | EC0026 |  | Gillespie, George | [33 empty] | FALSE | FALSE |  |  | 2.7 |  | 1334.1 | 1333 |  |  | 1334.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0038 | 0407FP | Short, Robert |  |  | N |  | N |  |  |  | FP |  | 2000-10-18 | 2000-11-01 |  | 2001-04-24 | 50129 | 2001-04-25 | 45800 |  | 2001-04-30 | 45800 | 600 | 2001-04-30 | 2001-06-12 | 2001-06-26 | 2001-06-29 |  | 45800 | 2001-08-30 |  |  | 2001-09-24 |  | Contractor: Tri-City Construction, Sammy White, phone (304) 752-0792 | FALSE | FALSE |  |  | 2.9 |  | 1339.2 | 1336.4 |  |  | 1339.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0040 |  | Mills, James | [33 empty] | FALSE | FALSE |  |  | 2.9 |  | 1339.8 | 1336.4 |  |  | 1339.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0049 |  | Poca Land Corp. | [33 empty] | FALSE | FALSE |  |  | 3.7 |  | 1359.5 | 1357 |  |  | 1363.55 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0055 | 0502FP | Greathead, Victoria | [5 empty] | 2000-06-12 | 2000-08-24 | [25 empty] | Need to do cost comp. | FALSE | FALSE |  |  | 6.1 |  | 1445 | 1443 |  |  | 1445.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0118 |  | White, Anthony | [33 empty] | FALSE | FALSE |  |  | 7.65 |  | 1475.8 | 1473.9 |  |  | 1481.85 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0119 |  | Barksdale, George | [33 empty] | FALSE | FALSE |  |  | 7.65 |  | 1476.4 | 1474.4 |  |  | 1482.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0120 |  | White, Anthony | [33 empty] | FALSE | FALSE |  |  | 7.6 |  | 1475.2 | 1472.1 |  |  | 1480.8 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0121 |  | Heilig, Garnett | [33 empty] | FALSE | FALSE |  |  | 7.6 |  | 1473.4 | 1471.3 |  |  | 1480.8 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0122 |  | Ferguson, Vivian | [33 empty] | FALSE | FALSE |  |  | 7.6 |  | 1473.3 | 1471.6 |  |  | 1480.8 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0123 |  | Dillard, Heath | [33 empty] | FALSE | FALSE |  |  | 7.6 |  | 1474.2 | 1471.9 |  |  | 1480.8 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0125 |  | Shelton, R.J. Estate | [33 empty] | FALSE | FALSE |  |  | 7.6 |  | 1473.5 | 1472.5 |  |  | 1480.8 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0127 |  | Campbell, Frank | [33 empty] | FALSE | FALSE |  |  | 7.65 |  | 1476.6 | 1473.2 |  |  | 1482.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0128 |  | Perdue, Arlie | [33 empty] | FALSE | FALSE |  |  | 7.7 |  | 1475.9 | 1473.8 |  |  | 1484.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0135 | 0604FP | Neal, Lorene | 2001-03-05 | 2001-04-16 | Y |  |  | 2000-05-05 | 2000-08-04 | 2002-01-17 | FP |  | 2002-03-13 | 2002-03-15 | 2002-03-29 | 2002-03-28 | 98215 | 2002-04-13 | 10800 | 106072 | 2002-04-18 | 106672 | 600 | 2002-04-30 | 2002-05-17 | 2002-06-13 | 2002-06-27 |  | 106672 |  |  |  | 2002-12-19 |  | Have GP&S but Donna and Mary Ann want to take another look at this one. | FALSE | FALSE |  |  | 7.7 |  | 1476.8 | 1475.1 |  |  | 1484.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0136 |  | Holland, Sarah | [33 empty] | FALSE | FALSE |  |  | 7.7 |  | 1476.4 | 1475.4 |  |  | 1484.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0138 |  | Sinicrope, Jean | [33 empty] | FALSE | FALSE |  |  | 7.7 |  | 1476.3 | 1476.1 |  |  | 1484.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0140 |  | Town of Kimball | [33 empty] | FALSE | FALSE |  |  | 7.7 |  | 1474.1 | 1478.7 |  |  | 1477.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0157 |  | Johnson, Seeveh D. | [33 empty] | FALSE | FALSE |  |  | 8 |  | 1484.2 | 1482.2 |  |  | 1490.4 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0186 |  | Allen Jr., Joe | [33 empty] | FALSE | FALSE |  |  | 8.7 |  | 1499.3 | 1498 |  |  | 1503.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0187 |  | Evans, Sarah | [33 empty] | FALSE | FALSE |  |  | 8.7 |  | 1500.1 | 1498.5 |  |  | 1503.85 | [12 empty] | NGVD
FALSE | McDowell County | Phase I | EC0188 |  | Weaver, Willie | [33 empty] | FALSE | FALSE |  |  | 8.7 |  | 1500.6 | 1498.6 |  |  | 1503.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0189 |  | Wade, John | [33 empty] | FALSE | FALSE |  |  | 8.7 |  | 1501.6 | 1499.4 |  |  | 1503.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0190 |  | Weaver, Willie | [33 empty] | FALSE | FALSE |  |  | 8.7 |  | 1502.1 | 1499.9 |  |  | 1503.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0227 |  | Blankenship, P.E. | [33 empty] | FALSE | FALSE |  |  | 11.1 |  | 1566.8 | 1564.1 |  |  | 1568.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0229 |  | McDowell Cty Nat'l Bank | [33 empty] | FALSE | FALSE |  |  | 11.1 |  | 1567.8 | 1564.1 |  |  | 1568.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0235 |  | King, Daniel | [33 empty] | FALSE | FALSE |  |  | 11.2 |  | 1569.8 | 1567.2 |  |  | 1571.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0280 | 1112FP | Turner, Dalton | [8 empty] | OT | [24 empty] | FALSE | FALSE |  |  | 12.1 |  | 1593.9 | 1589.6 |  |  | 1594.65 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0281 |  | Luster, Charles | [33 empty] | FALSE | FALSE |  |  | 12.1 |  | 1591.6 | 1590 |  |  | 1594.65 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0282 | 1114FP | Steele, Roger / Carol Hayes | [33 empty] | FALSE | FALSE |  |  | 12.1 |  | 1592.6 | 1590.8 |  |  | 1594.65 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0298 |  | Lambert, Delorse | [33 empty] | FALSE | FALSE |  |  | 12.6 |  | 1610.9 | 1606.3 |  |  | 1614.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0299 | 1206FP | Watkins, Lora | [8 empty] | OT | [23 empty] | Need site visit. | FALSE | FALSE |  |  | 12.9 |  | 1620.4 | 1617.6 |  |  | 1622.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0300 |  | Maderia, Clyde Milton | [33 empty] | FALSE | FALSE |  |  | 12.9 |  | 1621.1 | 1619.6 |  |  | 1622.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0320 |  | Morrison, Scott | [33 empty] | FALSE | FALSE |  |  | 13.7 |  | 1658.6 | 1658.3 |  |  | 1665.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0321 |  | Morrison, Scott | [33 empty] | FALSE | FALSE |  |  | 13.7 |  | 1663.3 | 1659 |  |  | 1668 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0322 |  | Local Union 6196 Keystone | [33 empty] | FALSE | FALSE |  |  | 13.7 |  | 1663.3 | 1659.2 |  |  | 1667.55 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | EC0350 |  | Freeman, Thomas | [33 empty] | FALSE | FALSE |  |  | 0.75 |  | 1305.2 | 1298.5 |  |  | 1310.15 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC0847 |  | Vaughn, William H. Jr. | [33 empty] | FALSE | FALSE |  |  | 133.05 |  | 1283.2 | 1281.3 |  |  | 1286 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC0848 |  | McMillon, John Hart & Romona | [33 empty] | FALSE | FALSE |  |  | 133.06 |  | 1282.7 | 1280.6 |  |  | 1286 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC0856 |  | Lindsey, John D. & Elemora | [33 empty] | FALSE | FALSE |  |  | 133.11 |  | 1283.9 | 1282.3 |  |  | 1286 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC0902 |  | Coe, Paul E. & Patsy Lee | [33 empty] | FALSE | FALSE |  |  | 154.7 |  | 1735.7 | 1732.6 |  |  | 1743.85 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC0932 |  | Paris, Sharon Kay et al | [33 empty] | FALSE | FALSE |  |  | 137.15 |  | 1331.6 | 1328.7 |  |  | 1337.25 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1010 | 1500FP | Friedl, A. A. | [32 empty] | 2/27/18, letter detailing costs incurred on this tract submitted to Program Management, at the request of Judy Heath, CIAD. | FALSE | FALSE |  |  | 143.4 |  | 1431.1 | 1428 |  |  | 1437.55 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1011 | 1501FP | Rose, Shelia | [8 empty] | OT | [24 empty] | FALSE | FALSE |  |  | 143.41 |  | 1431.1 | 1428.6 |  |  | 1438.05 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1012 |  | David, Hoston & Martha M. | [7 empty] | 2002-04-04 | OT | [23 empty] | 6/28/02 SH spoke with David Hoston and was informed that Hoston opted out of the program. | FALSE | FALSE |  |  | 143.44 |  | 1431.7 | 1428.3 |  |  | 1438.55 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1014 |  | Brooks, Paul E. & Patricia Ann | [33 empty] | FALSE | FALSE |  |  | 143.46 |  | 1431.7 | 1429 |  |  | 1439.05 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1059 |  | Hemphill Methodist Church | [33 empty] | FALSE | FALSE |  |  | 133.22 |  | 1282 | 1282.2 |  |  | 1285.6 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1096 |  | Rose, Elmer J. | [33 empty] | FALSE | FALSE |  |  | 133.92 |  | 1292.4 | 1290 |  |  | 1294.1 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase I | MC1098 |  | Miller, Bertha | [33 empty] | FALSE | FALSE |  |  | 133.93 |  | 1292.5 | 1290 |  |  | 1294.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0008 |  | Brant, Gertrude | [33 empty] | FALSE | FALSE |  |  | 1.85 |  | 993.7 | 990.3 |  |  | 994.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0009 |  | Brant, Gertrude | [33 empty] | FALSE | FALSE |  |  | 1.86 |  | 994.4 | 990.2 |  |  | 994.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0011 |  | Brant, Gertrude | [33 empty] | FALSE | FALSE |  |  | 1.88 |  | 995 | 989.9 |  |  | 995.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0012 |  | Mullins, Dewey E. & Naomia | [33 empty] | FALSE | FALSE |  |  | 2.57 |  | 997.1 | 1001.8 |  |  | 999.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0023 |  | Burks, Allen & Nancy | [33 empty] | FALSE | FALSE |  |  | 2.84 |  | 999.3 | 1004.7 |  |  | 1002.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0070 |  | Carter Land Company | [33 empty] | FALSE | FALSE |  |  | 3.96 |  | 1018.9 | 1015.5 |  |  | 1021.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0104 |  | Hopkins, Homer & Joyce | [33 empty] | FALSE | FALSE |  |  | 5.58 |  | 1048.1 | 1045.2 |  |  | 1049.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | DF0120 |  | Shelton, Iris D. | [33 empty] | FALSE | FALSE |  |  | 6.29 |  | 1058.7 | 1060.1 |  |  | 1059.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0023 |  | Chapman, John & Rhoda | [33 empty] | FALSE | FALSE |  |  | 102.3 |  | 935.6 | 930.5 |  |  | 937.36 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0024 |  | Chapman, John & Rhoda | [33 empty] | FALSE | FALSE |  |  | 102.3 |  | 935 | 931.9 |  |  | 937.36 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0031 |  | Coleman, Douglas M. | [33 empty] | FALSE | FALSE |  |  | 0.31 |  | 940.15 | 937.85 |  |  | 942.25 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0033 |  | Board of Education (Panther Elem) | [33 empty] | FALSE | FALSE |  |  | 0.31 |  | 936.85 | 931.45 |  |  | 943.25 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0034 |  | Board of Education (Panther Elem) | [33 empty] | FALSE | FALSE |  |  | 0.31 |  | 935.25 | 931.55 |  |  | 943.25 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0057 |  | Blankenship, Charles | [33 empty] | FALSE | FALSE |  |  | 103.3 |  | 944.2 | 943.2 |  |  | 945.62 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0080 |  | Virginia Crews Coal Company | [33 empty] | FALSE | FALSE |  |  | 107.8 |  | 957.4 | 957.2 |  |  | 964.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0104 |  | McCoy, Oscar Jr. & Ruby Asbury | [33 empty] | FALSE | FALSE |  |  | 0.4 |  | 979.55 | 979.15 |  |  | 981.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0108 |  | Board of Education | [33 empty] | FALSE | FALSE |  |  | 110 |  | 974.6 | 973 |  |  | 976.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0117 | 2535FP | Addair, Scarlett | 2001-03-05 | [6 empty] | 2002-01-17 | OT | [23 empty] | Per memo 9-17-01, owner wished to opt out of the program and was consequently permanently withdrawn. MS | FALSE | FALSE |  |  | 0.1 |  | 978.85 | 976.75 |  |  | 979.65 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0122 |  | Dale, Paul D. & Anita M. | [33 empty] | FALSE | FALSE |  |  | 110.2 |  | 977.5 | 973.7 |  |  | 977.9 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0125 | 2532FP | Long, Sandra | 2001-03-05 |  | N |  | N |  | 2006-05-24 | 2002-01-17 | BU | 2002-05-01 |  | 2009-06-23 | 2009-07-08 | 2009-03-10 | 77015 | 2009-06-23 | 184500 |  | 2009-03-10 | 77015 | 0 | 2009-07-09 | 2009-08-10 | 2009-08-27 | 2009-09-22 |  | 77015 | 2010-03-01 | 2010-03-09 | 2010-03-16 | 2010-04-06 |  | The site visted was completed on this one. Donna and Mary Ann want to look at this one again. | FALSE | FALSE |  |  | 110.2 |  | 976 | 973.9 |  | 978.9 | 977.9 | 1977 | 3 | [7 empty] | Y |  |  | NGVD | McDowell County | MC0125 | 3049383036 |  |  |  | Home |  |  |  | 7
FALSE | McDowell County | Phase II | MC0133 | 2527FP | Rice, Virgie | 2001-03-05 | [7 empty] | OT | [24 empty] | FALSE | FALSE |  |  | 110.3 |  | 977.9 | 975.2 |  |  | 979.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0134 |  | Iaeger Methodist Church | [33 empty] | FALSE | FALSE |  |  | 110.3 |  | 977.6 | 975.2 |  |  | 979.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0135 |  | Roberts, Perry H. & Pauline | [33 empty] | FALSE | FALSE |  |  | 110.3 |  | 979.4 | 974.9 |  |  | 979.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0136 |  | Roberts, Perry H. & Pauline | [33 empty] | FALSE | FALSE |  |  | 110.3 |  | 978.3 | 974.8 |  |  | 979.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0143 | 1502FP | Hatfield, David & Della Jean | [8 empty] | OT | [23 empty] | opted out 2001 This tract number may be wrong. Structure info agrees with structure data sheets, but other structures in this sequence are in 2500 tract series. This one appears to be Tract 2523FP with owners being on record as Wilbert Marcum and Madge Robertson. 10/12/18 dh | FALSE | FALSE |  |  | 110.3 |  | 978.4 | 971 |  |  | 979.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0183 | 2501FP | Hare, Paul & Laura | 2001-03-05 | 2001-04-16 | [6 empty] | OT | 2002-05-29 | [22 empty] | Tried to do site visit. Was told Homeowner was in the Hospital. Converted to ACQ. because of lot restrictions. SH 5-29-02 Per memo dated 8/5/02, Laura Hare opted out of the program. MS | FALSE | FALSE |  |  | 110.3 |  | 979.5 | 976 |  |  | 982.5 | 100 year | [8 empty] | N |  |  | NGVD
FALSE | McDowell County | Phase II | MC0190 | 2508FP | Pioneer Community Bank | [5 empty] | 2001-02-27 | 2002-07-09 | 2002-07-29 | AC | 2003-03-03 | [23 empty] | FALSE | FALSE |  |  | 110.6 |  | 980.3 | 980.1 |  |  | 980.55 | 1977 | [8 empty] | N |  |  | NGVD
FALSE | McDowell County | Phase II | MC0192 | 2510FP | Vance, Shirley R. & Johnson | [33 empty] | FALSE | FALSE |  |  | 110.6 |  | 978.3 | 977.1 |  |  | 980.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0193 | 2511FP | A.F.& A.M. Lodge | 2001-03-05 | [7 empty] | AC | 2002-07-02 | [22 empty] | Need site visit. | FALSE | FALSE |  |  | 110.6 |  | 979 | 977.3 |  |  | 980.55 | 1977 | [8 empty] | N |  |  | NGVD
FALSE | McDowell County | Phase II | MC0195 |  | Ameribank Welch WV Inc | [33 empty] | FALSE | FALSE |  |  | 110.5 |  | 978.9 | 976.9 |  |  | 980.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0207 |  | Sowards, James Jr. & Hazel F. | [33 empty] | FALSE | FALSE |  |  | 111.3 |  | 979.5 | 978.4 |  |  | 986 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0211 | 2504FP | Fanning, John P. | [7 empty] | 2002-01-29 | OT | [23 empty] | Per memo 4-10-03, Tract 2504FP converted to acquisition. Per memo 2-29-08, Tract 2504 was permanently withdrawn due to owner not responding to requests for Right of Entry and hazardous materials investigation. MS | FALSE | FALSE |  |  | 110.8 |  | 981.9 | 978.1 |  |  | 982.5 | 100 year | [8 empty] | Y |  |  | NGVD
FALSE | McDowell County | Phase II | MC0224 |  | Unknown | [33 empty] | FALSE | FALSE |  |  | 123.8 |  | 1149.5 | 1147.2 |  |  | 1154 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0235 |  | Church, Elsie S. | [33 empty] | FALSE | FALSE |  |  | 111.7 |  | 985.5 | 982.8 |  |  | 987.5 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0244 | 3109FP | Lester, Chrissy | [8 empty] | NE | 2002-03-28 | [22 empty] | Was told that this structure and land was owned by the father Charles Lester. Later told that the trailer was owned by the daughter Chrissy and the land by the dad. Also need to check when this trailer was moved in and what the elevation is. Was convertered to ACQ. 3-28-02. SH | FALSE | FALSE |  |  | 111.8 |  | 984.9 | 982.3 |  |  | 988 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0265 |  | Butler, Sam Jr. & Emma Lori | [33 empty] | FALSE | FALSE |  |  | 112 |  | 986.1 | 983.7 |  |  | 989 | 100 year | [11 empty] | NGVD | McDowell County | MC0265 | [8 empty] | 0
FALSE | McDowell County | Phase II | MC0276 | 3200FP | Hatcher, Ivan & Glenna | 2001-03-05 | [5 empty] | 2000-10-16 | 2001-01-26 | AC | 2002-04-08 | 2001-02-28 | 2001-05-07 | 2001-05-21 | [19 empty] | Mary Ann and Donna wanted to look at this one again. Converted to ACQ because of cost. SH 4-9-02 | FALSE | FALSE |  |  | 112.3 |  | 988.2 | 984.2 |  |  | 991.5 | 100 year | [8 empty] | Y |  |  | NGVD
FALSE | McDowell County | Phase II | MC0381 |  | Roberts, Harry L. | [33 empty] | FALSE | FALSE |  |  | 118.1 |  | 1068.2 | 1064.4 |  |  | 1068.56 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0385 |  | Matney, Okie | [33 empty] | FALSE | FALSE |  |  | 118.1 |  | 1065.1 | 1059.6 |  |  | 1068.56 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0390 |  | Blankenship, Thelma | [33 empty] | FALSE | FALSE |  |  | 118.2 |  | 1066 | 1061.5 |  |  | 1070 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0391 |  | Blankenship, Thelma | [33 empty] | FALSE | FALSE |  |  | 118.2 |  | 1064.8 | 1062.1 |  |  | 1070 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0393 |  | Blankenship, Thelma | [33 empty] | FALSE | FALSE |  |  | 118.2 |  | 1065.9 | 1063.5 |  |  | 1070 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0397 |  | Matney, David | [33 empty] | FALSE | FALSE |  |  | 118.3 |  | 1068.5 | 1065.2 |  |  | 1072 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0447 | 3401FP | Glass, Charles | [33 empty] | FALSE | FALSE |  |  | 121 |  | 1110.6 | 1107.3 |  |  | 1113.74 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0461 |  | Assembly of God of Hensley | [33 empty] | FALSE | FALSE |  |  | 122.3 |  | 1132.1 | 1128 |  |  | 1133.34 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0494 | 3606FP | Brooks, Charles & Charmaine | 2001-03-05 | [7 empty] | AC | 2001-06-20 | [23 empty] | FALSE | FALSE |  |  | 124.6 |  | 1155.1 | 1151.3 |  |  | 1161 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0672 |  | Trent, Ottaway | [33 empty] | FALSE | FALSE |  |  | 101.5 |  | 933.1 | 929.5 |  |  | 933.61 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0680 | 3109FP | Lester, Charles Jr. & Patty B. | 2001-03-05 |  | N |  | N |  | 2000-09-08 | 2002-01-17 | FP |  | 2002-06-12 | 2002-06-26 | 2002-07-10 | 2002-06-28 | 59701 | 2002-07-29 | 71000 |  | 2002-06-26 | 65000 | 0 | 2002-09-06 | 2002-09-13 | 2002-09-25 | 2002-10-01 |  | 65000 |  | 2003-01-09 | 2003-01-13 | 2003-01-28 |  | Elevation check. Structures there now are not what are shown on maps. | FALSE | FALSE |  |  | 111.8 |  | 983.7 | 978.1 |  |  | 988 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0682 | 3202FP | Hess, William Andrew & Essie Louise | [33 empty] | FALSE | FALSE |  |  | 112.7 |  | 990.9 | 986.6 |  |  | 995 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0683 | 3202FP | Hess, William Andrew & Essie Louise | [33 empty] | FALSE | FALSE |  |  | 112.7 |  | 989.2 | 985.2 |  |  | 995 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0686 |  | Cassidy, Patty | [33 empty] | FALSE | FALSE |  |  | 115.8 |  | 1032.4 | 1029.4 |  |  | 1037 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0694 | 3403FP | Helmandollar, Ruth E. | [5 empty] | 2002-11-05 | 2003-02-24 | [26 empty] | FALSE | FALSE |  |  | 121 |  | 1115.9 | 1107.9 |  |  | 1116.1 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0704 |  | McMelly, Tommy & Edna | [33 empty] | FALSE | FALSE |  |  | 123.5 |  | 1140.9 | 1138.2 |  |  | 1147 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0707 |  | Georgia Pacific Corp. | [33 empty] | FALSE | FALSE |  |  | 127.58 |  | 1196.5 | 1192.6 |  |  | 1203.3 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0711 |  | Coleman, Douglas & Josie | [33 empty] | FALSE | FALSE |  |  | 101.44 |  | 925.2 | 922.3 |  |  | 933 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0737 |  | McMelly, Tommy & Edna | [33 empty] | FALSE | FALSE |  |  | 123.57 |  | 1141.4 | 1138.2 |  |  | 1152.5 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0763 |  | Griffith, Luther Dickson et al | [33 empty] | FALSE | FALSE |  |  | 0.21 |  | 938.6 | 935 |  |  | 942.25 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0764 |  | Blankenship, Jerry Dean | [33 empty] | FALSE | FALSE |  |  | 101.39 |  | 930.5 | 927.8 |  |  | 933 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0792 |  | Coleman, Douglas M. | [33 empty] | FALSE | FALSE |  |  | 0.12 |  | 940.5 | 936.7 |  |  | 942.25 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0799 |  | Blankenship, Thelma | [33 empty] | FALSE | FALSE |  |  | 118.3 |  | 1068.4 | 1064.4 |  |  | 1072 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0263 |  | Butler, Sam Jr. & Emma Lori | [33 empty] | FALSE | FALSE |  |  | 111.98 |  | 985.4 | 981.9 |  |  | 989 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0804 |  | Church, Tom C. | [33 empty] | FALSE | FALSE |  |  | 111.74 |  | 984.9 | 981.1 |  |  | 988 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0008 |  | Bailey, Wilma D. | [33 empty] | FALSE | FALSE |  |  | 1.13 |  | 961.8 | 957.6 |  |  | 965.31 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0011 |  | McGuire, Elmer | [33 empty] | FALSE | FALSE |  |  | 1.34 |  | 968.9 | 965.8 |  |  | 974.85 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0013 |  | McGuire, Elmer | [33 empty] | FALSE | FALSE |  |  | 1.39 |  | 970.7 | 967.3 |  |  | 974.85 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0015 |  | Justice, Arthur G. & Wanda | [33 empty] | FALSE | FALSE |  |  | 1.43 |  | 971.8 | 968.7 |  |  | 974.85 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0020 |  | Roberts, Clyde | [33 empty] | FALSE | FALSE |  |  | 1.58 |  | 976 | 972 |  |  | 981.6 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0025 |  | Hagy, Cordelia | [33 empty] | FALSE | FALSE |  |  | 2.11 |  | 986.4 | 983.8 |  |  | 992.61 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0026 |  | Panther Creek Regular Baptist Church | [33 empty] | FALSE | FALSE |  |  | 2.1 |  | 986.4 | 989.8 |  |  | 992.61 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0029 |  | Strickland, Boblue H. | [33 empty] | FALSE | FALSE |  |  | 2.19 |  | 990 | 987.5 |  |  | 998.2 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0033 |  | Bailey, Martha Ellen | [33 empty] | FALSE | FALSE |  |  | 2.33 |  | 1000.2 | 996.6 |  |  | 1005.61 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0040 |  | Justice, Zeb | [33 empty] | FALSE | FALSE |  |  | 3.06 |  | 1021.5 | 1017.5 |  |  | 1026.2 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0042 |  | Justice, Zeb | [33 empty] | FALSE | FALSE |  |  | 3.09 |  | 1020.9 | 1018.2 |  |  | 1026.2 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase II | PC0046 |  | W. Va. State Conservation Commission | [33 empty] | FALSE | FALSE |  |  | 3.95 |  | 1054.8 | 1051.5 |  |  | 1060.75 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0148 | 4005FP | Adam & Roy Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.63 |  | 1326.1 | 1322.7 |  |  | 1331.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0149 | 4005FP | Adam & Roy Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.64 |  | 1326.3 | 1323 |  |  | 1333 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0150 | 4005FP | Adam & Roy Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.68 |  | 1327.3 | 1324 |  |  | 1335.1 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0151 | 4005FP | Adam & Roy Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.7 |  | 1328.2 | 1324.7 |  |  | 1336.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0152 | 4005FP | Adam & Roy Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.7 |  | 1327.2 | 1323.5 |  |  | 1336.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0153 | 4005FP | Adam & Roy Hagerman | [33 empty] | FALSE | FALSE |  |  | 2.71 |  | 1328.7 | 1324.8 |  |  | 1336.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0155 | 4006FP | Sherri L. Hatfield | [6 empty] | 2011-03-03 |  | AC | [23 empty] | EC-DS MEMO 07Apr2010: Justification Not To Raise. | FALSE | FALSE |  |  | 2.71 |  | 1330.2 | 1326.6 |  |  | 1336.9 | 1977 | [11 empty] | NGVD | McDowell County | BD0155 | 3049675522 |  |  |  | Home |  |  |  | 0
FALSE | McDowell County | Phase III | BD0160 | 4008FP | Ray Hatfield | [33 empty] | FALSE | FALSE |  |  | 2.71 |  | 1331.1 | 1328.8 |  |  | 1336.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0161 | 4009FP | Ray & Claudine Hatfield | [33 empty] | FALSE | FALSE |  |  | 2.71 |  | 1331.1 | 1328.1 |  |  | 1336.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0162 | 4009FP | Ray & Claudine Hatfield | [33 empty] | FALSE | FALSE |  |  | 2.72 |  | 1331.4 | 1327.5 |  |  | 1337.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0163 | 4010FP | Montigue & Charlene Thomas | [33 empty] | FALSE | FALSE |  |  | 2.71 |  | 1330.1 | 1327.1 |  |  | 1336.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0165 | 4011FP | Shelby & Shirley A. Mullins | [33 empty] | FALSE | FALSE |  |  | 2.78 |  | 1331 | 1327.9 |  |  | 1341.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0166 | 4011FP | Shelby & Shirley A. Mullins | [33 empty] | FALSE | FALSE |  |  | 2.78 |  | 1332.4 | 1328.6 |  |  | 1341.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0168 | 4011FP | Shelby & Shirley A. Mullins | [33 empty] | FALSE | FALSE |  |  | 2.79 |  | 1332.99 | 1330.686 |  |  | 1336.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0169 | 4011FP | Shelby & Shirley A. Mullins | [33 empty] | FALSE | FALSE |  |  | 2.79 |  | 1333.4 | 1330.1 |  |  | 1342.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0171 | 4012FP | E.E. O'Quinn | [33 empty] | FALSE | FALSE |  |  | 2.8 |  | 1337.1 | 1334.2 |  |  | 1343.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0172 | 4012FP | E.E. O'Quinn | [33 empty] | FALSE | FALSE |  |  | 2.8 |  | 1337.1 | 1333.4 |  |  | 1343.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0173 | 4012FP | E.E. O'Quinn | [33 empty] | FALSE | FALSE |  |  | 2.8 |  | 1335.5 | 1333.1 |  |  | 1343.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0176 | 4013FP | E.E. O'Quinn | [33 empty] | FALSE | FALSE |  |  | 2.81 |  | 1337.7 | 1335.1 |  |  | 1344.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0177 | 4014FP | Margaret Estep | [33 empty] | FALSE | FALSE |  |  | 2.82 |  | 1337.3 | 1332.8 |  |  | 1345.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0179 | 4015FP | Robert J. & Margaret A. Compton | [33 empty] | FALSE | FALSE |  |  | 2.84 |  | 1333.1 | 1335.3 |  |  | 1347.6 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0181 | 4017FP-1 | Family Worship Center of Bradshaw | [33 empty] | FALSE | FALSE |  |  | 2.92 |  | 1344.7 | 1339.8 |  |  | 1355.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0182 | 4017FP-2 | Family Worship Center of Bradshaw | [33 empty] | FALSE | FALSE |  |  | 2.93 |  | 1347.1 | 1342.1 |  |  | 1356.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0183 | 4017FP-3 | Doris Ann Gibson | [33 empty] | FALSE | FALSE |  |  | 2.96 |  | 1350.7 | 1346.5 |  |  | 1360 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0185 | 4019FP-1 | Walter R. | [33 empty] | FALSE | FALSE |  |  | 3 |  | 1353.4 | 1351.1 |  |  | 1364.1 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0188 | 4019FP-2 | Walter R. | [33 empty] | FALSE | FALSE |  |  | 3.09 |  | 1365.3 | 1362 |  |  | 1372.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0190 | 4020FP | Adam Hagerman & Arthur Beavers | [33 empty] | FALSE | FALSE |  |  | 3.15 |  | 1367.53 | 1364.179 |  |  | 1371.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0192 | 4022FP | Bobby J. & Mary Thornsberry | [33 empty] | FALSE | FALSE |  |  | 3.21 |  | 1376.97 | 1372.669 |  |  | 1380.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0193 | 4023FP | Wilda Smith | [33 empty] | FALSE | FALSE |  |  | 3.27 |  | 1378.36 | 1374.26 |  |  | 1380.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0195 | 4024FP | Marika Baker Mounts & Edna Boyd Baker | [33 empty] | FALSE | FALSE |  |  | 3.27 |  | 1379.92 | 1379.69 |  |  | 1380.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0196 | 4025FP | Laura Mildred Keene | [33 empty] | FALSE | FALSE |  |  | 3.28 |  | 1377.79 | 1375.62 |  |  | 1380.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0001 | 4607FP | Roger L. Kennedy | [33 empty] | FALSE | FALSE |  |  | 0.37 |  | 1482.25 | 1480.05 |  |  | 1483.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0002 | 4608FP | Rita Sue Kennedy | [33 empty] | FALSE | FALSE |  |  | 0.38 |  | 1483.55 | 1481.15 |  |  | 1484.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0004 | 4609FP | Quinton L. Dawson | [33 empty] | FALSE | FALSE |  |  | 0.4 |  | 1486.05 | 1483.85 |  |  | 1487.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0007 | 4610FP | Bruce & Bonnie E. Oxford | [33 empty] | FALSE | FALSE |  |  | 0.45 |  | 1494.45 | 1492.45 |  |  | 1494.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0010 | 4611FP | Newburn M. & Maxine L. Sykes | [33 empty] | FALSE | FALSE |  |  | 0.5 |  | 1500.25 | 1496.05 |  |  | 1501.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0011 | 4612FP | Dan & Flora Foley | [33 empty] | FALSE | FALSE |  |  | 0.54 |  | 1503.85 | 1501.45 |  |  | 1505.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0013 | 4614FP | John W. III & Phyllis A. Russell | [33 empty] | FALSE | FALSE |  |  | 0.61 |  | 1510.95 | 1507.95 |  |  | 1511.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0016 | 4617FP | Billy Beavers | [33 empty] | FALSE | FALSE |  |  | 0.66 |  | 1517.85 | 1514.35 |  |  | 1520.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0017 | 4618FP | Michael Ray Cook | [33 empty] | FALSE | FALSE |  |  | 0.67 |  | 1519.05 | 1516.15 |  |  | 1522.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0019 | 4620FP | Emma Christian | [33 empty] | FALSE | FALSE |  |  | 0.7 |  | 1521.95 | 1518.05 |  |  | 1525.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0021 | 4621FP | Alma Sue Kidwell | [33 empty] | FALSE | FALSE |  |  | 0.72 |  | 1524.25 | 1520.35 |  |  | 1527.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0022 | 4622FP | Emma Jean Christian | [33 empty] | FALSE | FALSE |  |  | 0.73 |  | 1526.75 | 1523.55 |  |  | 1528.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | BH0026 | 4625FP | Danny Ray & Sandra Irene Kennedy | [33 empty] | FALSE | FALSE |  |  | 0.69 |  | 1519.65 | 1518.15 |  |  | 1524.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County |  | BR0008 | [35 empty] | FALSE | FALSE |  |  | 0.2 |  | 1292.6 | 1296.5 |  |  | 1293.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County |  | BR0009 | [35 empty] | FALSE | FALSE |  |  | 0.25 |  | 1296.8 | 1300.6 |  |  | 1299.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County |  | BR0010 | [35 empty] | FALSE | FALSE |  |  | 0.25 |  | 1296.5 | 1300.5 |  |  | 1299.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD001A | 3739FP | Osbourne Grizzle Sara (Randy) | [32 empty] | Randy Osbourne passed away on Dec 2015. His daughter will be taking care of the home from now on. Her address is the same as his was. SHH Jan 2016 | FALSE | FALSE | Levisa Fork | P.O. Box 184 Bradshaw, Wv | 0.25 | 24817 | 1178.42 | 1176.72 |  |  | 1186.85 | 1977 | [5 empty] | N |  |  | Y | N | Y | NGVD | McDowell County | BD001A | 3049382539 | [7 empty] | 0 | email - jwg0523@yahoo.com P.O. Box Bradshaw, WV 24817
FALSE | McDowell County |  | BR0014 | [35 empty] | FALSE | FALSE |  |  | 0.3 |  | 1301.9 | 1297.9 |  |  | 1303.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County |  | BR0022 | [35 empty] | FALSE | FALSE |  |  | 1.62 |  | 1405.3 | 1405.2 |  |  | 1411.65 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | BD0032 | 3802FP | Puckett William | [5 empty] | 2016-11-10 |  | 2017-05-25 | AC | [23 empty] | Mr. Puckett called to see when he could expect a site visit. Called back, got ans. Machine, responded with 2 - 4 weeks and would call to schedule with him before we came out. 4/14/17 dh Received HTRW results from Frank Albert 04/26/2017 CH Received Justification not to lift from Jeremy Miller 06/02/17. Starting requests for Replacement & demo estimate, request for appraisal. 06/06/17 dh Received Replacement estimate 08/18/17 MS; Cost comparison indicates conversion to acquisition cheaper option. MS 9/25/17 received memo from RE-P converting to acquisition. Tract 3802FP deleted and designated as tract 3802. | FALSE | FALSE |  |  | 1.63 |  | 1203.6 | 1203.7 |  |  | 1210.85 | 1977 | [11 empty] | NGVD | McDowell County | BD0032 | 3049677299 |  |  |  | Mr. Puckett |  |  |  | 0
FALSE | McDowell County | Phase III | DF0182 | 3720FP | Elizabeth Jane Rowe Webb | [33 empty] | FALSE | FALSE |  |  | 11.56 |  | 1169.6 | 1166.4 |  |  | 1170.9 | 1977 | [11 empty] | NGVD | McDowell County | DF0182 | 3049679052 |  |  |  | Home |  |  |  | 0 | P.O. Box 726 Bradshaw, WV 24817
FALSE | McDowell County | Phase III | DF0196 | 3702FP | Ballard S. Chafin | [33 empty] | FALSE | FALSE |  |  | 11.56 |  | 1171 | 1177.9 |  |  | 1177.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | DF0211 | 3721FP | Earnest Wade Steele | [7 empty] | 2015-11-19 | AC | 2015-11-23 | [23 empty] | FALSE | FALSE |  |  | 0.2 |  | 1172.4 | 1173.7 |  |  | 1186.45 | 1977 |  |  |  |  | Height of raise exceeds the 12' max. The height of raise for this structue is 14.45'. Therefore this structure is converted to acquistion on 23 Nov 2015. SHH | [6 empty] | NGVD | McDowell County | DF0211 | 3049679052 |  |  |  | home |  |  |  | 0 | P.O. Box 726 Bradshaw, WV 24817
FALSE | McDowell County | Phase III | DF0226 | 3715FP | Payne Jr, Fred D. & Carol Sue Horne | 2017-02-03 |  |  | 2017-07-10 | N | 2015-07-24 | 2015-07-24 | 2017-05-25 | HR |  | 2017-08-01 | 2017-08-04 | 2017-08-18 | 2017-08-29 | 154963.22 | 2017-08-22 | 159960 |  | 2017-09-11 | 159960 | 0 | 2017-09-19 | 2017-09-27 | 2017-10-04 | 2017-10-24 |  |  | 2018-03-19 | 2018-03-20 | 2018-03-23 | 2018-04-25 | 2018-05-11 | Current owners are Fred D. Payne, Jr. and Carol Sue Horne (heirs of Fred & Opal Payne) Homeowners opted for home owner replacement. Submitted foundation and floor plans 14 Sep 17. EC-DS approved submitted plan 14 Sep 17. | FALSE | FALSE |  |  | 0.0825 |  | 1173.6 | 1171 |  |  | 1176.95 | 1977 |  |  |  |  | HTRW clear for floodproofing, would require more extensive testing if acquired. Reports in folder 7/17/17 dh | [6 empty] | NGVD | McDowell County | DF0226 | 3049675260 |  |  |  | Home |  |  |  | 24
FALSE | McDowell County | Phase III | DF0236 | 3716FP | Bryan & Susan Pack | [6 empty] | 2011-03-03 | [26 empty] | FALSE | FALSE |  |  | 0.075 |  | 1174.6 | 1171.8 |  |  | 1176.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | DF0259 | 4100FP | Debra Jo Fife | [33 empty] | FALSE | FALSE |  |  | 13.05 |  | 1193.7 | 1193.7 |  |  | 1196.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0343 | 4309FP | Raymond P. & Mattie M. White | [33 empty] | FALSE | FALSE |  |  | 17 |  | 1267.1 | 1263.1 |  |  | 1268.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0359 | 4317FP | Roland Pruitt | [33 empty] | FALSE | FALSE |  |  | 17.17 |  | 1267.9 | 1265.6 |  |  | 1269.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0360 | 4318FP | Darrell Rose | [33 empty] | FALSE | FALSE |  |  | 17.17 |  | 1267.4 | 1266.8 |  |  | 1269.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0363 | 4319FP | Adams, Kieth D. | [6 empty] | 2011-03-03 | [26 empty] | FALSE | FALSE |  |  | 17.19 |  | 1268.5 | 1266.6 |  |  | 1269.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0387 | 4333FP | Marion & Deborah Sweeney | [33 empty] | FALSE | FALSE |  |  | 17.46 |  | 1271 | 1268.5 |  |  | 1272.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0404 | 4400FP | Ruth R. Hutchins | [33 empty] | FALSE | FALSE |  |  | 17.96 |  | 1275.7 | 1272.2 |  |  | 1276.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0411 | 4404FP | Quinton Louie Dawson | [33 empty] | FALSE | FALSE |  |  | 18.15 |  | 1276.6 | 1274 |  |  | 1277.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0435 | 4412FP | Billy Joe & Carolyn Sue Barrett | [33 empty] | FALSE | FALSE |  |  | 18.67 |  | 1281.75 | 1279.55 |  |  | 1282.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0495 | 4522FP | Yukon Community Church | [33 empty] | FALSE | FALSE |  |  | 20.52 |  | 1303.05 | 1303.65 |  |  | 1304.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0537 | 4805FP | Calvary Baptist Church | [33 empty] | FALSE | FALSE |  |  | 23.17 |  | 1340.75 | 1335.95 |  |  | 1337.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0567 | 4811FP | Julius Dwight & Loretta Mask | [33 empty] | FALSE | FALSE |  |  | 22.6 |  | 1327.25 | 1325.75 |  |  | 1328.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0610 | 4907FP | John E. Dash | [33 empty] | FALSE | FALSE |  |  | 23.67 |  | 1347.65 | 1344.85 |  |  | 1348.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0611 | 4908FP | Noah & Emma Jo Dellorso | [33 empty] | FALSE | FALSE |  |  | 23.68 |  | 1347.05 | 1346.45 |  |  | 1348.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0631 | 4914FP | Julia Zando | [33 empty] | FALSE | FALSE |  |  | 23.99 |  | 1354.15 | 1350.15 |  |  | 1352.95 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0638 | 4916FP | Oscar C. & George Opel Brewster | [33 empty] | FALSE | FALSE |  |  | 24.08 |  | 1355.25 | 1352.05 |  |  | 1353.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0648 | 4918FP | Roy & Georgia Hyatt | [33 empty] | FALSE | FALSE |  |  | 24.16 |  | 1349.65 | 1355.15 |  |  | 1354.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0649 | 4917FP | William E. Jaber | [33 empty] | FALSE | FALSE |  |  | 24.15 |  | 1348.35 | 1349.65 |  |  | 1354.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0677 | 150-2FP | Board of Education | [33 empty] | FALSE | FALSE |  |  | 28.17 |  | 1459.75 | 1464.15 |  |  | 1467.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0681 | 5002FP | Esther Sebastin | [33 empty] | FALSE | FALSE |  |  | 28.48 |  | 1471.25 | 1468.15 |  |  | 1472.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0682 | 5003FP | Billy Blevins | [33 empty] | FALSE | FALSE |  |  | 28.46 |  | 1471.55 | 1467.35 |  |  | 1472.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0683 | 5004FP | Monica Asbury | [33 empty] | FALSE | FALSE |  |  | 28.45 |  | 1471.65 | 1466.85 |  |  | 1472.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0685 | 5005FP | Augustine & Juanita Dellorso | [33 empty] | FALSE | FALSE |  |  | 28.41 |  | 1471.45 | 1467.55 |  |  | 1471.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0686 | 5006FP | Leonard & Betty L. Harless | [33 empty] | FALSE | FALSE |  |  | 28.4 |  | 1470.95 | 1468.35 |  |  | 1471.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0704 | 5007FP | Steven M. & Deborah Johnson | [33 empty] | FALSE | FALSE |  |  | 28.66 |  | 1468.45 | 1471.45 |  |  | 1474.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0707 | 5009FP | Benny Wilson | [33 empty] | FALSE | FALSE |  |  | 28.58 |  | 1472.85 | 1469.85 |  |  | 1473.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0718 | 5011FP | Thelma Duff | [33 empty] | FALSE | FALSE |  |  | 28.6 |  | 1470.7 | 1471.3 |  |  | 1474.05 | 100 year | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0732 | 5100FP | Richard Price Kestner | [33 empty] | FALSE | FALSE |  |  | 28.88 |  | 1476.15 | 1474.35 |  |  | 1477.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0733 | 5101FP | John M. & Pamela D. Veselosky | [33 empty] | FALSE | FALSE |  |  | 28.9 |  | 1477.25 | 1474.25 |  |  | 1478.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0751 | 5104FP | Janice L. Ashworth | [33 empty] | FALSE | FALSE |  |  | 29.02 |  | 1476.95 | 1475.05 |  |  | 1479.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0756 | 5106FP | Jennifer Jordan | [33 empty] | FALSE | FALSE |  |  | 29.12 |  | 1479.65 | 1476.95 |  |  | 1480.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0758 | 5107FP | Winford Crouse | [33 empty] | FALSE | FALSE |  |  | 29.12 |  | 1477.65 | 1479.55 |  |  | 1480.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0759 | 5108FP | Winford & Blanche Crouse | [33 empty] | FALSE | FALSE |  |  | 29.13 |  | 1476.85 | 1478.95 |  |  | 1480.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0760 | 5109FP | Fred E. Baldwin | [33 empty] | FALSE | FALSE |  |  | 29.14 |  | 1477.25 | 1479.55 |  |  | 1480.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0762 | 5110FP | Daniel R. Riley | [33 empty] | FALSE | FALSE |  |  | 29.15 |  | 1479.35 | 1479.05 |  |  | 1480.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0773 | 5111FP | Matthew D. Johnson | [33 empty] | FALSE | FALSE |  |  | 29.28 |  | 1482.05 | 1484.05 |  |  | 1484.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0793 | 5201FP | Berwind Revival Center | [33 empty] | FALSE | FALSE |  |  | 30.12 |  | 1501.35 | 1499.55 |  |  | 1502.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0796 | 5203FP | Sonny Mitchell | [33 empty] | FALSE | FALSE |  |  | 30.15 |  | 1501.75 | 1499.35 |  |  | 1502.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0801 | 5204FP | William H. Dishman | [33 empty] | FALSE | FALSE |  |  | 30.39 |  | 1505.25 | 1508.15 |  |  | 1507.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0819 | 5206FP | Leona Wingo | [33 empty] | FALSE | FALSE |  |  | 31.18 |  | 1527.45 | 1522.45 |  |  | 1529.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0834 | 5207FP | Willard W. Crouse | [33 empty] | FALSE | FALSE |  |  | 31.43 |  | 1533.85 | 1531.45 |  |  | 1538.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase IV | DF0882 | 5211FP | James B. & Merle Lickhart | [33 empty] | FALSE | FALSE |  |  | 33.41 |  | 1579.95 | 1581.55 |  |  | 1583.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0003 | 4102FP | Debonah Henderson | [33 empty] | FALSE | FALSE |  |  | 0.1 |  | 1202.05 | 1200.25 |  |  | 1203.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0004 | 4103FP | Maggie V. Pruett | [33 empty] | FALSE | FALSE |  |  | 0.11 |  | 1203.05 | 1200.05 |  |  | 1205.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0006 | 4105FP | Arland L. & Betty Jean Payne | [33 empty] | FALSE | FALSE |  |  | 0.13 |  | 1205.35 | 1203.45 |  |  | 1206.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0007 | 4106FP | Arland Payne | [33 empty] | FALSE | FALSE |  |  | 0.14 |  | 1205.65 | 1204.65 |  |  | 1208.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0008 | 4107FP | George Serra | [33 empty] | FALSE | FALSE |  |  | 0.16 |  | 1206.45 | 1204.85 |  |  | 1208.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0010 | 4109FP | Jerry Thornsberry | [33 empty] | FALSE | FALSE |  |  | 0.18 |  | 1209.05 | 1205.65 |  |  | 1210.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0011 | 4110FP | Paul H. Jones | [33 empty] | FALSE | FALSE |  |  | 0.2 |  | 1209.35 | 1207.35 |  |  | 1211.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0015 | 4113FP | Thos. S. J. & Mary A. K. Williams | [33 empty] | FALSE | FALSE |  |  | 0.26 |  | 1214.95 | 1211.95 |  |  | 1215.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0017 | 4114FP-1 | Swanson & Jean A. Kennedy | [33 empty] | FALSE | FALSE |  |  | 0.28 |  | 1216.65 | 1213.25 |  |  | 1218.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0018 | 4114FP-2 | Swanson & Jean A. Kennedy | [33 empty] | FALSE | FALSE |  |  | 0.3 |  | 1216.8 | 1214.2 |  |  | 1218.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0020 | 4115FP | Hobert Adkins | [33 empty] | FALSE | FALSE |  |  | 0.3 |  | 1218.95 | 1215.65 |  |  | 1219.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0021 | 4117FP | Billie Lee & Carolyn Sue Crigger | [33 empty] | FALSE | FALSE |  |  | 0.28 |  | 1214.8 | 1213.3 |  |  | 1218.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0023 | 4118FP | Marion C. Sweeney | [33 empty] | FALSE | FALSE |  |  | 0.26 |  | 1214.2 | 1211 |  |  | 1214.6 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0028 | 4123FP | Sam | [33 empty] | FALSE | FALSE |  |  | 0.2 |  | 1209.05 | 1207.35 |  |  | 1211.25 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0029 | 4124FP | Mack & Jean Mullins | [33 empty] | FALSE | FALSE |  |  | 0.18 |  | 1208.75 | 1206.75 |  |  | 1210.15 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0031 | 4126FP | George V. III & linda Sue Serra | [33 empty] | FALSE | FALSE |  |  | 0.16 |  | 1207.55 | 1205.65 |  |  | 1208.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0032 | 4127FP | William & Mary Rutter | [33 empty] | FALSE | FALSE |  |  | 0.16 |  | 1206.45 | 1205.25 |  |  | 1208.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0033 | 4128FP | William & Aggnes Rutter | [33 empty] | FALSE | FALSE |  |  | 0.14 |  | 1204.2 | 1203.8 |  |  | 1204.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0034 | 4129FP | Patrick & Diann Bowman | [33 empty] | FALSE | FALSE |  |  | 0.13 |  | 1204.95 | 1202.75 |  |  | 1206.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0039 | 4133FP | Felcia Gail & Kathy Veldin Mullins | [33 empty] | FALSE | FALSE |  |  | 0.14 |  | 1207.65 | 1204.65 |  |  | 1208.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0043 | 4134FP | Larry Dean & Evelyn Herron | [33 empty] | FALSE | FALSE |  |  | 0.37 |  | 1224.35 | 1224.75 |  |  | 1224.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0046 | 4136FP | Johnny & Brenda Baker | [33 empty] | FALSE | FALSE |  |  | 0.38 |  | 1222 | 1218.7 |  |  | 1223.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0049 | 4139FP | Lorene & Mark Burton | [33 empty] | FALSE | FALSE |  |  | 0.43 |  | 1227.8 | 1224 |  |  | 1230 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0050 | 4140FP | Mary M. Asbury | [33 empty] | FALSE | FALSE |  |  | 0.45 |  | 1229.4 | 1225.8 |  |  | 1232.7 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0052 | 4142FP | Stephen D. Burton | [33 empty] | FALSE | FALSE |  |  | 0.47 |  | 1231 | 1228.6 |  |  | 1233.6 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0054 | 4144FP | Lawrence Hicks | [33 empty] | FALSE | FALSE |  |  | 0.5 |  | 1233.6 | 1230.7 |  |  | 1234.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0058 | 4148FP | Dennis Morgan & Ruby K. Mutter | [33 empty] | FALSE | FALSE |  |  | 0.55 |  | 1237.8 | 1234.9 |  |  | 1238.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0059 | 4149FP | Eulip & Norma Jean Rose | [33 empty] | FALSE | FALSE |  |  | 0.56 |  | 1238.1 | 1235.3 |  |  | 1239.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0060 | 4200FP | Vincent W. & Sally Ann Cantrell | [33 empty] | FALSE | FALSE |  |  | 0.56 |  | 1239.46 | 1234.69 |  |  | 1240.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0061 | 4201FP | Wilson H. & Felecia Cantrell | [33 empty] | FALSE | FALSE |  |  | 0.57 |  | 1239.3 | 1236.2 |  |  | 1240.6 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0062 | 4202FP | Wilson H. & Felecia Cantrell | [33 empty] | FALSE | FALSE |  |  | 0.59 |  | 1241.1 | 1237.6 |  |  | 1242.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0063 | 4203FP | Shurla Sweeney | [33 empty] | FALSE | FALSE |  |  | 0.61 |  | 1242.3 | 1239.8 |  |  | 1244.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0064 | 4204FP | Kevin Estep | [33 empty] | FALSE | FALSE |  |  | 0.63 |  | 1244.3 | 1241.7 |  |  | 1246.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0065 | 4205FP | David A. & Lucy Mutter | [33 empty] | FALSE | FALSE |  |  | 0.65 |  | 1246.3 | 1242.3 |  |  | 1248.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0066 | 4206FP | Sarita Carol & Ralph James Stacy | [33 empty] | FALSE | FALSE |  |  | 0.66 |  | 1246.9 | 1243.5 |  |  | 1248.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0068 | 4207FP | Franklin Lee Cook | [33 empty] | FALSE | FALSE |  |  | 0.7 |  | 1249.5 | 1246.1 |  |  | 1251.7 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0069 | 4208FP | Brian Keith Addair | [33 empty] | FALSE | FALSE |  |  | 0.65 |  | 1246 | 1241.2 |  |  | 1248.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0071 | 4209FP | Lacy Troy & Joyce A. Hughes | [33 empty] | FALSE | FALSE |  |  | 0.62 |  | 1242.7 | 1239.6 |  |  | 1245.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0072 | 4210FP | James & Emma Atwell | [33 empty] | FALSE | FALSE |  |  | 0.61 |  | 1243.4 | 1239.7 |  |  | 1244.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0073 | 4211FP | Randy L. & Kathy lynn Baker | [33 empty] | FALSE | FALSE |  |  | 0.6 |  | 1241.7 | 1238.1 |  |  | 1243.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0074 | 4212FP | Lonnie W. Blevins | [33 empty] | FALSE | FALSE |  |  | 0.58 |  | 1240.1 | 1237 |  |  | 1241.7 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0076 | 4213FP | Edna J. & Roscoe C. Jr. Garlin | [33 empty] | FALSE | FALSE |  |  | 0.56 |  | 1236.9 | 1236.4 |  |  | 1239.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0077 | 4214FP | Tommy G. & Frankie Lee Cook | [33 empty] | FALSE | FALSE |  |  | 0.72 |  | 1250.9 | 1248.2 |  |  | 1253.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0080 | 4215FP | James & Bobbie Hughes | [33 empty] | FALSE | FALSE |  |  | 0.83 |  | 1260.2 | 1258.6 |  |  | 1260.9 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0081 | 4216FP | Mary Sue Shelton | [33 empty] | FALSE | FALSE |  |  | 0.86 |  | 1262.4 | 1260 |  |  | 1263 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0087 | 4217FP | Coolridge Fugate | [33 empty] | FALSE | FALSE |  |  | 1.08 |  | 1286.17 | 1279.72 |  |  | 1287.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0088 | 4218FP | James H. Blevins | [33 empty] | FALSE | FALSE |  |  | 1.04 |  | 1278.23 | 1274.82 |  |  | 1279.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0090 | 4219FP | Wendy Nadine Blevins Tolliver | [32 empty] | Wendy called on June 11, 2010 asked where her application stands and if she has one turned in at all. | FALSE | FALSE |  |  | 1.02 |  | 1275.82 | 1272.62 |  |  | 1276.45 | 1977 | [11 empty] | NGVD | McDowell County | LS0090 | 3049675570 | 2767019709 | 2767019710 |  | Home | Cell | Husban Cell |  | 0 | Wendy Tollizer 913 Raysal Hollow Rd. Raysal 24879-8013
FALSE | McDowell County | Phase III | LS0092 | 4220FP | North American Timber Corp. | [33 empty] | FALSE | FALSE |  |  | 0.98 |  | 1271.88 | 1267.92 |  |  | 1274.45 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0093 | 4221FP | Robert | [33 empty] | FALSE | FALSE |  |  | 0.97 |  | 1271.33 | 1266.72 |  |  | 1273.2 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0097 | 4222FP | Rosa B. Dawson | [33 empty] | FALSE | FALSE |  |  | 0.83 |  | 1260.68 | 1258.13 |  |  | 1261.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0098 | 4223FP | Harry | [33 empty] | FALSE | FALSE |  |  | 0.82 |  | 1260.17 | 1256.93 |  |  | 1260.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0103 | 4225FP | Clifford Lee & Linda Gail Kendrick | [33 empty] | FALSE | FALSE |  |  | 1.09 |  | 1287.64 | 1283.52 |  |  | 1288.05 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0104 | 4226FP | Randall & Jackie Hamilton | [33 empty] | FALSE | FALSE |  |  | 1.14 |  | 1287.6 | 1284.4 |  |  | 1289.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0105 | 4227FP | Robert & Marie Brownfield | [33 empty] | FALSE | FALSE |  |  | 1.16 |  | 1289.8 | 1284.3 |  |  | 1291.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0108 | 4228FP | Marie Robinson | [33 empty] | FALSE | FALSE |  |  | 1.3 |  | 1301.4 | 1298.9 |  |  | 1306.5 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0110 | [35 empty] | FALSE | FALSE |  |  | 1.32 |  | 1301.4 | 1299.7 |  |  | 1308.3 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0116 | 4231FP | Don L. Christian | [33 empty] | FALSE | FALSE |  |  | 1.52 |  | 1321.2 | 1316.8 |  |  | 1325.4 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0117 | 4231FP | Don L. Christian | [33 empty] | FALSE | FALSE |  |  | 1.54 |  | 1322.4 | 1318.1 |  |  | 1325.8 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0120 | 4232FP | Pocahontas Minning Co. | [33 empty] | FALSE | FALSE |  |  | 1.65 |  | 1333.37 | 1327.57 |  |  | 1333.75 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0121 | 4233FP | Lonnie & Ruby Mullins | [33 empty] | FALSE | FALSE |  |  | 1.67 |  | 1334.8 | 1331.11 |  |  | 1334.95 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0122 | 4233FP | Lonnie & Ruby Mullins | [33 empty] | FALSE | FALSE |  |  | 1.69 |  | 1335.5 | 1331.91 |  |  | 1337.85 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0124 | 4234FP-1 | Pocahontas Minning Co. | [33 empty] | FALSE | FALSE |  |  | 1.72 |  | 1338.91 | 1335.38 |  |  | 1339.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0126 | 4234FP-2 | Pocahontas Minning Co. | [33 empty] | FALSE | FALSE |  |  | 1.74 |  | 1340 | 1336.04 |  |  | 1340.55 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase III | LS0127 | 4234FP-3 | Pocahontas Minning Co. | [33 empty] | FALSE | FALSE |  |  | 1.75 |  | 1341.08 | 1337.94 |  |  | 1341.35 | 1977 | [11 empty] | NGVD
FALSE | McDowell County | Phase II | MC0156 | 2514 | Iaeger City Hall | [33 empty] | FALSE | FALSE |  |  | 3.98 |  | 1056.2 | 1052.2 |  |  | 1063.75 | 100 year | [11 empty] | NGVD