## Outreach
Community | County | Status | Priority | Date Email Sent | Response | Date Response Received | Received Response From | July 2023 Status (WVSOS/WVU) | 9/8/2023 Update by WVU
Danville | Boone | WVGISTC Has Updates | High | 2023-02-14 | No response. | 2023-04-09 | Michael Mayhorn | Submitted BAS to Census on behalf of all 4 Muni. Mikayla Twarog @ Census is reviewing and working on submission (4/4) | Submissions made by Community to Census. See Census BAS Response Status Viewer. Verify files in January 2024 when new BAS 2023 files released. | https://mtgis-portal.geo.census.gov/arcgis/apps/webappviewer/index.html?id=9b225912e96b4e3c816e4fe413e95d49&extent=-9419145.5839%2C4452684.9055%2C-8391831.9238%2C4904580.6167%2C102100
Madison | [8 empty] | Submitted by community to BAS.
Sylvester | [8 empty] | Submitted by community to BAS.
Whitesville | [8 empty] | Submitted by community to BAS. | RECOMMENDATIONS
Huntington | Cabell/Wayne |  |  | 2023-02-14 | They are working on submission; Probably by May 31st | 2023-02-15 | Brad Nunley and Matt Strogen | Check in with Brad early May. | Telephone call with Brad Nunley (304-696-5540 Ext 2104), GIS Analyst. Brad regarded 1871 first boundary; 30 or 40 adjustments with boundaries compared to Census. Former boundaries submitted on hand-drawn maps. Many boundary corrections do not involve residents. Most issues south of I-64. 1985 Annexation related to Mr. Steven Spagna needs to be addressed. Recommendation is to focus on boundary corrections and 1985 annex. | (1) Finish cleaning up (e.g., whole parcels versus bisect parcels) and finalizing the correct city boundary for Huntington; then email to us. You stated most of boundary issues are south of I-64. (2) Email annexation orders and survey plats for 1985 Spagna/2016 school annexations. (3) Other boundary changes can be classified as boundary corrections of improved mapping accuracy and thus don’t require documentation.
Charleston | Kanawha |  |  | 2023-02-14 | Charleston and South Charlestion will submit changes to 2024 BAS | 2023-02-15 | Dan Vriendt | None needed. | Call with Dan Vriendt and John Butterworth from the Charleston Planning Office. The city of Charleston is hiring a company to perform a survey on the city border to provide a new legal description for the BAS submission. In coordination with South Charleston about shared boundary.
South Charleston
Barrackville | Marion |  |  | 2023-02-14 | During meeting with WVGISTC regarding precinct changes, said their local boundaries are probably correct. Not sure about getting supporting documentation from communities. WVGISTC will do BAS submission for communities with minimal change. The submissions will not have documentation so we will see if the changes are accepted by Census. | 2023-04-23 | Mike Kraley | Mike said he has spoken with WVGIS & Kurt and has everything in order. | Telephone conversation and email with Mike Kraley, GIS/Floodplain Coordinator for Marion County. He is to verify with Tim Newlon (retired) the authoritative status and history of incorporated places file received from county clerk's office in 2022. Mike also to check if county has annexation orders. Also left message with Tom Antulov, County Clerk Chief Deputy about incorporated place boundaries. Once incorporated places boundary file is verified, set up a conference call with BAS contacts of corporations. Local source data may be erroneosly adjusted to parcel boundaries. | Is area of cemetery and parcels along Chesapeake Rd. (near confluence of Buffalo Creek and Finches Run) part of Barrackville Corporation?
Fairmont | [8 empty] | Review Fairmont City shapefile from 2021. | Northern annexation missing and other annexations may not be mapped correctly according to local data sources. Fairmont sent new file for review. Planning Director engaged.
Fairview | [9 empty] | Western Annexation of Fairview school. Remaining border correction to USGS topo map.
Farmington | [9 empty] | Use Census boundary line (Red dash-dot boundary line) and not local data source
Grant Town | [9 empty] | Northeast Shoestring Annexation along Chinks Run Road and Arnett Run. Border correction to USGS topo map boundary on western border.
Mannington | [9 empty] | Southeast Annexations along Husky Hwy (Rt. 250) and Blackshere Rd. Boundary corrections to USGS topo map.
Monongah | [8 empty] | Annexation on Census but not local data source. Call with Tom Antulov 9/12. | For municipal boundary, use existing Census boundary (red dash-dot line) and not local county data source.
Pleasant Valley | [9 empty] | Northern and eastern boundaries do not match Census boundary. Shared boundary with Fairmont including Morris Park.
Rivesville | [9 empty] | Use Census boundary which is close to USGS topo map
White Hall | [9 empty] | Census boundary file does not match municipal boundary from local data source. Southern annexations missing or incomplete.
Worthington | [9 empty] | SE Annexation of Worthington for South Worthington. Border corrections to USGS topo map.
Iaeger | McDowell |  |  | 2023-02-14 | Forwarded to Matt (Trueline) and Dwight Gillipsie | 2023-02-16 | Jennifer Wimmer |  | Jennifer Wimmer (304.436.8549) provided three annexation orders/legal descriptions for Iaeger. Missing a CAD or digital map file for 2011 eastern annex of 59.98 acres for Iaeger provided by Matt Fullen of True Line. Email sent about missing map file. Submitted to WGISTC for processing.
Welch | McDowell |  |  |  | "We have an engineering company (True Line) working to get this matter resolved. I have copied the engineer in this email." | 2023-02-28 | Jennifer Wimmer | Asked if they are planning on doing a BAS submission. WVGISTC waiting for response. | Submitted to BAS 2023
Belmont | Pleasants |  |  | 2023-02-14 | Scheduled call for 2-17-23 to discuss redoing BAS Submission. They would like WVGISTC to do BAS submissions. We are waiting on documentation. | 2023-02-16 | Robin Wright | WVGISTC waiting for documentation, will proceed with BAS submissions once documents are received. | Use Census? Consult with Johnna.
St. Marys | [8 empty] | Use Census? Consult with Johnna.
Bancroft | Putnam |  |  | 2023-02-14 | Attempted submission before and was not accepted by Census due to lack of documentation. | 2023-02-16 | Bobby Stover | WVGISTC will schedule call with Bobby. | Okay. Use Census.
Buffalo | [8 empty] | Submitted to WVGISTC for processing
Eleanor | [8 empty] | Submitted to WVGISTC for processing
Hurricane | [8 empty] | Submitted to WVGISTC for processing
Nitro | [8 empty] | Submitted to WVGISTC for processing. Add split community to status map.
Poca | [8 empty] | Submitted to WVGISTC for processing
Davis | Tucker |  |  | 2023-02-14 | Andrew sent documentation; WVGISTC did BAS submissions for Davis, Thomas, Hambleton, and Hendricks. Andrew said Parsons needs more research and the boundary needs updated. | 2023-02-14 | Andrew Meador | Census and Parsons Have Communicated re: BAS Boundaries Info | Submitted to BAS 2023
Hambleton | [8 empty] | Submitted to BAS 2023
Hendricks | [8 empty] | Submitted to BAS 2023
Parsons | [8 empty] | Not submitted. Emailed Andrew Meadows about Parsons certification letter after due diligence did not locate any supporting documentation. Follow call with Andrew provided strategy framework for moving forward. Note that 1985 flood destroy many legal records.
Thomas
North Hills | Wood |  |  | 2023-02-14 | No response. | 2023-03-30 | County Clerk Joe Gonzales | Assessors Mapper said he submitted everything for county but not corporations. | Call with Paul Dawkins, county assessor mapper. He emailed to WVU an incorporated boundaries file for verification. Johnna verified as same file on WV BAS Viewer and email sent to Paul to identify missing annexations and spatially inaccurate boundaries.
Parkersburg
Vienna
Williamstown
Keyser | Mineral |  |  | 2022-02-22 | Keyser submitted changes March 2022. Changed status to "Updated with Census 2022 data". | 2023-02-23 | Janette Basile | None needed. | None Needed.
Ohio County (Dave Weaver) communities should be added for 2024 BAS.
Email sent 9/12/2023
Community-level BAS submission by Dave Weaver

## County Clerks
County | Clerk | Address | Phone | Fax | Email
Barbour | Laurie "Marsh" Austin | 26 N. Main | (304) 457-2232 | (304) 457-5983 | barbourcounty@wvsos.com
Philippi, WV 26416
Berkeley | Anthony J. "Tony" Petrucci | 400 W. Stephen St. | (304) 264-1989 | (304) 260-4882 | berkeleycounty@wvsos.com
Suite 106
Martinsburg, WV 25401
Boone | Roger Toney | 200 State Street | (304) 369-7330 | (304) 369-7329 | boonecounty@wvsos.com
Suite 104
Madison, WV 25130
Braxton | Sue (Singleton) Rutherford | 300 Main Street | (304) 765-2833 | (304) 765-2093 | braxtoncounty@wvsos.com
P.O. Box 486
Sutton, WV 26601
Brooke | Kimberly "Kimmy" Barbetta | 632 Main Street | (304) 737-3661 | (304) 737-4023 | barbetta@mail.wvnet.edu
Wellsburg, WV 26070
Cabell | Scott Caserta | 750 5th Avenue | (304) 526-8633 | (304) 526-8632 | cabellcounty@wvsos.com
Suite 108
Huntington, WV 25701
Calhoun | Jean Simers | 363 Main Street, Suite 201 | (304) 354-6725 | (304) 354-6447 | calhouncounty@wvsos.com
P.O. Box 230
Grantsville, WV 26147
Clay | Connie Workman | 246 Main Street | (304) 587-4259 | (304) 587-4202 | claycounty@wvsos.com
P.O. Box 190
Clay, WV 25043
Doddridge | Lorena "Catee" Slater | 108 Court Street | (304) 873-2631 | (304) 873-1840 | doddridgecounty@wvsos.com
Suite 1
West Union, WV 26456
Fayette | Michelle L. Holly | ATTN: Elections | (304) 574-4225 | (304) 574-4335 | fayettecounty@wvsos.com
100 Court Street Ste. 1
P.O. Box 569
Fayetteville, WV 25840
Gilmer | Jean Butcher | 10 Howard Street | (304) 462-7641 | (304) 462-8855 | gilmercounty@wvsos.com
Glenville, WV 26351
Grant | Lora Bennett | 5 Highland Avenue | (304) 257-4550 | (304) 257-4207 | grantcounty@wvsos.com
Petersburg, WV 26847
Greenbrier | Robin Yates Loudermilk | 912 Court Street N | (304) 647-6602 | (304) 647-6694 | greenbriercounty@wvsos.com
P.O. Box 506
Lewisburg, WV 24901
Hampshire | Eric W. Strite | 19 East Main Street | (304) 822-5112 | (304) 822-4039 | hampshirecounty@wvsos.com
P.O. Box 806
Romney, WV 26757
Hancock | Karan (Baier) Valenti | 102 North Court Street | (304) 564-3311 | (304) 564-5941 | hancockcounty@wvsos.com
|  | P.O. Box 367 | Ext. 266
New Cumberland, WV 26047
Hardy | Gregory L. Ely | 204 Washington Street | (304) 530-0250 | (304) 530-0251 | hardycounty@wvsos.com
Room 111
Moorefield, WV 26836
Harrison | John R. Spires | 306B Washington Avenue | (304) 624-8613 | (304) 626-1090 | harrisoncounty@wvsos.com
Clarksburg, WV 26301
Jackson | Christina Gossett | 100 Court Street North | (304) 373-2250 | (304) 372-1107 | christina.gossett@jacksoncountywv.com
P.O. Box 800
Ripley, WV 25271
Jefferson | Jacki Shadle | 100 East Washington Street | (304) 728-3246 | (304) 728-1957 | jeffersoncounty@wvsos.com
P.O. Box 208
Charles Town, WV 25414
Kanawha | Vera McCormick | 415 Quarrier Street | (304) 357-0130 | (304) 357-0585 | veramccormick@kanawha.us
Charleston, WV 25301
Lewis | Cindy Stout Rowan | 110 Center Avenue | (304) 269-8215 | (304) 269-8202 | lewiscounty@wvsos.com
Weston, WV 26452
Lincoln | Kristy Scraggs | 8000 Court Avenue | (304) 824-3336 | (304) 824-2444 | lincolncounty@wvsos.com
P.O. Box 497
Hamlin, WV 25523
Logan | John A. Turner | 300 Stratton Street | (304) 792-8600 | (304) 792-8246 | logancounty@wvsos.com
Room 102
Logan, WV 25601
Marion | Julie Kincaid | 219 Adams Street | (304) 367-5445 | (304) 367-5448 | marioncounty@wvsos.com
P.O. Box 1267
Fairmont, WV 26555
Marshall | Connie Howard | 600 7th Street | (304) 845-1220 | (304) 845-5891 | marshallcounty@wvsos.com
P.O. Box 459
Moundsville, WV 26041
Mason | Diana Cromley | 200 Sixth Street | (304) 675-1997 | (304) 675-2521 | masoncounty@wvsos.com
Point Pleasant, WV 25550
McDowell | Donald L. Hicks | 90 Wyoming Street | (304) 436-8544 | (304) 436-8576 | mcdowellcounty@wvsos.com
Suite 109
Welch, WV 24801
Mercer | Verlin T. Moye | 1501 West Main Street | (304) 487-8338/8339 | (304) 425-4851 | mercercounty@wvsos.com
Suite 121
Princeton, WV 24740
Mineral | Lauren Ellifritz | 150 Armstrong Street | (304) 788-3924 | (304) 788-4109 | mineralcounty@wvsos.com
Keyser, WV 26726
Mingo | Larry ‘Yogi’ Croaff | 78 East Second Avenue | (304) 235-0330 | (304) 235-0565 | mingocounty@wvsos.com
Room 125
Williamson, WV 25661
Monongalia | Carye L. Blaney | 243 High Street | (304) 291-7230 | (304) 291-7233 | monongaliacounty@wvsos.com
Room 123
Morgantown, WV 26505
Monroe | Jeremy Meadows | 350 Main Street | (304) 772-3096 | (304) 772-4191 | jmeadows@monroecountywv.net
P.O. Box 350
Union, WV 24983
Morgan | Kimberly Johnson-Nickles | 77 Fairfax Street | (304) 258-8547 | (304) 258-8545 | knickles@morgancountywv.gov
Room 102
Berkeley Springs, WV 25411
Nicholas | Robert Painter II | 700 Main Street | (304) 872-7820 | (304) 872-9600 | nicholascounty@wvsos.com
Suite 2
Summersville, WV 26651
Ohio | Michael E. Kelly | 1500 Chapline Street | (304) 234–3656 | (304) 234-3829 | mkelly2@clerk.state.wv.us
Room 205
Wheeling, WV 26003
Ohio | Vacant | 1500 Chapline Street | (304) 234-3750 | (304) 234-3827
| Elections Clerk | Room 215
Wheeling, WV 26003
Pendleton | Elise Miller White | 100 South Main Street | (304) 358-2505 | (304) 358-2473 | pendletoncounty@wvsos.com
P.O. Box 1167
Franklin, WV 26807
Pleasants | Jody Lynn Davis | 301 Court Lane | (304) 684-3542 | (304) 684-7569 | pleasantscounty@wvsos.com
St. Marys, WV 26170
Pocahontas | Melissa "Missy" Bennett | 900 C 10th Avenue | (304) 799-4549 | (304) 799-6947 | pocahontascounty@wvsos.com
Marlinton, WV 24954
Preston | Linda Huggins | 106 West Main Street | (304) 329-0070 | (304) 329-0198 | lhuggins@prestoncountywv.gov
Suite 103
Kingwood, WV 26537
Putnam | Brian Wood | 12093 Winfield Rd. | (304) 586-0202 | (304) 204-1408 | bwood@putnamwv.org
Suite 3
Winfield, WV 25213
Raleigh | Scott Van Meter | 215 Main Street | (304) 252-8681 | (304) 252-8698 | raleighcounty@wvsos.com
Beckley, WV 25802
Randolph | Brenda Wiseman | 2 Randolph Avenue | (304) 636-0543 | (304) 636-0544 | randolphcounty@wvsos.com
Elkins, WV 26241
Ritchie | Tracie D. McDonald | 115 East Main Street | (304) 643-2164 | (304) 643-2906 | tdmcdona@clerk.state.wv.us
Room 201
Harrisville, WV 26362
Roane | Sena McDonald | 200 Main Street | (304) 927-2860 | (304) 927-2489 | roanecounty@wvsos.com
Spencer, WV 25276
Summers | Lynn Reed | 120 Ballengee Street | (304) 466-7104 | (304) 466-7146 | summerscounty@wvsos.com
Suite 106
P.O. Box 97
Hinton, WV 25951
Taylor | Jaron Freeman | 128 W. Main St., Annex 2 | (304) 265-1401 | (304) 265-2889 | taylorcounty@wvsos.com
Grafton, WV 26354
Tucker | Sherry Simmons | 211 First Street | (304) 478-2414 | (304) 478-2217 | tuckercounty@wvsos.com
|  | Suite 204 | Ext. 201
Parsons, WV 26287
Tyler | Neil Archer II | 121 Main Street | (304) 758-2102 | (304) 758-2126 | tylercounty@wvsos.com
P.O. Box 66
Middlebourne, WV 26149
Upshur | Carol J. Smith | 40 West Main Street | (304) 472-1068 | (304) 472-1029 | upshurcounty@wvsos.com
Room 101
Buckhannon, WV 26201
Wayne | Craig Evans | 700 Hendricks Street | (304) 272-6362 | (304) 272-5318 | waynecounty@wvsos.com
P.O. Box 248
Wayne, WV 25570
Webster | Eva R. Green | 2 Court Square | (304) 847-2508 | (304) 847-7755 | webstercounty@wvsos.com
Room G1
Webster Springs, WV 26288
Wetzel | Jessica Davis | 200 Main Street | (304) 455-8224 | (304) 455-5256 | wetzelcounty@wvsos.com
P.O. Box 156
New Martinsville, WV 26155
Wirt | Marolyn Baldrige | 19 Washington St Room 102 | (304) 275-4271 | (304) 275-3418 | wirtcounty@wvsos.com
P.O. Box 53
Elizabeth, WV 26143
Wood | Joe Gonzales | 1 Court Square | (304) 424-1850 | (304) 424-1982 | woodcounty@wvsos.com
P.O. Box 1474
Parkersburg, WV 26101
Wyoming | Jewell (Spears) Aguilar | 24 Main Avenue | (304) 732-8000 | (304) 732-9659 | wyomingcounty@wvsos.com
|  | P.O. Box 309 | Ext. 242
Pineville, WV 24874