## Legend
IMPORTANT UPDATES !!
Please provide updates to any milestone dates (prelim, appeals, LFD and effective) ASAP, as required for the monthly Congressional Notification. Updates should be sent to madeline.harrell@mbakerintl.com, jeffrey.r.smith@wsp.com, and mmcgeehin@hwcinc.com.
Archive:
Comments have been split into New and Archived Columns. Comments made in the delivery month will be in the 'New' column; all others will be in the Archived column. For LFD dates that are italicized in bold red font, please see the Comments field for updated notes. Recently FEMA has passed down guidelines pertaining to how MIP cases are named. Going forward, the MIP cases may have Prefixes such as REG, which indicates the project is tracking production of regulatory products and processes, and RMP, which indicates the project is tracking production of Risk MAP products and services. In addition, some of the REG cases needed RMP cases created in conjunction with them. We have added a seperate column to track these case numbers. This allievates duplicate projects appearing in the list. Finally, please take notice of the updated color legend at the bottom of this page.
1) Field Definition
2) Color Coding/Font Definition
1) Field Definition:
FMPU Field | Description | Data Source | Comments
STATE | State | MIP
COMM. | Community: This is typically county or independent city, sometimes it is a combination of a county and independent city included in one study. | MIP
FEMA CASE NUMBER | MIP Case Number | MIP
FIPS CODE | Federal Information Processing Standards Code | MIP
# OF COMM. | Number of communities/ jurisdictions | MIP | Number of communities requiring ordinance updates
PRELIM | Preliminary release date | MIP
Discovery Meeting | Discovery Meeting date | FMPU - MCP Table
Fld Rsk Rvw Mtg | Flood Risk Review Meeting date | FMPU - MCP Table
CCO MEETING | CCO Meeting Date | FMPU - MCP Table | Will pull completed/actual dates from MIP, projected dates may be filled in until they are reported.
Open House Meeting | Open House Meeting Date | FMPU - MCP Table
Resilience Meeting | Resilience Meeting Date
Final Meeting Partner |  | FMPU
FEMA ENG | Risk Analysis Branch Project Officer | MIP
FEMA PLAN | FPM&I Contact | MIP
APPEAL START | Date the appeal period starts (date of 2nd newspaper notice). | FMPU | Will pull completed/actual dates from MIP
END OF APPEAL | Date the appeal period ended (90-days after 2nd newspaper notice). | FMPU | Confirm with mapping partner.
LFD ISSUANCE | Date of Letter of Final Determination | MIP | Projects in scoping with no projected dates will be filled until they are entered in the MIP
EFFECTIVE DATE | Date revised Flood Insurance Study (FIS) and Digital Flood Insurance Rate Map (DFIRM) become effective, 6 months after LFD. | MIP | Projects in scoping with no projected dates will be filled until they are entered in the MIP
CURRENT TASK/ NOTES | Current tasks and notes | FMPU
DATA DEVELOPMENT MAPPING PARTNER | Mapping Partner contracted to complete Data Development | FMPU
ENGINEERING REVIEW MAPPING PARTNER | Mapping Partner contracted to complete Engineering Review. | FMPU
POST PROCESSING MAPPING PARTNER | Mapping Partner contracted to complete Post-Preliminary Processing. | FMPU
INSURANCE INTEREST | Identifies studies where PAL agreements are involved or county is restudied. | FMPU
Study Manager | Email address of primary POC for the subject study | FMPU
2) Color Coding:
Preliminary date due in a prior quarter
Preliminary date due FY23 Q1
Preliminary date due FY23 Q2
Preliminary date due FY23 Q3
Preliminary date due FY23 Q4
Preliminary date due FY24 Q1
Preliminary date due FY24 Q2
**IMPORTANT** Please note that all future dates are subject to change and reflect best projections as of the current month.
Date Coding:
2010-01-28 | Actual prelim/LFD/effective date
2010-01-29 | Projected prelim/LFD/effective date date
2010-01-29 | Non-milestone date
DD/MM/YYYY | MIP does not match FMPU - action required
N/A | Not Applicable (i.e., the meeting or milestone is not applicable for this particular project)
TBD | To Be Determined (i.e., the meeting or milestone is applicable for this particular project but has not yet been scheduled)
PENDING | Appeal period dates that are pending (i.e., the required Federal Register publication is itself pending or recently occurred)
Examples:
2010-01-28 | Preliminary Map issued in the current quarter which is in proper standing in the MIP
2010-01-29 | Preliminary Map projected to be due in a future quarter

## Active
STATE | PROJECT | FIPS | HUC8 | MIP CASE NO | INSURANCE INTEREST | # REV PREL | # ORDINANCE UPDATES | FEMA ENG | FEMA PLAN | STUDY MANAGER | DATA DEVT PART | ENG RVW PART | POST PROCESS PART | DISCOVERY MEETING | FLD RSK RVW MTG | PRELIMINARY | CCO Meeting | REVISED PRELIM | APPEAL PERIOD STARTS | APPEAL PERIOD ENDS | PRE/POST LFD MEETING | LFD ISSUANCE | EFFECTIVE DATES | CURRENT NOTE | ARCHIVED NOTES
DE | Kent County, DE - Dover and South of Dover - PMR | 10001 |  | TBD | TBD |  | TBD | Andrew Jackson | TBD | alexandria.hunt@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
DE | Sussex County, DE - Town of Milton - PMR | 10005 |  | TBD | TBD |  | TBD | Andrew Jackson | TBD | alexandria.hunt@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
MD | Baltimore County, MD - Gunpowder-Patapsco Basin-Wide Study (24 Communities) | 24005 |  | 11-03-2204S | Restudy |  | 1 | Bob Pierson | Bobby Cobelli | dave.guignet@maryland.gov | MDE / Baltimore County | USACE | MDE | 2011-11-16 | 2019-11-22 | 2020-08-12 | 2020-09-23 | 2022-09-19 | 2021-07-08 | 2021-10-08 | TBD | TBD | TBD | Appeal Resolutions in progress (7 of 8 issued, and 1 of 8 pending). 2nd Appeal Period is not warranted. | Open House occured on 5/12/2021. A second one will be scheduled in the future.
MD | Carroll County, MD PMR - Incorporate Frederick Flood Studies | 24013 |  | TBD | TBD |  | TBD | Lee Brancheau | TBD | brandon.cramer@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
MD | Frederick County, MD - Monocacy Basin-Wide Study | 24021 | 02070009 | 14-03-1939S | Restudy | 1 | 13 | Lee Brancheau | Josh Lippert | brett.holthaus@atkinsglobal.com | USACE / STARR II | TBD | STARR II/ Compass | 2014-06-04 | 2018-01-30 | 2018-09-28 | 2018-11-27 | 2022-05-13 | 2021-06-01 | 2021-09-01 | 2022-07-05 | TBD | 2023-05-09 | First LFD 11/9/2022, will need another appeal period | Original appeal start date is 4/29/2021. 2nd revised prelim issued 8/19/2020. Revised prelim #1 6/19/2020; CCO #2 will be on 3/28/19. Third revised preliminary issued on 12/2/2020.
MD | Garrett County, MD - Kitzmiller and Blaine Levee PMR | 24023 |  | 21-03-0011S | Levee |  | TBD | Hani Rimawi | Bobby Cobelli | craig.m.thomas@usace.army.mil | TBD | TBD | TBD | N/A | TBD | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
MD | Howard County, MD - Countywide | 25027 |  | 19-03-0041S | Restudy |  | 1 | Hani Rimawi | Bobby Cobelli | jonathan.langley@wsp.com | Wood | USACE | MDE / ARC | N/A | 2023-05-03 | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
MD | Montgomery County, MD - Middle Potomac-Catoctin Basin-Wide Study | 24031 | 02070008 | 12-03-0415S | Restudy |  | 1 | Hani Rimawi | Bobby Cobelli | tyler.bruce@wsp.com | MDE | USACE | MDE / ARC | 2014-09-29 | 2021-04-27 | 2023-01-31 | TBD |  | TBD | TBD | TBD | TBD | TBD | First preliminary 11/30/2022 | Only funded through workmap for LAMP study
MD | St. Mary's County, MD - Riverine Update | 24037 | 02060006; 02070011 | 19-03-0027S | Restudy |  | 2 | Hani Rimawi | Bobby Cobelli | brandon.cramer@wsp.com | MDE | USACE | ARC | N/A | 2021-11-22 | 2022-11-29 | 2023-01-15 |  | TBD | TBD | TBD | TBD | TBD | First preliminary date 10/28/2022
NY, PA, OH, WV | Ohio River - Technical Data and Hydrology Investigation |  |  | 19-03-0042S | PENDING |  | N/A | Andrew Jackson | N/A | TBD | TBD | TBD | TBD | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
PA | Adams County, PA - 2D Pilot PMR | 42001 |  | TBD | TBD |  | TBD | Amanuel Ghebreegziabher | TBD | swetha.konduru@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Bedford County, PA (LAMP Everett Levee) | 42009 |  | 14-03-2043S | Levee |  | 1 | Bob Pierson | Bobby Cobelli | james.barbis@woodplc.com | RAMPP / Compass / ARC | TBD | TBD | N/A | N/A | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Funded for continued LSIP monitoring
PA | Bradford County, PA - Upper Susquehanna River PMR - Bradford and Wyoming Counties | 42015 |  | 16-03-0615S | Restudy | 1 | 19 | Nikki Roberts | Bobby Cobelli | matthew.mcglone@mbakerintl.com | STARR II | N/A | STARR II/ Compass / ARC | N/A | 2017-09-06 | 2018-08-30 | 2018-12-12 | 2022-06-17 | 2021-04-01 | 2021-07-01 | TBD | TBD | TBD | First revised preliminary issued 7/1/2020 | 6/13/2019 - 9/11/2019 dates of original appeals period
PA | Bradford County, PA (LAMP Sayre PMR) | 42015 |  | 16-03-0615S | Levee |  | 4 | Nikki Roberts | Bobby Cobelli | justin.king@stantec.com | STARR II | TBD | TBD | N/A | 2019-06-25 | N/A | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Project mapping will be handled in revised prelims for the Bradford County project.
PA | Carbon County, PA - Countywide (Lehigh) ¦ Weissport Pre-LAMP | 42025 | 02040106 | 16-03-2422S | Restudy |  | 23 | Hani Rimawi | Bobby Cobelli | tyler.bruce@wsp.com | STARR II | TBD | STARR II / ARC | 2016-09-27 | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD |  | Resiliency Meeting was on 2/1/2018
PA | Columbia County, PA - Upper Susquehanna-Lackawanna Basin-wide | 42037 | 02050107 | 15-03-0227S | Restudy |  | 34 | Hani Rimawi | Bobby Cobelli | matthew.mcglone@mbakerintl.com | USACE / STARR II | N/A | STARR II/ Compass / ARC | 2015-04-01 | 2017-08-17 | 2019-05-31 | 2019-07-10 | 2022-06-17 | 4/29/2021 & 5/19/2021 | 7/28/2021 & 8/17/2021 | TBD | TBD | TBD | First revised prelim issued 8/28/2020 | Original appeal start date was 4/29/2021. 5/19/2021 start date for Conygham Twp only
PA | Cumberland County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 42041 | 02050305 | 15-03-0142S | Restudy, Zone A |  | 33 | Lee Brancheau | Bobby Cobelli | brett.holthaus@atkinsglobal.com | RAMPP / STARR II | TBD | STARR II | 2015-04-07 | 2016-12-05 | 2019-05-14 | 2019-06-26 | 2022-06-30 | 7/8/2021 & 8/5/2021 | 10/8/2021 & 11/3/2021 | 2019-11-06 | 2022-12-21 | 2023-06-21 | First revised prelim issued on 12/28/2020 | Due to a newspaper publication failure, a second appeals period is scheduled to start on 8/5. Original appeals period ran from 2/6/2020 to 5/8/2020. Open House scheduled for 11/6/19. Only funded through workmap for Zone A studies
PA | Dauphin County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 42043 | 02050305 | 15-03-0142S | Restudy, Zone A |  | 40 | Amanuel Ghebreegziabher | Bobby Cobelli | emily.seeton@mbakerintl.com | RAMPP / STARR II / ARC | TBD | STARR II / ARC | 2015-04-07 | 2018-06-04 | 2023-12-29 | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Eastwick - Darby Creek & Cobbs Creek Detailed Study | 42101 |  | TBD | Restudy |  | 0 | Hani Rimawi | Bobby Cobelli | TBD | USACE-Philadelphia | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Franklin County, PA PMR - Incorporate Cumberland Flood Studies | 42055 |  | TBD | TBD |  | TBD | Lee Brancheau | TBD | heather.rogers@freese.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Indiana County, PA (LAMP Cherry Tree Levees) | 42063 |  | 14-03-2057S | Levee |  | 1 | Bob Pierson | Bobby Cobelli | mike.seering@aecom.com | RAMPP / STARR II | TBD | TBD | N/A | TBD | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Funded for continued LSIP monitoring
PA | Juniata HUC 6 – Data Development Phase – Survey, Hydrology |  |  | 20-03-0001S | Zone A, Restudy |  | TBD | Andrew Jackson | Bobby Cobelli | craig.m.thomas@usace.army.mil | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Lackawanna County - LAMP for Seclusion Areas for Scranton/Olyphant PMR | 42069 |  | 17-03-0973S | Levee |  | 0 | Nikki Roberts | Bobby Cobelli | brian.lee@stantec.com | STARR II | TBD | STARR II | N/A | 2017-09-27 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Submitted with LOMR Team 3/15/2020
PA | Lackawanna County - LAMP for Seclusion Areas Spring Brook/Moosic | 42069 |  | 17-03-0973S | Levee |  | 0 | Lee Brancheau | Bobby Cobelli | kevin.donnelly@stantec.com | STARR II | TBD | STARR II | N/A | 2019-02-26 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Submitted with LOMR Team 3/15/2020
PA | Lackawaxen Basin-Wide: Pike County | 42103 | 02040103 | 16-03-2420S | Restudy, Zone A |  | 13 | Amanuel Ghebreegziabher | Bobby Cobelli | brian.edmondson@freese.com | STARR II / ARC | TBD | STARR II / ARC | 2016-09-13 | 2018-11-19 | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Lackawaxen Basin-Wide: Wayne County | 42127 | 02040103 | 16-03-2420S | Restudy, Zone A |  | 27 | Amanuel Ghebreegziabher | Bobby Cobelli | clayton.ballerine@mbakerintl.com | STARR II / ARC | TBD | STARR II / ARC | 2016-09-13 | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Lehigh County, PA - Countywide (Lehigh) | 42077 | 02040106 | 16-03-2422S | Restudy |  | 25 | Hani Rimawi | Bobby Cobelli | tyler.bruce@wsp.com | STARR II | TBD | STARR II/ Compass / ARC | 2016-09-27 | TBD | 2020-07-18 | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | Resiliency Meeting was on 2/1/2018
PA | Lehigh River - Updated Detailed Study |  |  | TBD | Restudy |  | TBD | Hani Rimawi | Bobby Cobelli | jason.f.miller@usace.army.mil | USACE | TBD | TBD | N/A | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Lower Juniata HUC8 - Discovery (Juniata River Basin) |  | 02050304 | 20-03-0001S | Discovery |  | N/A | Amanuel Ghebreegziabher | Bobby Cobelli | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Luzerne County, PA - Upper Susquehanna-Lackawanna basin-wide | 42079 | 02050107 | 15-03-0227S | Restudy |  | 42 | Bob Pierson | Bobby Cobelli | heather.rogers@freese.com | USACE / STARR II | N/A | STARR II/ Compass / ARC | 2015-04-01 | 2017-08-17 | 2020-09-15 | 2020-11-05 | 2022-08-31 | 2021-07-02 | 2021-09-30 | TBD | TBD | TBD
PA | Luzerne County, PA (LAMP Duryea PMR) | 42079 |  | 15-03-0227S | Levee |  | 7 | Bob Pierson | Bobby Cobelli | kevin.donnelly@stantec.com | STARR II | TBD | TBD | N/A | 2020-07-07 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Luzerne County, PA (LAMP Plymouth PMR) | 42079 |  | 15-03-0227S | Levee |  | 4 | Bob Pierson | Bobby Cobelli | John.Shirley@stantec.com | STARR II | TBD | TBD | N/A | 2020-01-24 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Luzerne County, PA (LAMP Wilkes Barre Mill Creek PMR) | 42079 |  | 15-03-0227S | Levee |  | 5 | Bob Pierson | Bobby Cobelli | kevin.donnelly@stantec.com | STARR II | TBD | TBD | N/A | 2019-08-29 | N/A | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Luzerne County, PA (LAMP Wilkes Barre, Hanover Twp. PMR) | 42079 |  | 15-03-0227S | Levee |  | 19 | Bob Pierson | Bobby Cobelli | John.Shirley@stantec.com | STARR II | TBD | TBD | N/A | 2020-01-24 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Monroe County, PA - Countywide (Lehigh) ¦ Stroudsburg Pre-LAMP | 42089 | 02040106 | 16-03-2422S | Restudy |  | 20 | Hani Rimawi | Bobby Cobelli | brandon.cramer@wsp.com | STARR II | TBD | STARR II / ARC | 2016-09-27 | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD |  | Resiliency Meeting was on 2/1/2018
PA | Montour County , PA (LAMP Danville - Mahoning Creek PMR) | 42093 |  | 15-03-0227S | Levee |  | 6 | Hani Rimawi | Bobby Cobelli | kevin.donnelly@stantec.com | STARR II | TBD | TBD | N/A | 2020-10-28 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Montour County , PA (LAMP Danville - State Hospital PMR) | 42093 |  | 15-03-0227S | Levee |  | 6 | Hani Rimawi | Bobby Cobelli | kevin.donnelly@stantec.com | STARR II | TBD | TBD | N/A | 2020-10-28 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Montour County , PA (LAMP Danville - Susq. River PMR) | 42093 |  | 15-03-0227S | Levee |  | 6 | Hani Rimawi | Bobby Cobelli | kevin.donnelly@stantec.com | STARR II | TBD | TBD | N/A | 2020-10-28 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Northampton County, PA | 42095 | 02040106 | 21-03-0001S | Restudy |  | TBD | Hani Rimawi | Bobby Cobelli | david.r.cooper@wsp.com | Compass | TBD | ARC | N/A | N/A | N/A | TBD |  | TBD | TBD | TBD | TBD | TBD |  | Scoped for data dev only
PA | Northumberland County, PA - Lower Susquehanna-Penns Basin-Wide Study | 42097 | 02050107 | 15-03-0140S | Restudy |  | 36 | Nikki Roberts | Bobby Cobelli | matthew.mcglone@mbakerintl.com | USACE / STARR II | N/A | STARR II/ Compass / ARC | 2015-04-01 | 2017-08-17 | 2019-04-09 | 2019-07-09 | 2022-06-30 | 2020-02-28 | 2020-05-28 | TBD | TBD | TBD | First revised prelim issued on 9/30/2021
PA | Raystown HUC8 - Discovery (Juniata River Basin) |  | 02050304 | 20-03-0001S | Discovery |  | N/A | Bob Pierson | Bobby Cobelli | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
PA | Tioga County, PA (LAMP Tioga River Levee) | 42117 |  | 15-03-0310S | Levee |  | 2 | Hani Rimawi | Bobby Cobelli | james.barbis@woodplc.com | USACE / Compass / ARC | TBD | TBD | N/A | 2018-02-12 | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD |  | Funded for LAMP Plan
PA | Upper Juniata HUC8 - Discovery (Juniata River Basin) |  | 02050302 | 20-03-0001S | Discovery |  | N/A | Andrew Jackson | Bobby Cobelli | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Albemarle County and Charlottesville Ind City, VA - FIRM Update ¦ Scottsville Pre-LAMP | 51003, 51540 |  | 20-03-0030S | Restudy |  | 3 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-26 | 2022-05-13 | 2023-06-01 | 2023-07-15 |  | TBD | TBD | TBD | TBD | TBD | First prelim date 1/30/2023
VA | Alexandria City, VA - Middle Potomac Anacostia Basin-Wide Study (Community Based) | 51510 | 02070010 | 14-03-3327S | Restudy |  | 1 | Lee Brancheau | Kristen Jones | matthew.mcglone@mbakerintl.com | STARR II | TBD | STARR II/ Compass / ARC | 2014-09-29 | 2020-04-06 | 2020-09-30 | 2020-10-29 | 2022-05-31 | 2022-12-12 | 2023-03-12 | TBD | TBD | TBD | First appeal period 7/22/2021-10/20/2021 | Original FRR on 2/23/2018
VA | Amherst County, VA - FIRM Update | 51009 |  | 20-03-0032S | Restudy |  | 2 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-27 | 2022-09-15 | 2023-02-28 | 2023-04-14 |  | TBD | TBD | TBD | TBD | TBD
VA | Appomattox County, VA - FIRM Update | 51011 |  | 20-03-0035S | Restudy |  | 3 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-27 | TBD | 2023-06-01 | 2023-07-16 |  | TBD | TBD | TBD | TBD | TBD
VA | Arlington County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 51013 | 02070010 | 14-03-3327S | Restudy |  | 1 | Lee Brancheau | Kristen Jones | matthew.mcglone@mbakerintl.com | STARR II | TBD | STARR II/ Compass / ARC | 2014-09-29 | 2020-04-06 | 2020-09-18 | 2020-11-09 | 2022-04-29 | 2022-10-06 | 2023-01-04 | TBD | TBD | TBD | First appeal period 7/22/21-10/20/21 | Original FRR on 2/23/2018
VA | Banister HUC8 |  | 03010105 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | kdunn@tandmassociates.com | Compass | TBD | TBD | 2019-08-13 | TBD | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Bland, VA Flood Studies and Prelim | 51021 |  | TBD | TBD |  | TBD | John Luff | TBD | alexandria.hunt@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Brunswick County, VA - FIRM Update | 51025 |  | 20-03-0040S | Restudy |  | 4 | John Luff | Kristen Jones | lshepherd@moffattnichol.com | Compass | Compass | ARC | 2019-08-15 | 2022-12-02 | 2023-05-01 | 2023-06-15 |  | TBD | TBD | TBD | TBD | TBD | First prelim date 1/31/2023
VA | Buckingham County, VA - FIRM Update | 51029 |  | 20-03-0041S | Restudy |  | 2 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-27 | 2022-09-09 | 2023-02-28 | 2023-07-01 |  | TBD | TBD | TBD | TBD | TBD
VA | Caroline County, VA - Mattaponi Basin-Wide Study | 51033 | 02080105 | 19-03-0013S | Restudy, Zone A |  | 3 | John Luff | Kristen Jones | kdunn@tandmassociates.com | Compass/ STARR II | N/A | Compass | 2017-09-20 | 2020-09-17 | 2021-06-01 | 2021-07-20 |  | 2022-02-22 | 2022-05-23 | TBD | 2022-11-23 | 2023-05-23
VA | Charlotte County, VA - FIRM Update | 51037 |  | 20-03-0042S | Restudy |  | 5 | John Luff | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2019-08-14 | TBD | 2023-06-01 | 2023-07-16 |  | TBD | TBD | TBD | TBD | TBD
VA | Cumberland County, VA - FIRM Update | 51049 |  | 20-03-0026S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | agilman@tandmassociates.com | Compass | Compass | ARC | 2018-11-27 | 2021-11-12 | 2022-04-14 | 2022-09-19 |  | TBD | TBD | TBD | 2023-08-31 | 2024-02-29
VA | Fairfax City, VA - Middle Potomac Anacostia Basin-Wide Study (Community Based) | 51600 | 02070010 | 14-03-3327S | Restudy |  | 1 | Lee Brancheau | Kristen Jones | matthew.mcglone@mbakerintl.com | STARR II | TBD | STARR II/ Compass / ARC | 2014-09-29 | 2020-04-06 | 2020-09-25 | 2020-10-27 | 2022-04-29 | 2022-10-06 | 2023-01-04 | TBD | TBD | TBD | First appeal period 7/8/21-10/6/21 | Original FRR on 2/23/2018
VA | Fairfax County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 51059 | 02070010 | 14-03-3327S | Restudy |  | 5 | Lee Brancheau | Kristen Jones | kevin.donnelly@stantec.com | STARR II | TBD | STARR II/ Compass | 2014-09-29 | 2020-04-06 | 2021-04-30 | 2021-08-05 | 2021-06-30 | TBD | TBD | TBD | TBD | TBD | First appeal period 4/22/22-7/21/22 | Original FRR on 9/30/2019
VA | Fairfax County, VA - Town of Herndon - Detailed Studies | 51059 |  | 23-03-0001S | Restudy |  | 2 | Lee Brancheau | Kristen Jones | craig.m.thomas@usace.army.mil | USACE - Baltimore | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD |  | USACE-Baltimore will produce a seamless floodplain mapping layer that they will hand over to the Town of Herndon. The Town of Herndon will submit a fee-exempt LOMR
VA | Falls Church City, VA - Middle Potomac Anacostia Basin-Wide Study (Community Based) | 51610 | 02070010 | 14-03-3327S | Restudy |  | 1 | Lee Brancheau | Kristen Jones | matthew.mcglone@mbakerintl.com | STARR II | TBD | STARR II/ Compass / ARC | 2014-09-29 | 2020-04-06 | 2020-09-18 | 2020-10-21 | 2022-04-29 | 2022-11-03 | 2023-02-01 | TBD | TBD | TBD | First appeal period 7/22/21-10/20/21 | Original FRR on 2/23/2018
VA | Fauquier County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 51061 | 02070010 | 14-03-3327S | Restudy |  | 4 | Lee Brancheau | Kristen Jones | matthew.mcglone@mbakerintl.com | STARR II | TBD | STARR II/ Compass / ARC | 2014-09-29 | 2018-02-23 | 2020-09-15 | 2020-10-28 | 2022-08-05 | 2021-05-11 | 2021-08-10 | TBD | TBD | TBD
VA | Fluvanna County, VA - FIRM Update | 51065 |  | 20-03-0031S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-26 | 2022-05-13 | 2022-11-15 | 2023-04-01 |  | TBD | TBD | TBD | TBD | TBD
VA | Franklin Independent City, VA - FIRM Update | 51620 |  | 20-03-0036S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | heather.rogers@freese.com | Compass | Compass | ARC | 2018-09-12 | TBD | 2023-04-01 | 2023-07-02 |  | TBD | TBD | TBD | TBD | TBD
VA | Fredericksburg City, VA - Lower Rappahannock | 51630 | 02080104 | 18-03-0012S | Zone A |  | 1 | Lee Brancheau | Kristen Jones | gjones@dewberry.com | STARR II | TBD | STARR II/ Compass | 2017-09-19 | 2019-05-28 | 2020-01-31 | 2020-03-03 | 2022-04-15 | 2020-12-02 | 2021-03-02 | 2022-08-04 | 2022-10-05 | 2023-04-05
VA | Goochland County, VA - FIRM Update | 51075 |  | 20-03-0027S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | noah.porter@aecom.com | Compass | Compass | TBD | 2018-11-27 | 2021-11-12 | 2022-05-24 | 2022-09-19 | 2022-08-25 | TBD | TBD | TBD | TBD | TBD
VA | Greensville County and Emporia Independent City, VA - FIRM Update | 51081 |  | 20-03-0043S | Restudy |  | 2 | John Luff | Kristen Jones | matthew.mcglone@mbakerintl.com | Compass | Compass | ARC | 2019-08-15 | 2022-12-02 | 2023-05-19 | 2023-06-30 |  | TBD | TBD | TBD | TBD | TBD | First prelim date 1/31/2023
VA | Halifax County, VA - Countywide | 51083 |  | 23-03-0003S | TBD |  | TBD | John Luff | TBD | david.r.cooper@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Hanover County, VA - Pamunkey Basin-Wide Study | 51085 | 02080106, 02080206 | 19-03-0021S | Restudy, Zone A |  | 2 | John Luff | Kristen Jones | agilman@tandmassociates.com | Compass | TBD | TBD | 2017-09-20 | 2020-09-17 | 2022-03-24 | 2022-09-19 |  | TBD | TBD | TBD | TBD | TBD
VA | Isle of Wight County, VA - Data Development & FIRM Update | 51093 |  | 20-03-0037S | Restudy |  | 3 | Hani Rimawi | Kristen Jones | lshepherd@moffattnichol.com | Compass | Compass | ARC | 2018-09-12 | 2023-03-01 | 2023-04-01 | 2023-07-02 |  | TBD | TBD | TBD | 2023-08-31 | 2024-02-29
VA | King William County, VA - Pamunkey Basin-Wide Study | 51101 | 02080106 | 19-03-0010S | Restudy, Zone A |  | 2 | John Luff | Kristen Jones | kdunn@tandmassociates.com | Compass | N/A | Compass | 2017-09-20 | 2020-09-17 | 2021-06-01 | 2021-08-03 |  | 2022-02-09 | 2022-05-10 | TBD | 2022-11-09 | 2023-05-09
VA | Lower Dan HUC8 - Data Development |  | 03010104 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | benjamin.kaiser@aecom.com | N/A | Compass | N/A | 2019-08-13 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Lower James Basin- Chesterfield County | 51041 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | david.r.cooper@wsp.com | STARR II | TBD | STARR II/ Compass / ARC | 2016-08-25 | 2020-04-28 | 2021-06-14 | 2021-07-22 | 2022-06-30 | 2022-12-12 | 2023-03-12 | TBD | TBD | TBD
VA | Lower James Basin- City of Colonial Heights | 51570 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | david.r.cooper@wsp.com | STARR II | TBD | STARR II/ Compass / ARC | 2016-08-25 | 2020-04-28 | 2021-02-12 | 2021-04-01 | 2022-05-31 | 2022-12-12 | 2023-03-12 | TBD | TBD | TBD | First appeal period 10/22/2021-1/20/2022
VA | Lower James Basin- City of Hopewell | 51670 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | donald.syriani@stantec.com | STARR II | TBD | STARR II/ Compass | 2016-08-25 | 2020-04-28 | 2021-02-12 | 2021-03-31 |  | 2021-09-24 | 2021-12-23 | TBD | 2022-06-15 | 2022-12-15 | Open House scheduled 11/17/2021 | Open House scheduled 10/27/2021
VA | Lower James Basin- City of Petersburg | 51730 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | errol.dufour@stantec.com | STARR II | TBD | STARR II/ Compass | 2016-08-25 | 2020-04-28 | 2021-02-12 | 2021-03-25 |  | 2021-09-02 | 2021-12-01 | TBD | 2022-06-15 | 2022-12-15
VA | Lower James Basin- City of Richmond | 51760 | 02080206 | 16-03-2426S | Restudy |  | 1 | Bob Pierson | Kristen Jones | jarod.skrivanek@wsp.com | STARR II | TBD | STARR II/ ARC | 2016-08-25 | 2021-07-28 | 2022-02-02 | 2022-04-18 |  | TBD | TBD | TBD | TBD | TBD
VA | Lower James Basin- Henrico County | 51087 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | jarod.skrivanek@wsp.com | STARR II | TBD | STARR II/ Compass / ARC | 2016-08-25 | 2021-04-27 | 2021-11-12 | 2021-12-09 |  | 2022-08-10 | 2022-11-08 | TBD | TBD | TBD
VA | Lower James Basin- Prince George County | 51149 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | errol.dufour@stantec.com | STARR II | TBD | STARR II/ Compass | 2016-08-25 | 2019-08-14 | 2021-02-26 | 2021-03-29 |  | 2021-10-22 | 2022-01-20 | TBD | 2022-08-09 | 2023-02-09
VA | Lunenburg County, VA - FIRM Update | 51111 |  | 20-03-0028S | Restudy |  | 1 | John Luff | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2019-08-15 | 2022-12-02 | 2023-05-01 | 2023-06-15 |  | TBD | TBD | TBD | TBD | TBD | First prelm date 1/31/2023
VA | Lynchburg Independent City, VA - FIRM Update | 51680 |  | 20-03-0033S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-27 | 2022-09-15 | 2023-04-15 | 2023-05-15 |  | TBD | TBD | TBD | TBD | TBD | First prelim date 2/28/2023
VA | Manassas City, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 51683 | 02070010 | 14-03-3327S | Restudy |  | 1 | John Luff | Kristen Jones | matt.witosky@stantec.com | STARR II | TBD | STARR II | 2014-09-29 | 2018-02-23 | 2020-09-30 | 2020-10-28 | 2022-08-24 | 2021-05-13 | 2021-08-11 | TBD | TBD | TBD
VA | Manassas Park City, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 51685 | 02070010 | 14-03-3327S | Restudy |  | 1 | John Luff | Kristen Jones | matt.witosky@stantec.com | STARR II | TBD | STARR II | 2014-09-29 | 2018-02-23 | 2020-09-30 | 2020-10-28 | 2022-08-24 | 2021-05-13 | 2021-08-11 | TBD | TBD | TBD
VA | Mecklenburg, VA - Countywide | 51117 |  | 23-03-0004S | TBD |  | TBD | John Luff | TBD | heather.rogers@freese.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Meherrin HUC8 |  | 03010204 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | mike.seering@aecom.com | Compass | Compass | N/A | 2019-08-15 | 2022-12-02 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
VA | Middle James-Buffalo HUC8 |  | 02080203 | 18-03-0031S | Restudy |  | N/A | John Luff | Kristen Jones | rajendra.rachamalla@atkinsglobal.com | STARR II | TBD | TBD | 2018-11-27 | 2022-09-09 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
VA | Middle New HUC8 - Data Development |  | 05050002 | 19-03-0005S | Restudy |  | N/A | John Luff | Kristen Jones | mike.seering@aecom.com | Compass | Compass | N/A | 2019-08-06 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Montgomery County, VA - Upper New Basin-Wide Study | 51121 | 03010101, 05050001 | 17-03-0960S | Zone A |  | 3 | Lee Brancheau | Kristen Jones | kevin.donnelly@stantec.com | STARR II | TBD | STARR II | N/A | N/A | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Nelson County, VA - FIRM Update | 51125 |  | 20-03-0034S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | jarod.skrivanek@wsp.com | Compass | Compass | ARC | 2018-11-27 | 2022-09-09 | 2023-02-28 | 2023-04-14 |  | TBD | TBD | TBD | TBD | TBD
VA | North Anna Pamunkey - Detailed H&H Study |  | 02080106 | 17-03-1358S | FRP | N/A | N/A | Andrew Jackson | Kristen Jones | kdunn@tandmassociates.com | Compass | N/A | N/A | 2017-09-20 | N/A | N/A | N/A |  | N/A | N/A | TBD | N/A | N/A |  | Scoped for survey, H&H, and floodplain mpapping only, no reg or non-reg deliverables
VA | Powhatan County, VA - FIRM Update | 51145 |  | 20-03-0029S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | noah.porter@aecom.com | Compass | Compass | TBD | 2018-11-27 | 2021-11-12 | 2022-05-24 | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Prince Edward County, VA - Countywide | 51147 | 02080207 | 19-03-0018S | Restudy, Zone A |  | 2 | John Luff | Kristen Jones | jarod.skrivanek@wsp.com | STARR II | TBD | STARR II/ Compass / ARC | 2018-09-10 | 2020-07-10 | 2021-04-14 | 2021-04-28 |  | 2022-02-16 | 2022-05-17 | TBD | 2022-10-19 | 2023-04-19
VA | Prince William County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 51153 | 02070010 | 14-03-3327S | Restudy |  | 5 | John Luff | Kristen Jones | matthew.mcglone@mbakerintl.com | STARR II | TBD | STARR II/ Compass / ARC | 2014-09-29 | 2018-02-23 | 2020-09-30 | 2020-10-28 | 2022-08-24 | 2021-05-13 | 2021-08-11 | TBD | TBD | TBD
VA | Pulaski County, VA - Upper New Basin-Wide Study | 51155 | 05050001, 05050002 | 18-03-0014S | Zone A |  | 3 | Lee Brancheau | Kristen Jones | jarod.skrivanek@wsp.com | STARR II | TBD | STARR II/ Compass / ARC | N/A | 2019-06-03 | 2020-01-31 | 2020-02-20 | 2022-05-15 | 2022-12-18 | 2023-03-18 | TBD | TBD | TBD | Original revised preliminary dated 6/30/2021, first appeal period 8/30/2020-11/28/2020
VA | REG Virginia Automated Engineering - FY18 BLE |  | 02080203, 03010201, 03010202, 03010204 | 17-03-0914S | Zone A |  | N/A | Andrew Jackson | N/A | daniel.ahn@stantec.com | STARR II | TBD | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | TBD | N/A | N/A
VA | Rivanna HUC8 |  | 02080204 | 18-03-0031S | Restudy |  | N/A | Andrew Jackson | Kristen Jones | justin.king@stantec.com | STARR II | TBD | TBD | 2018-11-26 | 2022-05-13 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
VA | Roanoke Rapids HUC8 |  | 03010106 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | christine.estes@aecom.com | Compass | TBD | TBD | 2019-08-14 | 2023-02-15 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Southampton County, VA - FIRM Update | 51175 |  | 20-03-0038S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | heather.rogers@freese.com | Compass | Compass | ARC | 2018-09-11 | TBD | 2023-04-01 | 2023-07-02 |  | TBD | TBD | TBD | TBD | TBD
VA | Spotsylvania County, VA - Mattaponi Basin-Wide Study | 51177 | 02080103, 02080104, 02080105, 02080106 | 18-03-0011S | Zone A |  | 1 | Lee Brancheau | Kristen Jones | gjones@dewberry.com | STARR II | TBD | STARR II/ Compass | 2017-09-19 | 2019-05-28 | 2020-01-31 | 2020-03-03 | 2021-09-30 | 2022-02-22 | 2022-05-23 | 2022-08-04 | 2022-11-09 | 2023-05-09 | First appeal period 12/2/20-3/2/21
VA | Stafford County, VA - Lower Potomac Basin | 51179 | 02070011 | 18-03-0002S | Restudy, Zone A |  | 1 | Lee Brancheau | Kristen Jones | agilman@tandmassociates.com | Compass/ STARR II/ USACE | N/A | Compass | 2017-09-18 | 2019-03-11 | 2019-12-23 | 2020-02-19 | 2021-07-21 | 2022-03-25 | 2022-06-23 | 2022-08-04 | 2022-12-07 | 2023-06-07 | Original appeals period from 9/30/2020 - 12/29/2020 | First revised preliminary date is 7/10/2020
VA | Suffolk City, VA - Data Development & FIRM Update | 51800 |  | 20-03-0039S | Restudy |  | 1 | Hani Rimawi | Kristen Jones | lshepherd@moffattnichol.com | Compass | Compass | ARC | 2018-09-11 | TBD | 2023-07-15 | 2023-11-15 |  | TBD | TBD | TBD | TBD | TBD | First prelim date 4/1/2023
VA | Sussex County VA - Data Development | 51183 |  | 20-03-0025S | Restudy |  | N/A | Amanuel Ghebreegziabher | Kristen Jones | rebecca.starosta@aecom.com | N/A | Compass | N/A | 2018-09-11 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Sussex County, VA - Countywide | 51183 |  | TBD | TBD |  | TBD | Amanuel Ghebreegziabher | TBD | tyler.bruce@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Upper (Partial) and Middle Roanoke HUC8 |  | 03010102 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | kdunn@tandmassociates.com | Compass | Compass | TBD | 2019-08-14 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Upper Dan HUC8 - Data Development |  | 03010103 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | benjamin.kaiser@aecom.com | N/A | Compass | N/A | 2020-07-09 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Upper Levisa HUC8 Watershed Discovery |  | 05070202 | TBD | Discovery |  | TBD | Lee Brancheau | TBD | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Upper New Watershed Discovery |  | 05050001 | TBD | Discovery |  | TBD | Lee Brancheau | TBD | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
VA | Upper Roanoke HUC8 - Data Development |  | 03010101 | 19-03-0032S | Restudy |  | N/A | John Luff | Kristen Jones | kdunn@tandmassociates.com | N/A | Compass | N/A | 2020-07-09 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA | Upper Yadkin HUC8 - Data Development |  | 03040101 | 20-03-0023S | Restudy |  | N/A | John Luff | Kristen Jones | celiko@cdmsmith.com | N/A | Compass | Compass | 2020-07-09 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Scoped for data dev only
VA, WV | Tug HUC8 Flood Studies |  | 05070201 | 21-03-0025S | Restudy |  | N/A | Hani Rimawi | Betsy Ranson | benjamin.kaiser@aecom.com | Compass | TBD | TBD | 2012-06-13 | 2022-06-23 | N/A | TBD |  | TBD | TBD | TBD | TBD | TBD | Scoped for data dev only
WV | Berkeley County, WV - Countywide Study | 54003 |  | 21-03-0021S | Restudy |  | 3 | Andrew Jackson | Betsy Ranson | brandon.cramer@woodplc.com | Wood / DEM | USACE | TBD | 2021-11-15 | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Big Sandy HUC8 Flood Studies |  | 05070204 | 21-03-0025S | Restudy |  | TBD | Hani Rimawi | Betsy Ranson | heather.zhao@aecom.com | Compass | TBD | TBD | TBD | N/A | N/A | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Coal HUC8 - Discovery (Kanawha River Basin) |  | 05050009 | 21-03-0026S | Discovery |  | N/A | Hani Rimawi | Betsy Ranson | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Elk HUC8 - Discovery (Kanawha River Basin) |  | 05050007 | 19-03-0005S | Discovery |  | N/A | Bob Pierson | Betsy Ranson | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Gauley HUC8 - Discovery (Kanawha River Basin) |  | 05050005 | 19-03-0005S | Discovery |  | N/A | Andrew Jackson | Betsy Ranson | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Greenbrier County, WV Countywide | 54025 | 05050003, 05050005 | 19-03-0028S | Restudy |  | 9 | Andrew Jackson | Betsy Ranson | jonathan.langley@woodplc.com | Wood | USACE | TBD | N/A | 2020-09-15 | 2021-09-30 | 2021-10-25 |  | 2022-05-13 | 2022-08-11 | TBD | 2023-01-05 | 2023-07-05
WV | Hampshire County, WV - Countywide | 54027 |  | 21-03-0004S | Restudy |  | 3 | Andrew Jackson | Betsy Ranson | jonathan.langley@wsp.com | Wood | USACE | ARC | 2021-06-28 | TBD | 2023-04-15 | TBD |  | TBD | TBD | TBD | TBD | TBD | Kick-off meeting on 6/28
WV | Hardy County, WV - Countywide | 54031 |  | 21-03-0002S | Restudy |  | 3 | Bob Pierson | Betsy Ranson | brandon.cramer@woodplc.com | Wood | USACE | Wood / ARC | N/A | 2021-09-15 | 2022-04-14 | 2022-06-21 |  | TBD | TBD | TBD | TBD | TBD
WV | Hardy County, WV, (LAMP Moorefield Levees) | 54031 |  | 11-03-0526S | Levee |  | 2 | Bob Pierson | Bobby Cobelli | brandon.cramer@wsp.com | RAMPP / Compass / ARC | N/A | TBD | N/A | N/A | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Funded for continued LSIP monitoring
WV | Huntington, WV, LPP - Guyandotte | 54011 |  | TBD | Levee |  | TBD | Bob Pierson | Bobby Cobelli | TBD | USACE-Huntington | TBD | TBD | TBD | TBD | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
WV | Huntington, WV, LPP (Ohio River Floodwall) | 54011 |  | TBD | Levee |  | TBD | John Luff | Bobby Cobelli | TBD | USACE-Huntington | TBD | TBD | TBD | 2019-08-27 | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Jefferson County, WV - Countywide | 54037 |  | 21-03-0006S | Restudy |  | 6 | Andrew Jackson | Betsy Ranson | tyler.bruce@wsp.com | Wood | USACE | ARC | N/A | 2023-06-15 | 2023-10-31 | TBD |  | TBD | TBD | TBD | TBD | TBD | First prelim date 6/30/2023
WV | Kanawha County - WV Disaster County PMR | 54039 | 05050006 | 19-03-0002S | Restudy | 1 | 2 | Bob Pierson | Betsy Ranson | jonathan.langley@woodplc.com | Wood | USACE | Wood | N/A | 2019-05-30 | 2019-12-13 | 2021-03-23 | 2021-10-25 | 2022-05-20 | 2022-08-18 | 2022-08-29 | 2023-02-01 | 2023-08-01 | First revised prelim issed on 2/25/2021
WV | Little Kanawha HUC8 Watershed Discovery |  | 05030203 | TBD | Discovery |  | TBD | Lee Brancheau | TBD | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Lower Guyandotte HUC8 Flood Studies |  | 05070102 | 21-03-0026S | Restudy |  | TBD | Hani Rimawi | Betsy Ranson | boudjemaam@cdmsmith.com | Compass | TBD | TBD | 2017-08-22 | N/A | N/A | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Lower Kanawha HUC8 - Discovery (Kanawha River Basin) |  | 05050008 | 19-03-0005S | Discovery |  | N/A | John Luff | Betsy Ranson | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Lower New HUC8 - Discovery (Kanawha River Basin) |  | 05050004 | 19-03-0005S | Discovery |  | N/A | Amanuel Ghebreegziabher | Betsy Ranson | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Mercer County Flood Studies | 54055 |  | 19-03-0005S | Restudy |  | TBD | Bob Pierson | Betsy Ranson | mike.seering@aecom.com | Compass | TBD | TBD | 2019-08-06 | TBD | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
WV | Mineral County, WV - Kitzmiller and Blaine Levee PMR | 54057 |  | 21-03-0011S | Levee |  | TBD | Bob Pierson | Betsy Ranson | craig.m.thomas@usace.army.mil | TBD | TBD | TBD | N/A | TBD | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD
WV | Mineral County, WV (LAMP Ridgeley Levee) | 54057 |  | 14-03-1666S | Levee |  | 2 | Bob Pierson | Bobby Cobelli | james.barbis@woodplc.com | RAMPP / Compass / ARC | TBD | TBD | N/A | 2018-03-01 | TBD | N/A |  | TBD | TBD | TBD | TBD | TBD |  | Funded for LAMP plan
WV | Monroe County WV - Countywide Update | 54063 |  | 21-03-0007S | Restudy |  | 4 | Amanuel Ghebreegziabher | Betsy Ranson | brandon.cramer@wsp.com | Wood | USACE | ARC | 2019-08-06 | 2022-05-31 | 2022-10-31 | 2022-12-15 |  | TBD | TBD | TBD | TBD | TBD
WV | Morgan County, WV - Countywide Study | 54065 |  | 21-03-0020S | Restudy |  | 3 | Andrew Jackson | Betsy Ranson | jonathan.langley@woodplc.com | Wood / DEM | USACE | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD | Kick-off meeting on 11/15/21
WV | Pendleton County, WV - Countywide | 54071 |  | 21-03-0003S | Restudy |  | 2 | Andrew Jackson | Betsy Ranson | tyler.bruce@wsp.com | Wood | USACE | Wood / ARC | N/A | 2021-04-15 | 2021-09-07 | 2021-09-14 |  | 2022-03-03 | 2022-06-01 | TBD | 2022-11-09 | 2023-05-09
WV | Pocahontas County, WV - Countywide | 54075 |  | 21-03-0005S | Restudy |  | 4 | Andrew Jackson | Betsy Ranson | david.r.cooper@wsp.com | Wood | USACE | ARC | N/A | 2022-12-01 | 2023-10-01 | TBD |  | TBD | TBD | TBD | TBD | TBD | Kick-off meeting on 6/28, original prelim 7/30/2023
WV | Raccoon-Symmes HUC8 Flood Studies |  | 05090101 | 21-03-0024S | Restudy |  | TBD | Hani Rimawi | Betsy Ranson | rebecca.starosta@aecom.com | Compass | TBD | TBD | N/A | N/A | N/A | N/A |  | TBD | TBD | TBD | TBD | TBD
WV | Summers County, WV - Countywide | 54089 |  | 21-03-0008S | Restudy |  | 2 | Amanuel Ghebreegziabher | Betsy Ranson | brandon.cramer@wsp.com | Wood | USACE | ARC | N/A | 2022-02-17 | 2022-09-30 | 2022-12-15 |  | TBD | TBD | TBD | TBD | TBD
WV | Twelvepole HUC8 Flood Studies |  | 05090102 | 21-03-0024S | Restudy |  | TBD | Hani Rimawi | Betsy Ranson | rebecca.starosta@aecom.com | Compass | TBD | TBD | TBD | N/A | N/A | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Upper Guyandotte HUC8 - Discovery |  | 05070101 | 21-03-0026S | Discovery |  | N/A | Hani Rimawi | Betsy Ranson | crystal.ward@wsp.com | Compass | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Upper Guyandotte HUC8 Flood Studies |  | 05070101 | 21-03-0026S | Restudy |  | TBD | Hani Rimawi | Betsy Ranson | heather.zhao@aecom.com | Compass | TBD | TBD | TBD | N/A | N/A | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Upper Kanawha HUC8 - Discovery (Kanawha River Basin) |  | 05050006 | 19-03-0005S | Discovery |  | N/A | John Luff | Betsy Ranson | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD
WV | Upper Ohio-Shade Watershed Discovery |  | 05030202 | TBD | Discovery |  | TBD | Lee Brancheau | TBD | crystal.ward@wsp.com | ARC | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD

## FMPU Archive
STATE | PROJECT | FIPS | HUC8 | MIP CASE NO | INSURANCE INTEREST | # Rev Prel | # Ordinance Updates | FEMA ENG | FEMA PLAN | Study Manager | DATA DEVT PART | ENG RVW PART | POST PROCESS PART | Discovery Meeting | Fld Rsk Rvw Mtg | Preliminary | Resilience Meeting | CCO Meeting | Open House Meeting | Most Recent Rev Prel | APPEAL PERIOD STARTS | APPEAL PERIOD ENDS | PRE/POST LFD MEETING | LFD | EFFECTIVE | CURRENT NOTE | ARCHIVED NOTES
DC | Washington, DC | 11001 |  | MICS_12682 | PAL/Restudy |  | 1 | Jon Janowicz | Marty Frengs |  | USACE | N/A | Baker | N/A | N/A | 2006-09-20 | N/A | N/A | N/A |  | 2007-09-21 | 2008-01-03 |  | 2010-03-26 | 2010-09-27 |  | 3/14/2014: Second set of appeals runs 3/19 - 6/17 for communities that published on different date. 12/23/2013: FR for appeals published. 5/17 & 8/2/2013: revised prelims issued for Atlantic coastal communities; Original prelim issued 1/31/2013.
DC | Washington, DC, Federal Triangle Flood Study | 11001 |  | 10-03-0356S |  |  |  | Jon Janowicz | Henry Chau |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
DC | Washington, DC, PMR (Anacostia River Et Al) | 11001 |  | 13-03-0096S |  |  |  | Robin Danforth | Henry Chau |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
DE | Kent County, DE - Delaware Risk MAP | 10001 |  | 13-03-1974S | Restudy |  | 3 | Nikki Roberts | Charlie Baker | manas.borah@aecom.com | AECOM | TBD | AECOM | N/A | 2015-06-23 | 2016-02-15 | TBD | 2016-04-20 | N/A |  | 2017-06-01 | 2017-09-01 |  | 2017-12-20 | 2018-06-20
DE | Kent County, DE (Pre-MM) | 10001 |  | MICS_10055 |  |  | 15 | [6 empty] | N/A | N/A | 2001-09-27 | N/A | N/A | N/A |  |  |  |  | 2002-11-05 | 2003-05-05 |  | Jan-2016: Original CCO meeting held 6-13-2011
DE | Kent County, DE, Coastal PMR | 10001 |  | 10-03-0341S | Restudy |  | 12 | Robin Danforth | Darlene Messina |  | RAMPP | RAMPP | RAMPP | 2010-12-01 | 2012-07-31 | 2012-08-30 | 2014-11-18 | 2012-10-22 | 2013-07-02 |  | 2013-05-30 | 2013-08-27 |  | 2014-01-07 | 2014-07-07
DE | Kent County, DE, PMR (Murderkill River) SEE 10-03-0341S | 10001 |  | 11-03-2219S |  |  |  | Nikki Roberts | Katie Lipiecki |  |  |  |  | N/A | N/A | 2012-08-30 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
DE | New Castle County, DE | 10003 |  | 06-03-B785S | [9 empty] | N/A | N/A | 2005-09-01 | N/A | N/A | N/A |  |  |  |  | 2006-07-17 | 2007-01-17
DE | New Castle County, DE - Brandywine-Christina Basin-Wide Study | 10003 |  | 11-03-2202S | Rev Prel | 1 | 7 | Nikki Roberts | Charlie Baker | michael.powell@state.de.us | DNREC | TBD | DNREC/ COMPASS | N/A | N/A | 2017-06-15 | N/A | N/A |  | 2018-05-18 | 2018-12-14 | 2019-03-14 | 2019-07-31 | 2019-07-22 | 2020-01-22 |  | 12/23/2013: FR for appeals published. 6/13/2013: Mapping partner requested move to 10/2/2013 LFD; appeals period hasn't started yet. TO23 POP ends 6/30/2015.
DE | New Castle County, DE - Brandywine-Christina Basin-Wide Study (Revised Prelim for 11-03-2202S) | 10003 |  | 11-03-2202S | Rev Prel |  | 14 | Nikki Roberts | Sarah Wolfe | michael.powell@state.de.us | DNREC | TBD | DNREC | N/A | N/A | 2017-06-15 | N/A | N/A | N/A |  | N/A | N/A |  | TBD | TBD
DE | New Castle County, DE (MM) | 10003 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2002-11-05 | 2003-05-05
DE | New Castle County, DE, Coastal PMR | 10003 |  | 10-03-0342S |  |  |  | Robin Danforth | Darlene Messina |  |  |  |  | 2010-11-30 | 2012-12-06 | 2013-05-10 | 2015-07-09 | 2013-06-18 | 2013-11-26 |  |  |  |  | 2014-08-04 | 2015-02-04
DE | New Castle County, DE, PMR (Appoquinimink River) SEE 10-03-0342S | 10003 |  | 11-03-2220S |  |  |  | Nikki Roberts | Katie Lipiecki |  |  |  |  | N/A | N/A | 2011-11-07 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
DE | New Castle County, DE, PMR (White Clay Creek Et Al) | 10003 |  | 11-03-1442S |  |  |  | Nikki Roberts | Katie Lipiecki |  |  |  |  | N/A | N/A | 2013-04-30 | N/A | 2013-06-18 | N/A |  |  |  |  | 2014-03-03 | 2014-09-03
DE | Sussex County, DE - Delaware Risk MAP | 10005 |  | 13-03-1974S | Restudy | 1 | 8 | Nikki Roberts | Charlie Baker | manas.borah@aecom.com | AECOM | TBD | AECOM | N/A | 2015-06-23 | 2016-02-15 | TBD | 2016-04-20 | N/A | 2016-11-04 | 2017-06-02 | 2017-09-02 |  | 2017-12-20 | 2018-06-20
DE | Sussex County, DE (Pre-MM) | 10005 |  | MICS_15497 | [9 empty] | N/A | N/A | 2004-01-30 | N/A | N/A | N/A |  |  |  |  | N/A | 2005-01-06
DE | Sussex County, DE (Revised Prelim for 10-03-0343S) | 10005 |  | 13-03-2516S |  |  |  | Robin Danforth | Katie Lipiecki |  |  |  |  | N/A | N/A | 2013-05-31 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
DE | Sussex County, DE (South Bethany PMR) | 10005 |  | 15-03-1590S | Restudy |  | 2 | Bob Pierson | Molly Kaput | christine.estes@aecom.com | RAMPP | TBD | TBD | N/A | N/A | 2015-05-18 | TBD | 2015-05-21 | 2015-06-12 |  | 2015-10-23 | 2016-01-20 |  | 2016-09-07 | 2017-03-07
DE | Sussex County, DE, Coastal PMR | 10005 |  | 10-03-0343S | Restudy | 1 | 25 | Bob Pierson | Darlene Messina |  | RAMPP | RAMPP | RAMPP | 2011-12-01 | 2012-12-06 | 2013-01-31 | 2015-03-25 | 2013-06-19 | 2013-12-02 | 2013-05-31 | 2014-02-16 | 2014-05-06 |  | 2014-09-16 | 2015-03-16
DE | Sussex County, DE, PMR (Nanticoke River Et Al) | 10005 |  | 10-03-1994S |  |  |  | Nikki Roberts | Katie Lipiecki |  |  |  |  | N/A | N/A | 2010-12-30 | N/A | 2011-03-30 | N/A |  |  |  |  | 2014-01-07 | 2014-07-07
DE | Sussex County,DE | 10005 |  | 06-03-B515S | [9 empty] | N/A | N/A | 2004-01-06 | N/A | N/A | N/A |  |  |  |  | 2004-07-06 | 2005-01-06 |  | Open House scheduled for 4/2/19
MD | Allegany County, MD | 24001 |  | 09-03-0015S | Other BFE | 2 | 8 | Bob Pierson | Julius Lockhart | jason.sevanick@woodplc.com | Wood | USACE | Wood | N/A | N/A | 2011-04-14 | N/A | 2011-06-13 | N/A | 2018-12-11 | 2019-04-17 | 2019-07-16 | N/A | 2019-10-03 | 2020-04-03
MD | Allegany County, MD (Revised Prelim for 09-03-0015S) | 24001 |  | 14-03-3562S | Rev Prel | 2 | 8 | Bob Pierson | Heather Davis-Jenkins | jason.sevanick@woodplc.com | Wood | USACE | AMEC | N/A | N/A | 2018-12-11 | N/A | N/A | N/A | 2018-12-11 | 2019-04-17 | 2019-07-16 |  | N/A | N/A |  | 4/29/2014: Project restarting at appeals resolution stage. 4/13/2013: On hold awaiting funding to address appeals. 1/7/2013: Project put on hold to resolve 5 appeals. 11/2012: Dropped from 7/8/2013 LFD. Coordination will be needed. Funded in 2008
MD | Allegany County, MD (Revised Prelim for 09-03-0015S) | 24001 |  | 14-03-3562S | Rev Prel |  |  | Bob Pierson | Molly Kaput | jason.sevanick@amecfw.com | AMEC | N/A | N/A | N/A | N/A | 2015-09-30 | N/A | N/A | N/A |  | N/A | N/A |  | 2015-12-02 | 2016-06-02
MD | Allegany County, MD, Scoping (MM) | 24001 |  | 07-03-0421S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Completed QR5 &7. Will go LFD as planned.
MD | Anne Arundel Co., MD, Coastal PMR | 24003 |  | 11-03-0513S | Restudy |  |  | Bob Pierson | Molly Kaput | christine.worley@aecom.com | RAMPP | USACE | RAMPP | 2011-02-14 | 2013-03-25 | 2013-05-23 | 2016-03-11 | 2013-08-06 | 2014-09-09 |  | 2014-02-12 | 2014-05-12 |  | 2014-08-18 | 2015-02-18 |  | 1/4/2013: Awaiting decision on extension of TO2 POP.
MD | Anne Arundel County, MD | 24003 |  | 06-03-B487S | Restudy |  | 3 | Bob Pierson | Henry Chau |  | MDE / USACE | N/A | AMEC | N/A | N/A | 2009-09-30 | N/A | 2009-11-10 | N/A |  | 2010-06-11 | 2010-09-20 |  | 2012-04-16 | 2012-10-16
MD | Baltimore City (Ind), MD | 24510 |  | 09-03-0198S | Restudy | 1 | 1 | Nikki Roberts | Henry Chau |  | City of Baltimore CTP | N/A | GG3 | N/A | N/A | 2009-03-31 | N/A | N/A | N/A | 2010-12-30 |  |  |  | 2011-08-02 | 2012-02-02 |  | 12/23/2013: FR for appeals published. 1/14/2013: Prelim date pushed back to allow countywide to go effective.
MD | Baltimore City (Ind), MD (Rev Prel for 09-03-0198S) | 24510 |  | 10-03-2230S |  |  |  | Nikki Roberts | Henry Chau |  |  |  |  | N/A | N/A | 2010-12-30 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
MD | Baltimore City (Ind), MD, Coastal PMR | 24510 |  | 10-03-0345S | Restudy |  | 1 | Robin Danforth | Henry Chau |  | RAMPP | RAMPP | RAMPP | 2010-11-23 | 2012-10-24 | 2012-11-30 | 2016-03-11 | 2013-02-20 | 2014-04-22 |  | 2013-04-23 | 2013-07-21 |  | 2013-10-02 | 2014-04-02 |  | 3/2014: Case to be reopened since revised prelim was closed. 10/24/2013: Revised prelim iissued to correct water surface elevations between coastal and riverine studies.
MD | Baltimore City, MD - Gunpowder-Patapsco (Baltimore City) 11-03-2204S | 24510 |  | 13-03-1975S | Restudy |  | 1 | Bob Pierson | Julius Lockhart | dave.guignet@maryland.gov | MDE | TBD | MDE | 2011-11-16 | 2018-08-16 | 2018-12-26 | N/A | 2019-01-18 | N/A | N/A | 2019-04-17 | 2019-07-16 | TBD | 2020-12-16 | 2021-06-16
MD | Baltimore County (Uninc Areas), MD | 24005 |  | 09-03-2161S | PAL/Restudy |  | 1 | Nikki Roberts | Henry Chau |  | Baltimore County CTP | N/A | Dewberry | N/A | N/A | 2009-09-30 | N/A | N/A | N/A |  | 2010-06-09 | 2010-09-23 |  | 2011-02-02 | 2011-08-02
MD | Baltimore County (Uninc Areas), MD, Coastal PMR | 24005 |  | 10-03-0344S |  |  | 1 | Robin Danforth | Henry Chau |  | RAMPP | RAMPP | RAMPP | 2010-11-23 | 2012-10-24 | 2012-11-30 | 2016-03-11 | 2013-02-20 | TBD |  | 2013-04-23 | 2013-07-21 |  | 2013-11-05 | 2014-05-05 |  | On Hold
MD | Baltimore County, MD | 24005 |  | 06-03-B488S |  |  | 1 | Nikki Roberts | Ed Copeland |  |  |  |  | N/A | N/A | 2006-08-25 | N/A | N/A | N/A |  |  |  |  | 2008-03-26 | 2008-09-26 |  | Revising 1 FIRM panel based on study for Bayard Levees in Grant Co., WV
MD | Baltimore County, MD (MM) | 24005 |  | MICS_30215 | [9 empty] | N/A | N/A | 2003-02-25 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-07-16
MD | Calvert County, MD | 24009 |  | 06-03-B490S | Restudy |  | 3 | Bob Pierson | Henry Chau |  | MDE / USACE | N/A | AMEC | N/A | N/A | 2009-09-30 | N/A | 2009-11-09 | N/A |  | 2010-06-11 | 2010-09-23 |  | 2011-06-16 | 2011-12-16
MD | Calvert County, MD, Coastal PMR | 24009 |  | 11-03-0514S |  |  |  | Robin Danforth | Henry Chau |  |  |  |  | 2011-02-10 | 2013-02-19 | 2013-03-29 | 2015-05-06 | 2013-05-23 | 2014-01-22 |  |  |  |  | 2014-05-19 | 2014-11-19
MD | Caroline County, MD (Revised Prelim for 10-03-0346S) | 24011 |  | 13-03-2590S |  |  |  | Bob Pierson | Henry Chau |  |  |  |  | N/A | N/A | 2013-09-19 | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Incorporated Case No. 10-03-0349S. 1/15/2014: Potential delay with prelim to incorporate Plumtree Run study.
MD | Caroline County, MD, Coastal Countywide | 24011 |  | 10-03-0346S | Restudy | 1 | 11 | Bob Pierson | Molly Kaput | gjones@dewberry.com; jason.sevanick@amecfw.com | RAMPP | N/A | RAMPP | 2011-01-27 | 2013-02-21 | 2013-08-14 | 2016-01-19 | 2013-09-24 | 2014-06-12 | 2013-09-19 | 2015-02-05 | 2015-05-05 |  | 2014-07-16 | 2015-01-16
MD | Carroll County, MD | 24013 |  | 09-03-0013S | Restudy |  | 9 | Bob Pierson | Molly Kaput | mike.seering@aecom.com | MDE / USACE / AECOM | N/A | AMEC/RAMPP | N/A | N/A | 2010-06-04 | N/A | 2010-07-07 | N/A |  | 2012-07-18 | 2012-10-15 |  | 2015-04-02 | 2015-10-02
MD | Carroll County, MD PMR (South Branch Patapsco River) | 24013 |  | 15-03-0120S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | 2015-07-23 | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Per 9/16/10 rebaseline, USACE performing post-prel rev H&H per comm cmnts // Per 6/28/10 discussion with AMEC, FR pub and appeal period delayed pending additional coordination with communities
MD | Cecil County, MD | 24015 |  | 06-03-B491S | Restudy |  | 9 | Bob Pierson | Henry Chau |  | MDE / USACE | N/A | AMEC | N/A | N/A | 2010-04-28 | N/A | 2010-06-11 | N/A |  |  | 2012-12-19 |  | 2013-01-08 | 2013-07-08
MD | Cecil County, MD, Coastal PMR | 24015 |  | 10-03-0347S | Restudy |  | 8 | Bob Pierson | Molly Kaput | dsyriani@dewberry.com | RAMPP | RAMPP | RAMPP | 2010-11-30 | 2012-10-26 | 2013-08-01 | 2016-01-19 | 2013-09-23 | 2015-03-04 |  | 2014-03-19 | 2014-06-16 |  | 2014-11-04 | 2015-05-04
MD | Charles County, MD | 24017 |  | 09-03-0188S | Restudy |  | 3 | Bob Pierson | Katie Lipiecki |  | MDE / AMEC | USACE | AMEC | N/A | N/A | 2011-09-30 | N/A | 2011-12-19 | N/A |  | 2012-07-27 | 2012-10-24 |  | 2013-03-04 | 2013-09-04 |  | Will be rolled into future Howard County, MD project
MD | Charles County, MD, Coastal PMR | 24017 |  | 11-03-0515S | Restudy |  | 3 | Bob Pierson | Katie Lipiecki | christine.worley@aecom.com | RAMPP | USACE | RAMPP | 2011-02-09 | 2013-07-12 | 2013-09-05 | 2016-01-13 | 2013-09-23 | 2014-02-18 |  | 2014-02-26 | 2014-05-26 |  | 2014-11-04 | 2015-05-04
MD | Dorchester County, MD | 24019 |  | 06-03-B492S | Other BFE |  | 11 | Bob Pierson | David Odegard |  | MDE / USACE | AMEC | AMEC | N/A | N/A | 2009-03-12 | N/A | N/A | N/A |  | 2010-01-07 | 2010-04-28 |  | 2010-11-24 | 2011-05-24 |  | Incorporated Case No. 14-03-2034S (Rev Prel). 1/14/2013: Materials submitted to AMEC; will release Coastal and revised prelim together. First appeals period for Countywide ended 8/9/2011.
MD | Dorchester County, MD, Coastal PMR | 24019 |  | 10-03-0348S | Restudy | 1 | 10 | Bob Pierson | Molly Kaput | dsyriani@dewberry.com | RAMPP | RAMPP | RAMPP | 2011-02-01 | 2013-03-21 | 2013-05-28 | 2016-01-21 | 2013-08-01 | 2014-06-10 | 2013-10-24 | 2014-03-14 | 2014-06-11 |  | 2014-09-16 | 2015-03-16
MD | Dorchester County, MD, Coastal PMR (Revised Prelim for 10-03-0348S) | 24019 |  | 14-03-0119S |  |  |  | Robin Danforth | Henry Chau |  |  |  |  | N/A | N/A | 2013-10-24 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
MD | Frederick County, MD | 24021 |  | MICS_30217 | [9 empty] | N/A | N/A | 2005-08-05 | N/A | N/A | N/A |  |  |  |  | 2007-03-19 | 2007-09-19
MD | Garrett County, MD | 24023 |  | 09-03-0200S | On Hold |  | 9 | Bob Pierson | Katie Lipiecki |  |  |  |  | N/A | N/A | 2011-09-30 | N/A | 2011-12-20 | N/A |  |  |  |  | 2013-04-02 | 2013-10-02 |  | RSC: Final Meeting same day as Wicomico // AMEC: Revised prelim to correct all partial foot BFEs & missing VE area (email from J. Sevanick on 10/14/2009)
MD | Garrett County, MD (LAMP Bayard Levees) | 24023 |  | 11-03-0525S | Restudy |  | 1 | Bob Pierson | Heather Davis-Jenkins | christine.estes@aecom.com | RAMPP / STARR II | N/A | Compass | N/A | N/A | 2017-01-06 |  | 2017-02-22 |  |  | 2017-12-21 | 2018-03-21 |  | 2018-08-01 | 2019-02-01
MD | Garrett County, MD (PAL Kitzmiller and Blaine Levees) | 24023 |  | 14-03-3488S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | 2015-09-30 | N/A | N/A | N/A |  |  |  |  | 2017-12-20 | 2018-06-20
MD | Garrett County, MD, Scoping (MM) | 24023 |  | 07-03-0423S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
MD | Harford County | 24025 |  | MICS_12593 | [9 empty] | N/A | N/A | 1999-01-07 | N/A | N/A | N/A |  |  |  |  | N/A | 2000-01-07 |  | Funded in 2008; first appeals period ended 10/10/2012.
MD | Harford County, MD, Coastal PMR | 24025 |  | 10-03-0349S |  |  |  | Robin Danforth | Henry Chau |  |  |  |  | 2011-02-02 | 2013-01-06 | 2014-07-09 | N/A | 2014-12-16 | 2015-02-17 |  |  |  |  | 2015-03-02 | 2015-09-02
MD | Harford County, MD, Countywide Rev | 24025 |  | 11-03-0518S | Restudy | 1 | 4 | Bob Pierson | Molly Kaput | christine.estes@aecom.com | RAMPP | USACE | RAMPP | 2011-02-02 | 2013-01-06 | 2014-07-09 | 2016-03-11 | 2014-12-16 | 2015-05-14 | 2014-11-21 | 2015-04-24 | 2015-07-22 |  | 2015-10-19 | 2016-04-19
MD | Harford County, MD, Countywide Rev (Revised Prelim for 11-03-0518S) | 24025 |  | 14-03-3441S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | 2014-11-21 | N/A | N/A | N/A |  |  |  |  | 2015-03-02 | 2015-09-02 |  | Nov-2014: Revised preliminary issued 11/14/2014 // 6/6/2014: On hold in MIP for revised prelim. 1/4/2012: Awaiting decision on extension of TO2 POP.
MD | Howard County, MD | 24027 |  | 06-03-B493S | Other BFE |  | 1 | Bob Pierson | Henry Chau |  | MDE / USACE | AMEC | AMEC | N/A | N/A | 2009-11-30 | N/A | 2011-09-28 | N/A |  | 2012-05-17 | 2012-08-14 |  | 2013-05-06 | 2013-11-06 |  | Effective Aug-2017 and Resilience N/A or Held May-2015: Includes revised preliminary (14-03-3543S) issued 3/31/2015. // 6/5/2013: On hold until funding for new hydraulics and post-processing becomes available. Awaiting new LiDAR data. // First CCO Meeting on 2/28/2011 - no appeal period to date.
MD | Kent County, MD, Coastal Countywide | 24029 |  | 10-03-0350S |  |  | 6 | Bob Pierson | Katie Lipiecki |  | AMEC / RAMPP | AMEC / RAMPP | AMEC | 2011-01-26 | 2012-11-28 | 2012-09-27 | 2014-11-18 | 2012-11-28 | 2014-06-19 |  | 2013-04-11 | 2013-07-09 |  | 2013-12-09 | 2014-06-09
MD | Montgomery County, MD | 24031 |  | MICS_30218 | [9 empty] | N/A | N/A | 2005-09-27 | N/A | N/A | N/A |  |  |  |  | 2006-03-29 | 2006-09-29
MD | Patuxent River - Updated Detailed Study |  |  | 19-03-0041S | PENDING |  | N/A | Lee Brancheau | Julius Lockhart | Craig.M.Thomas@usace.army.mil | USACE | TBD | TBD | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Incorporated Case No. 10-03-0354S. 4/9/2015: First appeal period 31-Mar-2010 to 28-Jun-2010. 4/8/2013: Coastal project will be combined with countywide. 2nd Appeal Period needed for Beaverdam Creek Revision (6/28/2010 from Jason S. at AMEC)
MD | Prince George's County, MD | 24033 |  | 06-03-B494S |  | 1 |  | Bob Pierson | Henry Chau |  |  |  |  | N/A | N/A | 2010-09-30 | N/A | 2010-11-30 | N/A | 2015-01-16 |  |  |  | 2015-06-02 | 2015-12-02
MD | Prince George's County, MD (Combined Coastal and Countywide) | 24033 |  | 11-03-0516S | Restudy |  | 3 | Bob Pierson | Molly Kaput | christine.estes@aecom.com | RAMPP | USACE | RAMPP | 2011-02-08 | 2012-11-12 | 2013-02-22 | 2016-03-14 | 2013-04-25 | 2015-06-10 |  | 2015-06-04 | 2015-09-01 |  | 2016-03-16 | 2016-09-16
MD | Prince George's County, MD (Revised Prelim for 06-03-B494S) | 24033 |  | 14-03-2034S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | 2015-01-16 | N/A | N/A | N/A |  |  |  |  | 2015-06-02 | 2015-12-02
MD | Queen Anne's County, MD, Coastal Countywide | 24035 |  | 10-03-0351S |  |  |  | Bob Pierson | Katie Lipiecki |  |  |  |  | N/A | N/A | 2012-09-27 | N/A | N/A | N/A |  |  |  |  | 2014-04-16 | 2014-10-16
MD | Queen Anne's, MD (PPP for 10-03-0351S) | 24035 |  | 13-03-2568S | Restudy |  | 9 | Bob Pierson | Molly Kaput | christine.worley@aecom.com; jason.sevanick@amecfw.com | RAMPP | N/A | RAMPP | 2011-01-26 | 2013-01-16 | 2012-09-28 | 2016-01-19 | 2013-01-16 | 2014-07-24 |  | 2013-04-05 | 2013-07-03 |  | 2014-05-05 | 2014-11-05
MD | Somerset County, MD | 24039 |  | 06-03-B495S | Restudy |  | 3 | Bob Pierson | David Odegard |  | MDE / USACE | AMEC | AMEC | N/A | N/A | 2008-12-31 | N/A | N/A | N/A |  | 2010-01-07 | 2010-04-28 |  | 2010-09-03 | 2011-03-03
MD | Somerset County, MD, Coastal PMR | 24039 |  | 10-03-0352S | Restudy |  | 3 | Robin Danforth | Molly Kaput | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2011-02-02 | 2013-02-21 | 2013-03-21 | 2016-01-21 | 2013-05-22 | 2014-06-11 |  | 2014-02-12 | 2014-05-12 |  | 2014-08-04 | 2015-02-04 |  | Only funded through Floodplain Mapping /workmap for Zone A and Zone AE studies
MD | St. Marys County | 24037 |  | MICS_10088 |  |  | 1 | [6 empty] | N/A | N/A | 2003-05-02 | N/A | N/A | N/A |  |  |  |  | 2004-04-19 | 2004-10-19 |  | Second appeals period only for affected communities. First appeals period ended 7/24/2013. 6/5/2013: On hold until funding for new hydraulics and post-processing becomes available.
MD | St. Mary's County, MD, Coastal PMR | 24037 |  | 11-03-0517S | Restudy |  | 2 | Robin Danforth | Henry Chau | christine.worley@aecom.com | RAMPP | N/A | RAMPP | 2011-02-10 | 2013-02-19 | 2013-03-29 | 2016-01-13 | 2013-05-23 | 2014-06-09 |  | 2013-09-11 | 2013-12-09 |  | 2014-05-19 | 2014-11-19
MD | Talbot County, MD | 24041 |  | 09-03-0199S | Restudy |  | 5 | Bob Pierson | Henry Chau |  | MDE / AMEC | USACE | AMEC | N/A | N/A | 2011-06-30 | N/A | 2011-08-22 | N/A |  | 2012-08-22 | 2012-11-19 |  | 2013-02-05 | 2013-08-05
MD | Talbot County, MD (Revised Prelim for 10-03-0353S) | 24041 |  | 16-03-0378S | Rev Prel |  | 0 | Bob Pierson | Molly Kaput | kdunn@dewberry.com | RAMPP | RAMPP | RAMPP | N/A | N/A | 2015-11-17 | N/A | N/A | N/A |  | N/A | N/A |  | 2016-01-20 | 2016-07-20 |  | 4/1/2014: Analysis of Kittanning Floodwall confirmed; revised panel prelim 6/10/2014. 1st rev prelim issued 2/1/2013. 1st app period ended 4/24/2011; will require 2nd appeals period for revised map. Original CCO meeting held 8/24/2010.
MD | Talbot County, MD (Revised Prelim for 10-03-0353S) | 24041 |  | 14-03-2312S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | 2014-11-14 | N/A | N/A | N/A |  |  |  |  | 2015-11-02 | 2016-05-02
MD | Talbot County, MD, Coastal PMR | 24041 |  | 10-03-0353S | Restudy | 1 | 5 | Bob Pierson | Molly Kaput | kdunn@dewberry.com | RAMPP | RAMPP | RAMPP | 2011-01-27 | 2012-11-14 | 2013-09-12 | 2016-01-19 | 2013-09-24 | 2015-06-11 | 2015-11-17 | 2015-07-13 | 2015-10-11 |  | 2016-01-20 | 2016-07-20 |  | 3/13/2014: Updated indexes uploaded to MSC. 2/15/2013: Revised prelim issued. Original CCO meeting held 5/4/2010.
MD | Washington County, MD | 24043 |  | 09-03-0014S | Restudy | 2 | 10 | Bob Pierson | Heather Davis-Jenkins | jason.sevanick@amecfw.com | MDE / USACE / AECOM | N/A | AMEC | N/A | N/A | 2010-09-30 | 2017-08-29 | 2015-06-25 | 2015-11-09 | 2016-10-18 | 2015-11-16 | 2016-02-13 |  | 2017-02-15 | 2017-08-15 |  | Will be processed as a LOMR 19-03-0284P. Old:Natural Valley concurrence letter has been sent
MD | Washington County, MD (Revised Prelim for 09-03-0014S) | 24043 |  | 14-03-3543S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | 2015-03-31 | N/A | N/A | N/A |  |  |  |  | 2015-12-16 | 2016-06-16
MD | Wicomico (Revised Prelim for 06-03-B496S) | 24045 |  | 13-03-2711S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2012-02-29 | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Funded in 2008 / Delay in receiving external data at project start
MD | Wicomico County, MD | 24045 |  | 06-03-B496S | Other BFE | 2 | 9 | Bob Pierson | Katie Lipiecki | jason.sevanick@amecfw.com | MDE / USACE | AMEC | AMEC | N/A | N/A | 2009-08-13 | N/A | 2012-04-04 | N/A | TBD | 2014-04-24 | 2014-07-23 |  | 2015-02-17 | 2015-08-17 |  | Funded in 2008
MD | Wicomico County, MD (Rev Prel 2 for 06-03-B496S) | 24045 |  | 12-03-0368S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
MD | Wicomico County, MD (Rev Prel for 06-03-B496S) | 24045 |  | 11-03-2016S |  |  |  | Bob Pierson | Katie Lipiecki |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
MD | Wicomico County, MD, Coastal PMR | 24045 |  | 10-03-0354S |  |  |  | Robin Danforth | Henry Chau |  |  |  |  | 2011-02-01 | 2013-02-21 | 2013-07-26 | 2016-01-21 | 2013-09-25 | 2014-07-17 |  |  |  |  | 2015-02-03 | 2015-08-03
MD | Worcester County, MD, Coastal Countywide | 24047 |  | 10-03-0355S | Restudy |  | 5 | Bob Pierson | Molly Kaput | jason.sevanick@amecfw.com | AMEC / RAMPP | AMEC / RAMPP | AMEC | 2011-02-02 | 2013-03-21 | 2013-07-19 | 2016-01-21 | 2013-09-25 | 2014-01-16 |  | 2014-03-14 | 2014-06-11 |  | 2015-01-16 | 2015-07-16
MD | Worcester County, MD, Coastal Countywide (Appeals Resolution for 10-03-0355S) | 24047 |  | 15-03-0128S |  |  |  | Bob Pierson | Molly Kaput |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | 10/16/2013: Appeals period deadline extended from 9/24/2013 to 11/5/2013. 8/14/2013: LFD date moved from 1/7/2014. 11/2012: On hold per Region, awaiting signature of PAL agreement from Sayre Borough.
PA | Adams County, PA | 42001 |  | 06-03-A636S |  |  | 34 | Nikki Roberts | [5 empty] | N/A | N/A | 2007-09-14 | N/A | N/A | N/A |  |  |  |  | 2008-08-18 | 2009-02-18 |  | Project incorporates Bucks County coastal study (12-03-0369S) and remapping of Rohm and Haas Levee.
PA | Adams County, PA - Monocacy Basin-Wide Study | 42001 | 02070009 | 14-03-1939S | Restudy |  | 17 | Lee Brancheau | Charlie Baker | Gjones@dewberry.com | USACE / STARR II | TBD | STARR II/ Compass | 2014-06-04 | 2017-06-27 | 2018-05-16 | N/A | 2018-06-25 | N/A |  | 2018-12-20 | 2019-03-19 | TBD | 2020-01-22 | 2020-07-22 |  | Processed via LOMR 20-03-1614P. Last LLPT date was 6/7/2017
PA | Allegheny County, PA | 42003 |  | 10-03-0271S | Restudy | 1 | 130 | Bob Pierson | Katie Lipiecki |  | RAMPP | N/A | RAMPP | TBD | 2012-12-06 | 2011-07-15 | 2012-12-06 | 2011-09-07 | TBD | 2012-08-08 | 2013-09-06 | 2013-12-04 |  | 2014-03-26 | 2014-09-26
PA | Allegheny County, PA (MM) | 42003 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2001-03-21 | 2001-09-21
PA | Allegheny County, PA (Rev Prel for 10-03-0271S) | 42003 |  | 12-03-2124S |  |  |  | Bob Pierson | Nicole Lick |  |  |  |  | N/A | N/A | 2012-08-08 | N/A | N/A | N/A |  |  |  |  | N/A | 2011-07-15
PA | Armstrong County, PA | 42005 |  | 06-03-A652S | Other BFE | 1 | 45 | Nikki Roberts | Katie Lipiecki | gjones@dewberry.com | GG3 | N/A | RAMPP | N/A | N/A | 2010-06-25 | N/A | 2010-08-24 | N/A | 2013-02-01 | 2014-12-25 | 2015-03-24 |  | 2015-08-17 | 2016-02-17
PA | Armstrong County, PA (Ford City LAMP) | 42005 |  | 17-03-1355S | Levee |  | 5 | Lee Brancheau | Bobby Cobelli | Craig.M.Thomas@usace.army.mil | USACE | TBD | TBD | N/A | 2019-09-10 | TBD | N/A | N/A | N/A
PA | Armstrong County, PA (Rev Prel for 06-03-A652S) | 42005 |  | 11-03-1435S |  |  |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | N/A | 2013-02-01 | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Jan-2016: Original appeal period from 8-8-2014 to 11-5-2014 // Apr-2015: Revised preliminary will be issued to address 1) a revised H&H analysis for the Callery Industrial Park along Breakneck Creek [Callery Bor] and 2) a revised flood hazard boundary for
PA | Beaver County, PA | 42007 |  | 06-03-A604S | Other BFE | 1 | 53 | Nikki Roberts | Richard Sobota | dsyriani@dewberry.com | GG3 | N/A | RAMPP | N/A | N/A | 2010-03-04 | N/A | 2010-05-04 | N/A | 2013-02-15 | 2014-08-05 | 2014-11-02 |  | 2015-02-17 | 2015-08-17
PA | Beaver County, PA (LAMP East Darlington and West Darlington Levees) | 42007 |  | 15-03-0289S | Levee |  | 2 | Lee Brancheau | Darlene Messina | mike.seering@aecom.com | USACE / Compass | TBD | TBD | N/A | 2018-02-15 | TBD | N/A | TBD | N/A |  | TBD | TBD |  | TBD | TBD
PA | Beaver County, PA (Rev Prel for 06-03-A604S) | 42007 |  | 11-03-1436S |  |  |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | N/A | 2013-02-15 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Bedford County, PA | 42009 |  | 07-03-0425S | Other BFE |  | 38 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2010-08-31 | N/A | N/A | N/A |  |  | 2011-05-10 |  | 2011-09-02 | 2012-03-02 |  | Delay in receiving external data at project start
PA | Berks County, PA | 42011 |  | 09-03-0185S | None |  | 76 | Bob Pierson | Katie Lipiecki |  | AMEC | N/A | AMEC | N/A | N/A | 2010-12-30 | N/A | 2011-02-24 | N/A |  |  |  |  | 2012-01-03 | 2012-07-03
PA | Berks County, PA (MM) | 42011 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2000-11-21 | 2001-05-21
PA | Berks County, PA (PAL Bernville Levee) | 42011 |  | 14-03-2049S | Levee |  | 3 | Bob Pierson | Sarah Wolfe | christine.estes@aecom.com | RAMPP | N/A | RAMPP/ Compass | N/A | N/A | 2015-06-26 | N/A | N/A | N/A |  | 2016-03-14 | 2016-06-25 |  | 2016-09-21 | 2017-03-21
PA | Blair County, PA | 42013 |  | 07-03-0651S | Restudy |  | 24 | Nikki Roberts | Marty Frengs |  | GG3 | N/A | GG3 | N/A | N/A | 2009-09-18 | N/A | 2009-11-18 | N/A |  |  | 2011-05-26 |  | 2011-09-02 | 2012-03-02
PA | Blair County, PA (Tyrone PMR) | 42013 |  | 16-03-0712S | PMR |  | 3 | Nikki Roberts | Heather Davis-Jenkins | christine.estes@aecom.com | USACE / Compass | TBD | Compass | N/A | N/A | 2016-04-07 | N/A | 2016-08-03 | N/A |  | 2017-02-03 | 2017-05-03 |  | 2017-11-02 | 2018-05-02 |  | Resilience meeting held Sep 2017
PA | Bradford County, PA | 42015 |  | 07-03-0427S | Restudy |  | 51 | Jon Janowicz | Katie Lipiecki |  | RAMPP | N/A | RAMPP | N/A | N/A | 2012-04-02 | N/A | 2012-05-03 | N/A |  | 2013-08-08 | 2013-11-05 |  | 2014-04-16 | 2014-10-16 |  | Delay in receiving external data at project start
PA | Bucks County, PA | 42017 |  | 11-03-1998S | Restudy |  | 22 | Bob Pierson | Sarah Wolfe | kdunn@dewberry.com | RAMPP | N/A | RAMPP | 2011-05-23 | 2014-11-20 | 2015-03-24 | TBD | 2015-06-30 | TBD |  | 2015-11-23 | 2016-02-20 |  | 2016-09-21 | 2017-03-21
PA | Bucks County, PA (Pre MM) | 42017 |  | MICS_30494 | [9 empty] | N/A | N/A | 1998-05-18 | N/A | N/A | N/A |  |  |  |  | N/A | 1999-05-18
PA | Bucks County, PA (Pre MM, East Branch Perkiomen Creek) | 42017 |  | MICS_11574 | [9 empty] | N/A | N/A | 2003-01-21 | N/A | N/A | N/A |  |  |  |  | 2003-10-02 | 2004-04-02
PA | Bucks County, PA (Rev Prel for 10-03-1995S) | 42017 |  | 12-03-2127S |  |  |  | Bob Pierson | Nicole Lick |  |  |  |  | N/A | N/A | 2012-07-26 | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Jan-2016: While the project only impacts ~3 communities, FPM&I intends to require that all communities in the county update their ordinances
PA | Bucks County, PA, Coastal PMR | 42017 |  | 12-03-0369S |  |  |  | Bob Pierson | [5 empty] | 2012-02-09 | N/A | 2015-03-24 | 2015-07-09 | N/A | N/A |  |  |  |  | 2016-04-20 | 2016-10-20
PA | Bucks County, PA, Countywide Rev | 42017 |  | 10-03-1995S |  | 1 |  | Bob Pierson | Nicole Lick |  |  |  |  | N/A | N/A | 2010-12-30 | N/A | 2011-02-23 | N/A | 2012-07-26 |  |  |  | 2014-09-16 | 2015-03-16
PA | Butler County, PA | 42019 |  | 06-03-A623S | Restudy | 2 | 57 | Nikki Roberts | Darlene Messina | christine.estes@aecom.com | GG3 | N/A | RAMPP/ Compass | N/A | N/A | 2010-03-12 | N/A | 2013-09-05 | N/A | 2015-10-15 | 2017-07-07 | 2017-10-04 |  | 2018-02-02 | 2018-08-02
PA | Butler County, PA (Rev Prel for 06-03-A623S) | 42019 |  | 11-03-1437S |  |  |  | Nikki Roberts | Henry Chau |  |  |  |  | N/A | N/A | 2013-06-26 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Butler County, PA (Rev Prel for 06-03-A623S) | 42019 |  | 15-03-1930S | Rev Prel |  |  | Nikki Roberts | Darlene Messina | dsyriani@dewberry.com | RAMPP | N/A | RAMPP | N/A | N/A | 2015-10-15 | N/A | N/A | N/A |  | N/A | N/A |  | 2016-03-16 | 2016-09-16
PA | Cambria County, PA | 42021 |  | 07-03-0289S | Restudy |  | 65 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-09-30 | N/A | 2009-12-03 | N/A |  |  | 2011-02-09 |  | 2011-12-19 | 2012-06-19
PA | Cameron County, PA | 42023 |  | 07-03-0428S | Restudy |  | 7 | Nikki Roberts | Marty Frengs |  | GG3 | N/A | GG3 | N/A | N/A | 2009-12-30 | N/A | 2010-04-30 | N/A |  |  | 2010-10-14 |  | 2011-01-04 | 2011-07-04
PA | Carbon County, PA (MM) | 42025 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2001-12-03 | 2002-06-03
PA | Centre County, PA | 42027 |  | MICS_30226 |  |  | 36 | Nikki Roberts | [5 empty] | N/A | N/A | 2008-01-15 | N/A | N/A | N/A |  |  |  |  | 2008-11-04 | 2009-05-04 |  | Delay in receiving external data at project start
PA | Centre County, PA, PMR (PAL) | 42027 |  | 11-03-0521S |  |  |  | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2013-08-16 | N/A | N/A | N/A |  |  |  |  | 2014-07-16 | 2015-01-16
PA | Chester County, PA | 42029 |  | MICS_30228 | [9 empty] | N/A | N/A | 2005-08-01 | N/A | N/A | N/A |  |  |  |  | 2006-03-29 | 2006-09-29
PA | Chester County, PA - Brandywine-Christina Basin-Wide Study | 42029 |  | 11-03-2202S | Restudy |  | 70 | Nikki Roberts | Sarah Wolfe | mike.seering@aecom.com | RAMPP | TBD | RAMPP | 2011-11-09 | 2015-09-18 | 2015-12-09 | 2017-09-28 | 2016-01-12 | 2017-07-20 |  | 2016-06-01 | 2016-08-29 |  | 2017-03-29 | 2017-09-29 |  | Effective in Jul-2017 with no resilience meeting required. Jun-2014: On Hold in MIP for Revised Prelim. First appeals period ended 4/5/2011; second appeals period required for revised map. Revised prelim issued 6/27/2014. First CCO held 3/26/2010.
PA | Clarion County, PA | 42031 |  | 07-03-0290S | Other BFE |  | 34 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2010-03-31 | N/A | 2010-06-23 | N/A |  |  |  |  | 2011-06-02 | 2011-12-02
PA | Clarion County, PA, PMR | 42031 |  | 11-03-1438S |  |  |  | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2012-11-29 | N/A | 2013-02-06 | N/A |  |  |  |  | 2014-06-09 | 2014-12-09 |  | Delay in receiving external data at project start
PA | Clearfield County, PA | 42033 |  | 07-03-0429S | Restudy |  | 51 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-09-25 | N/A | 2009-11-17 | N/A |  |  | 2010-10-26 |  | 2011-05-02 | 2011-11-02
PA | Clinton County | 42035 |  | MICS_30233 | [9 empty] | N/A | N/A | 2007-03-05 | N/A | N/A | N/A |  |  |  |  | 2008-03-26 | 2008-09-26 |  | Funded in 2008 / Delay in receiving external data at project start
PA | Clinton County, PA (PAL Lock Haven Levee) | 42035 |  | 14-03-2031S | Levee |  | 29 | Nikki Roberts | Sarah Wolfe | kdunn@dewberry.com | RAMPP | TBD | TBD | N/A | N/A | 2015-06-12 | N/A | N/A | N/A |  | N/A | N/A |  | 2015-12-16 | 2016-06-16 |  | 3/13/2014: Updated indexes uploaded to MSC. Revised prelim issued 3/1/2013. First appeals period ended 11/6/2011; second appeals period req'd for revised map. Original CCO meeting held 12/8/2010.
PA | Columbia County, PA | 42037 |  | MICS_11316 | [9 empty] | N/A | N/A | 2005-12-21 | N/A | N/A | N/A |  |  |  |  | 2008-02-19 | 2008-08-19
PA | Crawford County, PA | 42039 |  | 07-03-0291S | Restudy |  | 53 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-10-23 | N/A | 2010-01-28 | N/A |  |  | 2011-02-09 |  | 2012-02-16 | 2012-08-16 |  | Funded in 2008 / Delay in receiving external data at project start
PA | Cumberland County, PA | 42041 |  | 06-03-A613S |  |  | 34 | Nikki Roberts | [5 empty] | N/A | N/A | 2007-09-28 | N/A | N/A | N/A |  |  |  |  | 2008-09-16 | 2009-03-16
PA | Dauphin County, PA | 42043 |  | MICS_30225 | Restudy |  | 40 | Nikki Roberts | Nicole Lick |  | USACE | GG3 | GG3 | N/A | N/A | 2009-10-30 | N/A | 2009-01-12 | N/A |  | 2010-07-01 | 2010-09-28 |  | 2012-02-02 | 2012-08-02
PA | Delaware County, PA | 42045 |  | MICS_11978 | [9 empty] | N/A | N/A | 2005-08-01 | N/A | N/A | N/A |  |  |  |  | 2005-12-02 | 2006-05-31 |  | Delay in receiving external data at project start
PA | Delaware County, PA - Brandywine-Christina Basin-Wide Study | 42045 |  | 11-03-2202S | Restudy |  | 3 | Nikki Roberts | Sarah Wolfe | mike.seering@aecom.com | RAMPP | TBD | RAMPP | 2011-11-09 | 2015-09-18 | 2015-10-29 | TBD | 2016-01-12 | N/A |  | 2016-06-01 | 2016-08-29 |  | 2017-01-05 | 2017-07-05
PA | Delaware County, PA (Countywide Revision) | 42045 |  | 08-03-0199S | PAL/Restudy |  | 49 | Bob Pierson | Henry Chau |  | AMEC | N/A | AMEC | N/A | N/A | 2008-11-26 | N/A | N/A | N/A |  |  |  |  | 2009-05-18 | 2009-11-18 |  | LAMP plan is being developed
PA | Delaware County, PA (LAMP Chester Levee) | 42045 |  | 14-03-2024S | Levee |  | 2 | Bob Pierson | Sarah Wolfe | christine.estes@aecom.com | RAMPP | TBD | Compass | N/A | N/A | 2016-03-04 | TBD | TBD | TBD |  | 2016-10-05 | 2017-01-05 |  | 2017-05-03 | 2017-11-03 |  | Open House scheduled for 12/10/19 *Original revised prelim date is 8/31/2017
PA | Elk County, PA | 42047 |  | 07-03-0292S | Other BFE |  | 13 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2010-04-16 | N/A | 2010-06-16 | N/A |  |  |  |  | 2011-07-18 | 2012-01-18
PA | Erie County, PA | 42049 |  | 07-03-0293S | Restudy |  | 42 | Nikki Roberts | Henry Chau |  | GG3 | N/A | GG3 | N/A | N/A | 2009-09-30 | N/A | 2009-12-17 | N/A |  | 2012-12-21 | 2013-03-20 |  | 2013-08-19 | 2014-02-19
PA | Erie County, PA, Coastal PMR | 42049 |  | 13-03-0299S | Restudy |  | 10 | Bob Pierson | Charlie Baker | kdunn@dewberry.com | RAMPP | N/A | RAMPP | 2012-07-18 | 2015-09-14 | 2015-12-18 | 2017-07-20 | 2016-03-02 | TBD |  | 2016-05-20 | 2016-08-17 |  | 2016-12-07 | 2017-06-07
PA | Fayette County, PA | 42051 |  | 06-03-A625S | Restudy | 1 | 42 | Nikki Roberts | Darlene Messina | christine.estes@aecom.com | GG3 | N/A | RAMPP/ Compass | N/A | N/A | 2009-11-24 | N/A | 2017-04-26 | N/A | 2014-06-27 | 2015-04-20 | 2015-07-19 |  | 2017-01-18 | 2017-07-18
PA | Fayette County, PA (Rev Prel for 06-03-A625S) | 42051 |  | 11-03-1439S |  |  |  | Nikki Roberts | Nikki Roberts |  |  |  |  | N/A | N/A | 2014-06-27 | N/A | N/A | N/A |  |  |  |  | 2016-06-22 | 2016-12-22 |  | May-2015: Includes revised preliminary (15-03-1367S) issued 4/24/2015. // Mar-2015: Addressing appeal; scheduled LFD & effective dates are correct; the county did not respond to repeated attempts to schedule the Resilience Meeting
PA | Forest County, PA | 42053 |  | 07-03-0294S | None |  | 9 | Nikki Roberts | Richard Sobota |  | GG3 | N/A | GG3 | N/A | N/A | 2009-11-30 | N/A | 2010-02-11 | N/A |  |  |  |  | 2010-05-26 | 2010-11-26
PA | Franklin County, PA | 42055 |  | 07-03-0430S | Other BFE |  | 23 | Nikki Roberts | Richard Sobota |  | GG3 | N/A | GG3 | N/A | N/A | 2010-06-30 | N/A | 2010-08-25 | N/A |  |  |  |  | 2011-07-18 | 2012-01-18
PA | Fulton County, PA | 42057 |  | 07-03-0431S | None |  | 13 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2010-04-30 | N/A | 2010-05-27 | N/A |  |  |  |  | 2010-08-18 | 2011-02-18
PA | Greene County, PA | 42059 |  | 06-03-A631S | None | 1 | 26 | Nikki Roberts | Mari Radford | dsyriani@dewberry.com | GG3 / Baker (Prel) | N/A | RAMPP | N/A | N/A | 2010-09-30 | N/A | 2013-04-10 | N/A | 2013-03-01 | 2014-10-17 | 2015-01-14 |  | 2015-04-16 | 2015-10-16
PA | Greene County, PA (Rev Prel for 06-03-A631S) | 42059 |  | 11-03-1440S |  |  |  | Nikki Roberts | Mari Radford |  |  |  |  | N/A | N/A | 2013-03-01 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Huntingdon County, PA | 42061 |  | 07-03-0432S | Other BFE |  | 50 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2010-10-29 | N/A | 2010-01-12 | N/A |  |  | 2011-06-01 |  | 2012-04-16 | 2012-10-16
PA | Huntingdon County, PA (Tyrone PMR) | 42061 |  | 16-03-0713S | PMR |  | 5 | Nikki Roberts | Heather Davis-Jenkins | christine.estes@aecom.com | USACE / Compass | TBD | Compass | N/A | N/A | 2016-04-07 | N/A | 2016-08-03 | N/A |  | 2017-02-03 | 2017-05-03 |  | 2017-11-02 | 2018-05-02
PA | Indiana County, PA | 42063 |  | 07-03-0295S | Restudy |  | 39 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-10-30 | N/A | 2010-01-26 | N/A |  |  |  |  | 2011-10-03 | 2012-04-03
PA | Jefferson County, PA | 42065 |  | 07-03-0296S | Other BFE |  | 34 | Nikki Roberts | Henry Chau |  | GG3 | N/A | GG3 | N/A | N/A | 2010-04-30 | N/A | 2010-06-15 | N/A |  |  |  |  | 2011-09-15 | 2012-03-15
PA | Juniata County, PA | 42067 |  | 06-03-B511S | None |  | 17 | Nikki Roberts | Mari Radford |  | SEDA-COG / Baker | Baker | RAMPP | N/A | N/A | 2010-08-17 | N/A | 2010-09-29 | N/A |  |  | 2012-01-09 |  | 2012-04-02 | 2012-10-02
PA | Juniata County, PA - Lower Susquehanna-Penns Basin-Wide Study | 42067 | 02050301 | 15-03-0140S | Zone A |  | 1 | Nikki Roberts | Charlie Baker | errol.dufour@stantec.com | RAMPP / STARR II | TBD | STARR II/ Compass | 2015-04-02 | 2017-08-18 | 2018-09-28 | N/A | 2018-11-19 |  |  | 2019-06-25 | 2019-09-23 |  | 2020-08-26 | 2021-02-26
PA | Lackawanna County - (LAMP for Seclusion Areas Mayfield) | 42069 |  | 17-03-0973S | Levee |  | 18 | Lee Brancheau | Julius Lockhart | mike.seering@aecom.com | Compass | TBD | STARR II | N/A | 2018-12-11 | TBD | N/A | N/A | N/A |  | TBD | TBD | TBD | TBD | TBD
PA | Lackawanna County, PA | 42069 |  | 07-03-0433S | Restudy, Levee | 1 | 40 | Nikki Roberts | Sarah Wolfe | christine.estes@aecom.com | GG3 | N/A | Compass | N/A | 2016-08-25 | 2011-07-29 |  | 2017-11-02 |  | 2019-06-07 | 2018-04-25 | 2018-07-23 | 2019-12-10 | 2020-02-05 | 2020-08-05 |  | Jan-2016: Original CCO meeting held 5-13-2010 // Nov 2015: Prior appeal period held 11/30/2010-2/27/2011. // On-hold for revised prelim. Area behind levee to be mapped using natural valley. Delay in receiving external data at project start.
PA | Lackawanna County, PA (Revised Prelim for 07-03-0433S) | 42069 |  | 15-03-0164S | Rev Prel |  | 0 | Nikki Roberts | Sarah Wolfe | christine.estes@aecom.com | Compass | N/A | Compass | N/A | N/A | 2017-08-31 | N/A | 2017-11-02 | 2017-11-02 |  | N/A | N/A |  | N/A | N/A |  | On-hold
PA | Lackawaxen Basin-Wide Study (Discovery) |  | 02040103 | 16-03-2420S | TBD |  | 0 | Lee Brancheau |  | Toni.Pignatelli@mbakerintl.com | RAP / Compass | TBD | TBD | 2016-09-13 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | 6/13/2013: will not make 10/2/2013 LFD date; mapping partner has requested new LFD date. First appeals period ended 1/4/2011.
PA | Lancaster County | 42071 |  | MICS_30231 | [9 empty] | N/A | N/A | 2004-01-22 | N/A | N/A | N/A |  |  |  |  | N/A | 2005-04-19
PA | Lancaster County, PA - Lower Susquehanna Basin-Wide Study | 42071 |  | 11-03-1991S | Restudy | 1 | 60 | Lee Brancheau | Sarah Wolfe | kdunn@dewberry.com | RAMPP | N/A | RAMPP | 2011-06-28 | 2013-08-06 | 2013-10-31 | N/A | 2014-01-07 | N/A | 2014-04-30 | 2014-09-11 | 2014-12-09 |  | 2015-10-05 | 2016-04-05
PA | Lancaster County, PA (Revised Prelim for 11-03-1991S) | 42071 |  | 15-03-1367S |  |  |  | Lee Brancheau | Katie Lipiecki |  |  |  |  | N/A | N/A | 2015-04-24 | N/A | N/A | N/A |  |  |  |  | 2017-12-20 | 2018-06-20 |  | Apr-2014: On Hold in MIP for Revised Prelim. 9/6/14: Will require 2nd Appeals Period. First appeals period ended 7/25/2011. 3/5/2013. Cheltenham Levee mapped using seclusion method.
PA | Lawrence County, PA | 42073 |  | 07-03-0297S | Restudy |  | 27 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-11-20 | N/A | 2010-01-27 | N/A |  |  |  |  | 2011-07-18 | 2012-01-18
PA | Lebanon County, PA | 42075 |  | 06-03-A649S | Other BFE |  | 26 | Nikki Roberts | Nicole Lick |  | USACE | N/A | Dewberry | N/A | N/A | 2010-11-05 | N/A | 2010-12-17 | N/A |  |  |  |  | 2011-12-05 | 2012-06-05
PA | Lebanon County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 42075 | 02050305 | 15-03-0142S | Restudy, Zone A |  | 26 | Lee Brancheau | Charlie Baker | brett.holthaus@atkinsglobal.com | RAMPP / STARR II | TBD | STARR II/ Compass | 2015-04-07 | 2018-03-12 | 2018-08-20 | N/A | 2018-09-17 | N/A |  | 2019-04-10 | 2019-07-09 | TBD | 2020-01-08 | 2020-07-08
PA | Lehigh Basin-Wide Study (Discovery) |  | 02040106 | 16-03-2422S | TBD |  | 0 | Nikki Roberts | Darlene Messina | Toni.Pignatelli@mbakerintl.com | RAP / Compass | TBD | TBD | 2016-09-27 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
PA | Lehigh County, PA | 42077 |  | MICS_11598 | [9 empty] | N/A | N/A | 2002-10-07 | N/A | N/A | N/A |  |  |  |  | 2003-01-02 | 2004-07-16
PA | Lehigh County, PA, PMR (PAL) | 42077 |  | 11-03-0164S |  |  |  | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2013-09-30 | N/A | N/A | N/A |  |  |  |  | 2014-09-16 | 2015-03-16 |  | 8/26/2013: Revised prelim to address appeals. 5/2013: Project being reactivated. 1/16/2013: On-hold - awaiting funding for appeals/comments.
PA | Luzerne County, PA | 42079 |  | 08-03-0543S | Restudy |  | 76 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-10-30 | N/A | 2010-02-24 | N/A |  |  | 2011-01-19 |  | 2012-05-02 | 2012-11-02
PA | Lycoming County, PA | 42081 |  | 11-03-1993S | Restudy |  | 52 | Cynthia McCoy | Mari Radford | fmcjunkin@lyco.org | Lycoming | N/A | Lycoming | 2011-12-07 | 2013-12-10 | 2014-11-12 | 2016-03-23 | 2015-01-14 | 2013-01-29 |  | 2015-06-05 | 2015-09-03 |  | 2015-12-02 | 2016-06-02
PA | Lycoming County, PA | 42081 |  | MICS_10079 |  |  | 52 | [6 empty] | N/A | N/A | 2002-09-13 | N/A | N/A | N/A |  |  |  |  | 2003-09-16 | 2004-03-16
PA | Lycoming County, PA, PMR (PAL) | 42081 |  | 11-03-0165S | PAL/Restudy |  | 9 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2013-02-06 | N/A | N/A | N/A |  |  |  |  | 2013-08-05 | 2014-08-18
PA | Manheim Bor, PA, PMR (Unnamed Tributary to Little Conestoga) | 42071 |  | MICS_10601 |  |  | 2 | [6 empty] | N/A | N/A | 2004-04-19 | N/A | N/A | N/A |  |  |  |  | 2004-10-19 | 2005-04-19
PA | McKean County, PA | 42083 |  | 07-03-0298S | Other BFE, Levee | 1 | 22 | Nikki Roberts | Nicole Lick | kdunn@dewberry.com | Dewberry | N/A | Dewberry | N/A | N/A | 2010-03-31 | N/A | 2015-08-26 | N/A | 2015-05-22 | 2015-11-03 | 2016-01-31 |  | 2016-06-22 | 2016-12-22 |  | Resiliency meeting held on 1/3/2019. Only funded through workmap for Zone A studies
PA | McKean County, PA (Revised Prelim for 07-03-0298S) | 42083 |  | 14-03-1259S | Rev Prel |  |  | Nikki Roberts |  | kdunn@dewberry.com | RAMPP | N/A | N/A | N/A | N/A | 2015-05-22 | N/A | N/A | N/A |  | N/A | N/A |  | 2016-12-21 | 2017-06-21
PA | Mercer County, PA | 42085 |  | 07-03-0299S | N/A |  | 48 | Nikki Roberts | Nicole Lick |  |  |  | GG3 | N/A | N/A | 2009-12-18 | N/A | 2010-04-29 | N/A |  | 2013-05-15 | 2013-08-12 |  | 2013-12-09 | 2014-06-09 |  | Apr-2015: Comments on maps were received and addressed; final maps will reflect updates
PA | Mifflin County, PA | 42087 |  | MICS_30232 | [9 empty] | N/A | N/A | 2005-05-19 | N/A | N/A | N/A |  |  |  |  | 2006-02-16 | 2006-08-16
PA | Monroe County, PA | 42089 |  | MICS_11363 | Restudy |  | 20 | Nikki Roberts | Katie Lipiecki |  | USACE | TBD | Dewberry | N/A | N/A | 2011-09-30 | N/A | 2011-11-14 | N/A |  | 2012-02-15 | 2012-05-14 |  | 2012-11-02 | 2013-05-02 |  | Delay in receiving external data at project start
PA | Montgomery County, PA | 42091 |  | 07-03-1127S | Other BFE, Levee | 1 | 62 | Bob Pierson | Sarah Wolfe | catanianc@cdmsmith.com | AMEC | N/A | AMEC/Compass | N/A | N/A | 2010-07-30 | N/A | 2010-10-27 | N/A | 2014-01-09 | 2014-10-26 | 2015-01-23 |  | 2015-09-02 | 2016-03-02 |  | Will be processed as a LOMR 18-03-2057P. Old: Congressional correspondence in progress
PA | Montgomery County, PA (MM) | 42091 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1996-06-19 | 1996-12-19
PA | Montgomery County, PA (Rev Prel for 07-03-1127S) | 42091 |  | 14-03-0732S |  |  |  | Jon Janowicz | Nicole Lick |  |  |  |  | N/A | N/A | 2014-01-09 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Montgomery County, PA (Rev Prel for 07-03-1127S) | 42091 |  | 14-03-1881S |  |  |  | Bob Pierson | Katie Lipiecki |  |  |  |  | N/A | N/A | 2014-04-04 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Montgomery County, PA, PMR (PAL) | 42091 |  | 11-03-0522S |  |  |  | Bob Pierson | Nicole Lick |  |  |  |  | N/A | N/A | 2015-12-31 | N/A | N/A | N/A |  |  |  |  | 2014-12-16 | 2015-06-16
PA | Montour County, PA | 42093 |  | MICS_11319 | [9 empty] | N/A | N/A | 2005-11-15 | N/A | N/A | N/A |  |  |  |  | 2007-11-16 | 2008-05-16 |  | 11/2012: Will require 2nd appeals period. 1st Appeal Period ended 4/23/2012. Revised prelim issued 9/30/2011.
PA | Montour County, PA - Upper Susquehanna-Lackawanna basin-wide | 42093 | 02050107 | 15-03-0227S | Restudy |  | 8 | Hani Rimawi | Bobby Cobelli | matt.witosky@stantec.com | USACE / STARR II | N/A | STARR II/ Compass | 2015-04-01 | 2017-08-17 | 2019-03-08 | N/A | 2019-07-10 | N/A | 2020-10-30 | 2021-07-15 | 2021-10-13 |  | 2022-02-16 | 2022-08-16 |  | Original appeals period from 4/21/21-7/20/21 & 5/19/21-8/17/21. Multiple appeals periods due to newspaper failure to publish 2nd publication. Will need a second appeal period. Revised preliminary planned.
PA | Northampton County, PA | 42095 |  | 10-03-0359S | Restudy | 1 | 38 | Bob Pierson | Katie Lipiecki |  | RAMPP | RAMPP | RAMPP | N/A | N/A | 2011-12-14 | N/A | 2012-02-21 | N/A | 2013-09-06 | 2012-08-16 | 2012-11-13 |  | 2014-01-16 | 2014-07-16
PA | Northampton County, PA (MM) | 42095 |  | MICS_12597 | [9 empty] | N/A | N/A | 2000-04-06 | N/A | N/A | N/A |  |  |  |  | N/A | 2001-04-06
PA | Northampton County, PA (Revised Prelim for 10-03-0359S) | 42095 |  | 13-03-2471S | [9 empty] | N/A | N/A | 2013-09-06 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Northumberland County, PA | 42097 |  | MICS_30224 | [9 empty] | N/A | N/A | 2006-02-14 | N/A | N/A | N/A |  |  |  |  | 2008-01-16 | 2008-07-16
PA | Northumberland County, PA (PAL Sunbury Levee) | 42097 |  | 14-03-2032S | Levee |  | 2 | Nikki Roberts | Molly Kaput | kdunn@dewberry.com | RAMPP | TBD | TBD | N/A | N/A | 2015-05-29 | N/A | N/A | N/A |  | 2015-10-23 | 2016-01-26 |  | 2016-03-16 | 2016-09-16 |  | 5/15/2014: Project to move forward using seclusion around levees; no new appeals pd. Needed. 6/2012: Project on hold due to expired POP. Delay in receiving external data at project start.
PA | Perry County, PA | 42099 |  | 06-03-A655S | Other BFE |  | 30 | Nikki Roberts | Marty Frengs |  | GG3 | N/A | Baker | N/A | N/A | 2007-12-06 | N/A | N/A | N/A |  | 2008-02-15 | 2008-05-28 |  | 2008-12-16 | 2009-06-16
PA | Perry County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 42099 | 02050305 | 15-03-0142S | Restudy, Zone A |  | 25 | Lee Brancheau | Heather Davis-Jenkins | brett.holthaus@atkinsglobal.com | RAMPP / STARR II | TBD | STARR II | 2015-04-07 | 2016-09-29 | 2017-08-18 |  | 2017-09-25 |  |  | 2018-05-03 | 2018-07-31 | 2019-01-03 | 2018-12-20 | 2019-06-20
PA | Philadelphia County, PA | 42101 |  | 06-03-B789S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2005-09-26 | N/A | N/A | N/A |  |  |  |  | 2006-07-17 | 2007-01-17
PA | Philadelphia, PA, Coastal PMR | 42101 |  | 12-03-0373S | Restudy |  | 1 | Bob Pierson | Sarah Wolfe | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-02-08 | 2013-12-11 | 2014-02-20 | TBD | 2014-06-06 | 2015-07-07 |  | 2014-10-31 | 2015-01-28 |  | 2015-05-18 | 2015-11-18
PA | Pike County, PA (MM) | 42103 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2000-04-06 | 2000-10-06
PA | Potter County, PA | 42105 |  | 07-03-0434S | PAL/Other BFE |  | 31 | Tiffany Keane | Marty Frengs |  | Dewberry | N/A | Dewberry | N/A | N/A | 2010-01-29 | N/A | 2010-05-14 | N/A |  | 2010-06-16 | 2010-09-13 |  | 2011-01-18 | 2011-07-18 |  | 12/14/2012: LFD Dropped - won't make 3/27/2013. Delay in receiving external data at project start.
PA | Potter County, PA (LAMP Pine Creek Levees) | 42105 |  | 15-03-0304S | Levee |  | 1 | Lee Brancheau | Darlene Messina | mike.seering@aecom.com | USACE / Compass | TBD | TBD | N/A | 2018-02-12 | TBD | TBD | TBD |  |  | TBD | TBD |  | TBD | TBD |  | Nov-2015: Initial appeal period held 2-10-2011 through 5-10-2011, with initial CCO meeting held 8/15/2011. // Project on hold in MIP for revised prelim. Area behind levee to be mapped using natural valley. Delay in receiving external data at project start
PA | Raystown Branch, Juniata River - Updated Detailed Study |  |  | 20-03-0001S | Restudy |  | N/A | Andrew Jackson | Charlie Baker | TBD | TBD | TBD | TBD | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A |  | On-hold
PA | Schuylkill County, PA | 42107 |  | 06-03-B514S |  |  |  | Nikki Roberts | Mari Radford |  |  |  |  | N/A | N/A | 2010-06-30 | N/A | 2010-09-22 | N/A |  |  |  |  | 2014-05-19 | 2014-11-19
PA | Schuylkill County, PA - Schuylkill Basin-Wide Study | 42107 | 02040203 | 11-03-2055S | Zone A |  | 67 | Nikki Roberts | Charlie Baker | Gjones@dewberry.com | RAMPP / STARR II | TBD | STARR II/ Compass | 2015-04-07 | 2017-07-10 | 2018-08-24 | N/A | 2018-09-17 | N/A | 2018-12-17 | 2019-08-15 | 2019-11-13 | TBD | 2020-11-18 | 2021-05-18
PA | Snyder County, PA | 42109 |  | MICS_11321 | [9 empty] | N/A | N/A | 2006-01-23 | N/A | N/A | N/A |  |  |  |  | 2007-05-16 | 2007-11-16 |  | Apr-2015: Various comments on maps were received and addressed; final maps will reflect updates. 6/13/2014: Approval received to proceed with mapping using Natural Valley analysis. Pursuing re-mapping using natural valley. First appeals period ended 6/15/
PA | Snyder County, PA - Lower Susquehanna-Penns Basin-Wide Study | 42109 | 02050301 | 15-03-0140S | Restudy, Zone A |  | 8 | Nikki Roberts | Charlie Baker | errol.dufour@stantec.com | RAMPP / STARR II | N/A | STARR II/ Compass | 2015-04-02 | 2017-08-18 | 2019-03-29 | N/A | 2019-07-09 |  |  | 2020-02-28 | 2020-05-28 |  | 2021-02-24 | 2021-08-24
PA | Somerset County, PA | 42111 |  | 07-03-0300S | Restudy |  | 51 | Nikki Roberts | Henry Chau |  | GG3 | N/A | GG3 | N/A | N/A | 2009-09-30 | N/A | 2009-12-15 | N/A |  |  | 2011-03-05 |  | 2012-03-19 | 2012-09-19
PA | Somerset County, PA (LAMP Elk Lick Levee) | 42111 |  | 19-03-0464P | Levee |  | 3 | Lee Brancheau | Julius Lockhart | mike.seering@aecom.com | USACE / Compass | TBD | TBD | N/A | 2018-04-30 | N/A | N/A |  | N/A | N/A | N/A | N/A |  | 2019-10-07
PA | Sullivan County, PA | 42113 |  | 07-03-0435S | Restudy | 1 | 13 | Jon Janowicz | Nicole Lick |  | RAMPP | N/A | RAMPP | N/A | N/A | 2010-09-29 | N/A | 2010-12-15 | N/A | 2011-09-30 | 2013-02-27 | 2013-05-27 |  | 2013-09-03 | 2014-03-03
PA | Sullivan County, PA (Rev Prel for 07-03-0435S) | 42113 |  | 11-03-1443S |  |  |  | Tiffany Keane | Nicole Lick |  |  |  |  | N/A | N/A | 2011-09-30 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Susquehanna County, PA | 42115 |  | 07-03-0436S | Restudy |  | 40 | Jon Janowicz | Katie Lipiecki |  | RAMPP | N/A | RAMPP | N/A | N/A | 2011-08-31 | N/A | 2011-09-26 | N/A |  | 2012-02-13 | 2012-05-12 |  | 2012-10-02 | 2013-04-02
PA | Tinicum Twp, PA, PMR (Delaware River) | 42017 |  | MICS_10581 |  |  | 1 | [6 empty] | N/A | N/A | 2002-08-18 | N/A | N/A | N/A |  |  |  |  | 2003-02-18 | 2003-08-18
PA | Tioga County, PA | 42117 |  | 07-03-0437S | Other BFE, Levee | 1 | 40 | Nikki Roberts | Nicole Lick | kdunn@dewberry.com | Dewberry | N/A | Dewberry | N/A | N/A | 2010-05-28 | N/A | 2010-06-29 | N/A | 2014-07-15 | 2010-10-05 | 2011-01-02 |  | 2015-01-16 | 2015-07-16
PA | Tioga County, PA (Revised Prelim for 07-03-0437S) | 42117 |  | 14-03-2353S |  |  |  | Nikki Roberts | Katie Lipiecki |  |  |  |  | N/A | N/A | 2014-07-15 | N/A | N/A | N/A |  |  |  |  | 2015-01-16 | 2015-07-16
PA | Union County, PA | 42119 |  | MICS_11322 | [9 empty] | N/A | N/A | 2006-01-31 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
PA | Union County, PA - Lower Susquehanna-Penns Basin-Wide Study | 42119 | 02050301 | 15-03-0140S | Zone A |  | 2 | Nikki Roberts | Charlie Baker | errol.dufour@stantec.com | RAMPP / STARR II | TBD | STARR II/ Compass | 2015-04-02 | 2017-08-18 | 2018-09-28 | N/A | 2018-11-19 |  |  | 2019-06-25 | 2019-09-23 |  | 2020-08-26 | 2021-02-26 |  | Required new A Zones
PA | Union County, PA, PMR | 42119 |  | 09-03-0065S | None |  | 4 | Nikki Roberts | Henry Chau |  | SEDA-COG | Baker | Baker | N/A | N/A | 2008-11-26 | N/A | N/A | N/A |  |  |  |  | 2009-04-16 | 2009-10-16 |  | Location of several levee 65.10 packages that were scanned and archived on the MIP
PA | Venango County, PA | 42121 |  | 07-03-0301S | Other BFE |  | 31 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2010-03-31 | N/A | 2010-06-23 | N/A |  | 2013-01-04 | 2013-04-03 |  | 2013-07-16 | 2014-01-16 |  | Will be processed as a LOMR ; Case number 19-03-0464P. Original case no. is 15-03-0306S
PA | Warren County, PA | 42123 |  | 07-03-0302S | Restudy, Zone A | 2 | 27 | Nikki Roberts | Sarah Wolfe | kdunn@dewberry.com | Dewberry | N/A | STARR II | N/A | N/A | 2010-06-11 | N/A | 2015-08-27 | N/A | 2016-05-09 | 2015-12-14 | 2016-03-13 |  | 2016-09-21 | 2017-03-21
PA | Warren County, PA (Revised Prelim for 07-03-0302S) | 42123 |  | 16-03-1645S |  |  |  | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2016-05-31 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Warren County, PA (Revised Prelim for 07-03-0302S) | 42123 |  | 14-03-1282S | Rev Prel |  |  | Nikki Roberts |  | kdunn@dewberry.com | RAMPP | N/A | N/A | N/A | N/A | 2015-06-12 | N/A | N/A | N/A |  | N/A | N/A |  | 2016-09-21 | 2017-03-21 |  | Town of Scottsville lies in 2 counties - Albemarle and Fluvanna. Processing separate LOMR to address corporate limit mismatch in Fluvanna County, VA
PA | Washington County, PA | 42125 |  | 06-03-A634S | Restudy | 1 | 66 | Nikki Roberts | Nikki Roberts | dsyriani@dewberry.com | GG3 | N/A | RAMPP | N/A | N/A | 2009-11-19 | N/A | 2010-03-25 | N/A | 2014-06-27 | 2014-10-30 | 2015-01-27 |  | 2015-03-30 | 2015-09-30
PA | Washington County, PA (Rev Prel for 06-03-A634S) | 42125 |  | 11-03-1441S |  |  |  | Nikki Roberts | Nikki Roberts |  |  |  |  | N/A | N/A | 2013-10-25 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | Washington County, PA (Revised Prelim for 06-03-A634S) | 42125 |  | 14-03-2645S |  |  |  | Nikki Roberts | Katie Lipiecki |  |  |  |  | N/A | N/A | 2014-06-27 | N/A | N/A | N/A |  |  |  |  | 2017-12-20 | 2018-06-20 |  | BFE changes in City of Covington
PA | Wayne County, PA | 42127 |  | 05-03-A432S | Restudy |  | 28 | Nikki Roberts | Nicole Lick |  | USACE | Baker | RAMPP | N/A | N/A | 2011-06-01 | N/A | 2010-06-30 | N/A |  | 2012-01-17 | 2012-04-15 |  | 2012-11-16 | 2013-05-16 |  | 6/27/2019 - 9/27/2019 dates of original appeals period
PA | Wayne County, PA (Prompton PMR) | 42127 |  | 16-03-2419S | Restudy, Zone A |  | 4 | Lee Brancheau | Heather Davis-Jenkins | christine.estes@aecom.com | USACE/ Compass | N/A | Compass | N/A | 2017-02-23 | 2017-02-16 |  | 2017-02-23 |  |  | 2017-12-21 | 2018-03-21 |  | 2018-08-01 | 2019-02-01
PA | Westmoreland County, PA | 42129 |  | 08-03-0222S | PAL |  | 66 | Bob Pierson | Marty Frengs |  | AMEC | N/A | AMEC | N/A | N/A | 2010-04-30 | N/A | 2010-05-25 | N/A |  |  |  |  | 2010-09-17 | 2011-03-17
PA | Westmoreland County, PA (MM) | 42129 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2002-06-06 | 2002-12-06
PA | Wyoming County, PA | 42131 |  | 07-03-0438S | Restudy |  | 23 | Tiffany Keane | Nicole Lick |  | RAMPP / GG3 (FIS) | N/A | RAMPP | N/A | N/A | 2010-09-30 | N/A | 2010-12-14 | N/A |  |  | 2011-10-03 |  | 2012-02-02 | 2012-08-02
PA | Wyoming County, PA - Upper Susquehanna River PMR - Bradford and Wyoming Counties | 42131 |  | 16-03-0615S | Restudy | 1 | 14 | Nikki Roberts | Bobby Cobelli | justin.king@stantec.com | STARR II | N/A | STARR II/ Compass | N/A | 2017-09-06 | 2018-08-30 | N/A | 2018-12-11 | N/A | 2020-07-01 | 2021-04-01 | 2021-07-01 | N/A | 2021-11-17 | 2022-05-17 |  | May-2015: Includes revised preliminary (15-03-0743S) issued 1/16/2015. // 12/20/2013: on hold awaiting PAL PMR case 11-03-0524S LFD on 6/16/2014.
PA | York County, PA | 42133 |  | 06-03-A621S |  |  | 72 | Nikki Roberts | Henry Chau |  |  |  |  | N/A | N/A | 2008-08-22 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
PA | York County, PA - Lower Susquehanna Basin-Wide Study | 42133 |  | 11-03-1991S | Restudy | 1 | 72 | Lee Brancheau | Sarah Wolfe | benjamin.kaiser@aecom.com | RAMPP | N/A | RAMPP | 2011-06-28 | 2013-08-06 | 2013-11-26 | 2015-08-11 | 2014-01-07 | N/A | 2014-04-30 | 2014-08-28 | 2014-11-25 |  | 2015-06-16 | 2015-12-16
PA | York County, PA (Revised Prelim for 11-03-1991S) | 42133 |  | 14-03-1949S |  |  |  | Lee Brancheau | Molly Kaput |  |  |  |  | N/A | N/A | 2014-04-30 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
PA | York County, PA, PMR (PAL) | 42133 |  | 11-03-0523S |  |  |  | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2015-12-31 | N/A | N/A | N/A |  |  |  |  | 2015-01-16 | 2015-07-16
PA, MD, DE, VA, WV | Levee Certification Packages Archive |  |  | 19-03-0025S | Levee |  |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Accomack County, VA | 51001 |  | MICS_11966 | [9 empty] | N/A | N/A | 2006-06-20 | N/A | N/A | N/A |  |  |  |  | 2008-09-16 | 2009-03-16
VA | Accomack County, VA, Coastal PMR | 51001 |  | 11-03-0551S | Restudy |  | 7 | Bob Pierson | Mari Radford | dsyriani@dewberry.com | RAMPP | USACE | RAMPP | 2011-03-23 | 2013-04-24 | 2013-07-19 | 2015-05-02 | 2013-07-31 | 2014-05-13 |  | 2014-05-14 | 2014-08-11 |  | 2014-11-18 | 2015-05-18
VA | Albemarle County, VA | 51003 |  | MICS_11441 |  |  | 2 | [6 empty] | N/A | N/A | 2003-12-30 | N/A | N/A | N/A |  |  |  |  | 2004-08-04 | 2005-02-04
VA | Albemarle County, VA (PAL Scottsville Levee) | 51003 |  | 14-03-2058S | Levee |  | 2 | Bob Pierson | Darlene Messina | christine.estes@aecom.com | RAMPP | N/A | RAMPP | N/A | N/A | 2015-04-28 | N/A | N/A | N/A |  | N/A | N/A |  | 2015-11-16 | 2016-05-16
VA | Albemarle County, VA, PMR (PAL) | 51003 |  | 11-03-0167S | PAL/Restudy |  | 2 | Nikki Roberts | Mari Radford |  | GG3 | N/A | GG3 | N/A | N/A | 2012-09-04 | N/A | N/A | N/A |  | 2013-04-01 | 2013-06-29 |  | 2013-10-02 | 2014-04-02 |  | 7/15/2013: Rebaselining pending receipt of comments by community. 12/14/2012: on hold per ion.
VA | Alexandria City (Ind), VA | 51510 |  | 06-03-A742S | PAL/Restudy |  | 1 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-09-16 | N/A | N/A | N/A |  | 2010-06-08 | 2010-09-24 |  | 2010-12-16 | 2011-06-16
VA | Alleghany County, VA (Incl Covington) | 51005 |  | 08-03-1772S | Restudy |  | 4 | Tiffany Keane | Richard Sobota |  | Dewberry / VGIN (Topo) | N/A | Dewberry | N/A | N/A | 2009-06-26 | N/A | N/A | N/A |  | 2009-12-10 | 2010-03-24 |  | 2010-06-17 | 2010-12-17
VA | Alleghany County, VA (Incl Covington) | 51580 |  | 08-03-1772S |  |  |  | Tiffany Keane | Richard Sobota |  |  |  |  | N/A | N/A | 2009-06-26 | N/A | N/A | N/A |  |  |  |  | 2010-06-17 | 2010-12-17
VA | Amelia County, VA | 51007 |  | 08-03-0129S |  |  | 1 | Tiffany Keane | [5 empty] | N/A | N/A | 2008-05-03 | N/A | N/A | N/A |  |  |  |  | 2008-10-16 | 2009-04-16
VA | Amelia County, VA - Appomattox Basin Study | 51007 | 02080207 | 19-03-0015S | Zone A |  | 1 | John Luff | Zane Hadzick | matt.cobb@stantec.com | STARR II | TBD | STARR II/ Compass | 2018-09-10 | 2019-04-16 | 2019-08-30 | N/A | 2019-11-05 |  |  | 2020-09-03 | 2020-12-02 |  | 2021-04-07 | 2021-10-07
VA | Amherst County, VA | 51009 |  | 06-03-A729S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-09-29 | N/A | N/A | N/A |  |  |  |  | 2007-03-19 | 2007-09-19
VA | Appomattox County, VA | 51011 |  | 07-03-0443S | [9 empty] | N/A | N/A | 2007-03-08 | N/A | N/A | N/A |  |  |  |  | 2007-07-02 | 2008-01-02
VA | Appomattox HUC8 |  | 02080207 | 18-03-0031S | Restudy | N/A | N/A | Lee Brancheau | Charlie Baker | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | N/A | 2018-09-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA | Arlington County, VA | 51013 |  | MICS_12688 | PAL/Restudy | 1 | 1 | Bob Pierson | Richard Sobota |  | AMEC | N/A | RAMPP | N/A | N/A | 2009-09-23 | N/A | N/A | N/A | 2012-06-22 | 2010-07-04 | 2010-10-01 |  | 2013-02-19 | 2013-08-19
VA | Arlington County, VA (Rev Prel for MICS_12688) | 51013 |  | 11-03-2000S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2012-06-22 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Augusta County, VA (Incl Staunton & Waynesboro) | 51820 |  | 06-03-A733S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2006-11-08 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Augusta County, VA (Incl Staunton & Waynesboro) | 51790 |  | 06-03-A733S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2006-11-08 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Augusta County, VA (Incl Staunton & Waynesboro) | 51015 |  | 06-03-A733S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2006-11-08 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Augusta County, VA, PMR | 51015 |  | 12-03-0534S | Restudy |  | 3 | Bob Pierson | Mari Radford | kdunn@dewberry.com | Augusta County, VA | N/A | RAMPP | N/A | N/A | 2014-02-28 | N/A | 2014-05-20 | N/A |  | 2014-08-06 | 2014-11-03 |  | 2015-02-03 | 2015-08-03
VA | Augusta County, VA, PMR | 51015 |  | 09-03-0474S | Restudy |  | 2 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-03-13 | N/A | N/A | N/A |  |  |  |  | 2009-07-06 | 2010-01-06
VA | Augusta County, VA, PMR | 51790 |  | 09-03-0474S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2009-03-13 | N/A | N/A | N/A |  |  |  |  | 2009-07-06 | 2010-01-06
VA | Augusta County, VA, PMR | 51165 |  | 09-03-0474S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2009-03-13 | N/A | N/A | N/A |  |  |  |  | 2009-07-06 | 2010-01-06 |  | 1/14/2013: Delays with LIDAR may cause schedule to be pushed back.
VA | Augusta County, VA, Rev PMR | 51015 |  | 10-03-1644S | Restudy |  | 1 | Bob Pierson | Richard Sobota |  | RAMPP | RAMPP | RAMPP | N/A | N/A | 2010-08-20 | N/A | N/A | N/A |  |  |  |  | 2011-01-18 | 2011-07-18
VA | Bath County, VA | 51017 |  | 08-03-0119S |  |  | 1 | Tiffany Keane | [5 empty] | N/A | N/A | 2008-03-18 | N/A | N/A | N/A |  |  |  |  | 2008-10-02 | 2009-04-02
VA | Bedford County, VA (Incl Bedford City) | 51019 |  | 07-03-0465S | Restudy |  | 2 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2008-01-31 | N/A | N/A | N/A |  | 2009-10-21 | 2010-01-19 |  | 2010-03-29 | 2010-09-29
VA | Bedford County, VA (Incl Bedford City) | 51515 |  | 07-03-0465S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2008-01-31 | N/A | N/A | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
VA | Blackwater HUC8 |  | 03010202 | 19-03-0003S | Restudy | N/A | N/A | Lee Brancheau | Zane Hadzick | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | N/A | 2018-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA | Bland County, VA | 51021 |  | 07-03-0444S | [9 empty] | N/A | N/A | 2007-02-09 | N/A | N/A | N/A |  |  |  |  | 2007-10-02 | 2008-04-02
VA | Botetourt County, VA | 51023 |  | 08-03-1744S | Restudy |  | 4 | Tiffany Keane | David Odegard |  | Dewberry / VGIN (Topo) | N/A | Dewberry | N/A | N/A | 2009-07-07 | N/A | N/A | N/A |  | 2009-12-09 | 2010-03-30 |  | 2010-06-17 | 2010-12-17
VA | Bristol City (Ind), VA | 51520 |  | MICS_11457 |  |  | 1 | [6 empty] | N/A | N/A | 2002-11-26 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-02-04
VA | Brunswick County, VA | 51025 |  | 08-03-0107S | None |  | 4 | Tiffany Keane | Richard Sobota |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-06-27 | N/A | N/A | N/A |  |  |  |  | 2009-01-07 | 2009-07-07
VA | Buchanan County, VA | 51027 |  | 06-03-B599S | [9 empty] | N/A | N/A | 1996-08-19 | N/A | N/A | N/A |  |  |  |  | 1997-02-19 | 1997-08-19
VA | Buckingham County, VA | 51029 |  | 07-03-0445S |  |  | 2 | [6 empty] | N/A | N/A | 2007-09-07 | N/A | N/A | N/A |  |  |  |  | 2007-12-17 | 2008-06-17
VA | Buena Vista City, VA (Part of MICS_12599) | 51530 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1999-10-06 | 2000-04-06
VA | Campbell County, VA | 51031 |  | 07-03-0446S |  |  | 3 | [6 empty] | N/A | N/A | 2007-12-14 | N/A | N/A | N/A |  |  |  |  | 2008-02-28 | 2008-08-28 |  | Funded in 2008
VA | Caroline County, VA | 51033 |  | 08-03-0215S |  |  |  | Bob Pierson | Gene Gruber |  |  |  |  | N/A | N/A | 2008-04-07 | N/A | N/A | N/A |  |  |  |  | 2008-09-02 | 2009-03-02
VA | Carroll County, VA | 51035 |  | 07-03-0449S |  |  | 2 | Bob Pierson | [5 empty] | N/A | N/A | 2007-07-10 | N/A | N/A | N/A |  |  |  |  | 2008-02-28 | 2008-08-28 |  | Project Effective. Resilience meeting scheduled for 4/26.
VA | Charles City County, VA | 51036 |  | 08-03-0198S |  |  | 1 | Bob Pierson | Gene Gruber |  |  |  |  | N/A | N/A | 2008-03-27 | N/A | N/A | N/A |  |  |  |  | 2008-09-16 | 2009-03-16 |  | 5/14/2013: Appeals letters being mailed 5/16. 1/31/2013: Murderkill River (11-03-2219S) is being rolled into this project.
VA | Charles City County, VA, Coastal PMR | 51036 |  | 12-03-0375S | Restudy |  | 1 | Bob Pierson | Darlene Messina | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-15 | 2013-11-21 | 2014-01-31 | 2016-07-12 | 2014-02-06 | 2014-08-25 |  | 2014-06-26 | 2014-09-23 |  | 2015-01-06 | 2015-07-06
VA | Charlotte County, VA | 51037 |  | 08-03-0112S | None |  | 6 | Tiffany Keane | Ed Copeland |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-08-19 | N/A | N/A | N/A |  |  |  |  | 2009-01-20 | 2009-07-20
VA | Charlottesville City, VA (Part of MICS_11441) | 51540 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2004-08-04 | 2005-02-04
VA | Chesapeake City (Ind), VA, Coastal PMR | 51550 |  | 11-03-0552S |  |  | 0 | Robin Danforth | Mari Radford |  |  |  |  | 2011-03-22 | 2013-01-31 | 2013-04-05 | 2015-05-06 | 2013-05-23 | 2013-10-30 |  |  |  |  | 2014-06-16 | 2014-12-16
VA | Chesapeake City County, VA (MM) | 51550 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1998-11-02 | 1999-05-02
VA | Chesapeake County, VA | 51550 |  | 06-03-B600S | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Chesterfield County, VA | 51041 |  | MICS_30221 | Restudy |  | 1 | Bob Pierson | Richard Sobota |  | USACE | GG3 | AMEC | N/A | N/A | 2009-09-30 | N/A | 2009-12-09 | N/A |  | 2010-06-08 |  |  | 2012-06-18 | 2012-12-18
VA | Clarke County, VA | 51043 |  | MICS_16607 | [9 empty] | N/A | N/A | 2006-07-28 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Colonial Heights City (Ind), VA | 51570 |  | 07-03-0467S | Other BFE |  | 1 | Bob Pierson | Michelle Harel |  | USACE | N/A | AMEC | N/A | N/A | 2010-09-30 | N/A | 2010-11-03 | N/A |  |  | 2011-10-31 |  | 2012-02-02 | 2012-08-02
VA | Craig County, VA | 51045 |  | 08-03-0123S |  |  | 2 | Tiffany Keane | [5 empty] | N/A | N/A | 2008-03-18 | N/A | N/A | N/A |  |  |  |  | 2008-10-02 | 2009-04-02
VA | Culpeper County, VA | 51047 |  | 06-03-A713S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-06-01 | N/A | N/A | N/A |  |  |  |  | 2006-12-18 | 2007-06-18
VA | Culpeper County, VA - Rapidan-Rappahannock Basin-Wide Study (Countywide) | 51047 | 02080103 | 18-03-0004S | Zone A |  | 2 | Lee Brancheau | Zane Hadzick | gjones@dewberry.com | STARR II | TBD | STARR II/ Compass | 2017-09-21 | 2018-02-05 | 2018-07-23 | N/A | 2018-12-11 |  |  | 2019-08-08 | 2019-11-06 |  | 2020-08-26 | 2021-02-26
VA | Cumberland County, VA | 51049 |  | 08-03-0131S | None |  | 1 | Tiffany Keane | Nicole Lick |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-07-31 | N/A | N/A | N/A |  |  |  |  | 2008-12-16 | 2009-06-16 |  | Archived per direction of Lee Brancheau 3/6/19
VA | Dickenson County, VA | 51051 |  | 08-03-0201S | Restudy |  | 4 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2008-12-23 | N/A | N/A | N/A |  | 2009-10-28 | 2010-01-26 |  | 2010-03-29 | 2010-09-29 |  | Affects only unincorporated areas of Franklin County. Redelineation around Smith Mountain lake.
VA | Dinwiddie County, VA | 51053 |  | 08-03-1796S | Other BFE |  | 2 | Tiffany Keane | Richard Sobota |  | Dewberry | N/A | Dewberry | N/A | N/A | 2009-12-31 | N/A | 2010-03-11 | N/A |  | 2010-07-01 | 2010-10-01 |  | 2010-12-16 | 2011-06-16 |  | Old appeals period dates from 5/29/2018 to 8/27/2019
VA | Dinwiddie County, VA - Nottoway Basin-Wide Study | 51053 | 03010201 | 19-03-0016S | Restudy, Zone A |  | 2 | John Luff | Kristen Jones | matt.cobb@stantec.com | STARR II | TBD | STARR II/ Compass | 2018-09-11 | 2020-05-27 | 2020-09-30 | N/A | 2020-11-10 | N/A |  | 2021-05-13 | 2021-08-11 |  | 2021-12-01 | 2022-06-01
VA | Essex County, VA | 51057 |  | 08-03-0202S |  |  | 2 | Bob Pierson | Gene Gruber |  |  |  |  | N/A | N/A | 2008-05-12 | N/A | N/A | N/A |  |  |  |  | 2008-09-16 | 2009-03-16
VA | Essex County, VA - Lower Rappahannock Basin-Wide Study | 51057 | 02080104 | 19-03-0006S | Zone A |  | 2 | John Luff | Charlie Baker | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-19 | 2019-01-15 | 2019-09-15 |  | 2019-11-07 |  |  | 2020-09-02 | 2020-12-01 | TBD | 2021-04-21 | 2021-10-21
VA | Essex County, VA, Coastal PMR | 51057 |  | 12-03-0377S | Restudy |  | 2 | Bob Pierson | Zane Hadzick | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-03 | 2013-07-30 | 2013-08-23 | 2017-04-26 | 2013-09-18 | 2015-01-14 |  | 2014-03-12 | 2014-06-09 |  | 2014-11-04 | 2015-05-04
VA | Fairfax City (Ind), VA | 51600 |  | MICS_11575 |  |  | 1 | [6 empty] | N/A | N/A | 2002-01-22 | N/A | N/A | N/A |  |  |  |  | 2005-12-02 | 2006-06-02
VA | Fairfax City County, VA (MM) | 51600 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2002-08-19 | 2003-02-19
VA | Fairfax County, VA (Rev Prel for 07-03-1412S) | 51059 |  | 09-03-0596S | Restudy |  | 4 | Nikki Roberts | Richard Sobota |  | Fairfax County CTP | N/A | Baker | N/A | N/A | 2009-06-05 | N/A | N/A | N/A |  |  |  |  | 2010-03-17 | 2010-09-17
VA | Fairfax County, VA (Rev Prel for MICS_12038) | 51059 |  | 07-03-1412S |  | 1 |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | N/A | 2007-09-28 | N/A | N/A | N/A | 2009-06-05 |  |  |  | 2010-03-17 | 2010-09-17
VA | Fairfax County, VA (SEE 09-03-0596S) | 51059 |  | MICS_12038 |  | 1 |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | N/A | 2006-05-31 | N/A | N/A | N/A | 2007-09-28 |  |  |  | 2010-03-17 | 2010-09-17
VA | Falls Church City (Ind), VA | 51610 |  | MICS_19047 |  |  | 1 | [6 empty] | N/A | N/A | 2003-04-25 | N/A | N/A | N/A |  |  |  |  | 2004-01-16 | 2004-07-16
VA | Fauquier County, VA | 51061 |  | 06-03-A718S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-09-29 | N/A | N/A | N/A |  |  |  |  | 2007-08-06 | 2008-02-06
VA | Floyd County, VA | 51063 |  | 07-03-0451S |  |  | 2 | [6 empty] | N/A | N/A | 2007-05-22 | N/A | N/A | N/A |  |  |  |  | 2007-10-16 | 2008-04-16
VA | Fluvanna County, VA | 51065 |  | 07-03-0450S |  |  | 2 | [6 empty] | N/A | N/A | 2007-07-18 | N/A | N/A | N/A |  |  |  |  | 2007-11-16 | 2008-05-16
VA | Franklin City (Ind), VA | 51620 |  | MICS_10065 |  |  | 1 | [6 empty] | N/A | N/A | 2001-08-30 | N/A | N/A | N/A |  |  |  |  | 2002-03-04 | 2002-09-04
VA | Franklin County, VA | 51067 |  | 07-03-0452S |  |  | 3 | Bob Pierson | [5 empty] | N/A | N/A | 2008-02-04 | N/A | N/A | N/A |  |  |  |  | 2008-06-16 | 2008-12-16
VA | Franklin County, VA, PMR | 51067 |  | 09-03-0683S | None |  | 1 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-04-02 | N/A | N/A | N/A |  |  |  |  | 2009-07-06 | 2010-01-06
VA | Frederick County, VA - Conococheague-Opequon Basin-Wide Study | 51069 | 02070004 | 12-03-0413S | Restudy |  | 3 | Bob Pierson | Zane Hadzick | errol.dufour@stantec.com | RAMPP / STARR II | TBD | STARR II/ Compass | 2012-05-30 | 2016-11-16 | 2017-09-12 | N/A | 2017-11-27 |  | 2019-05-14 | 2019-11-06 | 2020-02-04 | 2020-09-16 | 2020-07-29 | 2021-01-29
VA | Frederick County, VA (Incl Winchester) | 51840 |  | 06-03-B003S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2008-09-30 | N/A | N/A | N/A |  |  |  |  | 2009-03-02 | 2009-09-02 |  | Incorporated Case No. 13-03-1759S. 4/15/2014: Prelim date of 7/31/2014 pending approval of CR.
VA | Frederick County, VA (Incl Winchester) | 51069 |  | 06-03-B003S |  |  | 4 | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2008-09-30 | N/A | N/A | N/A |  |  |  |  | 2009-03-02 | 2009-09-02
VA | Fredericksburg, VA | 51630 |  | 06-03-B001S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-08-17 | N/A | N/A | N/A |  |  |  |  | 2007-03-19 | 2007-09-19
VA | Galax City (Ind), VA | 51640 |  | 07-03-0463S |  |  | 1 | Bob Pierson | [5 empty] | N/A | N/A | 2007-07-10 | N/A | N/A | N/A |  |  |  |  | 2008-02-28 | 2008-08-28
VA | Giles County, VA | 51071 |  | 06-03-B636S | None |  | 6 | Nikki Roberts | Terese Grubb |  | VA DCR / Virginia Tech | AMEC | AMEC | N/A | N/A | 2008-06-30 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
VA | Gloucester County, VA | 51073 |  | 08-03-1559S | None |  | 1 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-08-28 | N/A | 2009-12-08 | N/A |  |  |  |  | 2010-03-17 | 2010-09-17
VA | Gloucester County, VA - Great Wicomico-Piankatank Basin-Wide Study | 51073 | 02080102 | 19-03-0007S | Zone A |  | 1 | John Luff | Charlie Baker | agilman@tandmassociates.com | Compass | N/A | STARR II/ Compass | N/A | 2019-03-07 | 2019-10-15 |  | 2019-12-16 |  |  | 2020-09-10 | 2020-12-09 | TBD | 2021-04-21 | 2021-10-21
VA | Gloucester County, VA, Coastal PMR | 51073 |  | 11-03-0553S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2011-03-31 | 2013-01-29 | 2013-03-05 | 2017-04-26 | 2013-05-20 | 2014-02-04 |  | 2013-09-19 | 2013-12-17 |  | 2014-05-19 | 2014-11-19
VA | Goochland County, VA | 51075 |  | 07-03-0464S |  |  | 1 | Bob Pierson | [5 empty] | N/A | N/A | 2007-11-01 | N/A | N/A | N/A |  |  |  |  | 2008-06-02 | 2008-12-02
VA | Grayson County, VA | 51077 |  | 07-03-0462S |  |  | 4 | [6 empty] | N/A | N/A | 2007-07-10 | N/A | N/A | N/A |  |  |  |  | 2008-02-28 | 2008-08-28
VA | Greene County, VA | 51079 |  | 06-03-A720S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-03-09 | N/A | N/A | N/A |  |  |  |  | 2006-07-05 | 2007-01-05
VA | Greene County, VA - Rapidan-Rappahannock Basin-Wide Study | 51079 | 02080103, 02080204 | 18-03-0008S | Zone A |  | 2 | Lee Brancheau | Zane Hadzick | brian.lee@stantec.com | STARR II |  | STARR II/ Compass | 2017-09-21 | 2018-02-14 | 2018-08-31 |  | 2018-12-11 |  |  | 2019-08-08 | 2019-11-06 |  | 2020-09-23 | 2021-03-23
VA | Greensville County, VA (Incl Emporia) | 51595 |  | 08-03-0124S |  |  |  | Tiffany Keane | Ed Copeland |  |  |  |  | N/A | N/A | 2008-06-13 | N/A | N/A | N/A |  |  |  |  | 2009-01-07 | 2009-07-07
VA | Greensville County, VA (Incl Emporia) | 51081 |  | 08-03-0124S | None |  | 3 | Tiffany Keane | Ed Copeland |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-06-13 | N/A | N/A | N/A |  |  |  |  | 2009-01-07 | 2009-07-07
VA | Grottoes Town, VA, PMR | 51165 |  | MICS_10042 |  |  | 1 | [6 empty] | N/A | N/A | 2001-07-18 | N/A | N/A | N/A |  |  |  |  | 2002-06-20 | 2002-12-20 |  | Incorporated Case No. 12-03-0411S (Williamsburg City). 4/10/2013: Williamsburg City will be combined with this project.
VA | Halifax County, VA | 51083 |  | 08-03-0125S | Other BFE |  | 5 | Tiffany Keane | Richard Sobota |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-09-08 | N/A | N/A | N/A |  | 2008-10-23 | 2009-02-01 |  | 2009-04-16 | 2009-10-16
VA | Hampton City (Ind), VA | 51650 |  | 05-03-A546S | Restudy |  | 1 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2009-09-25 | N/A | 2009-12-08 | N/A |  | 2010-07-01 | 2010-10-14 |  | 2011-02-16 | 2011-08-16 |  | 8/1/2014: Revised prelim to be issued under original case number; original prelim issued on 10/3/2013.
VA | Hampton City (Ind), VA, PMR (New Market Creek) | 51650 |  | 13-03-1759S |  |  |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2014-07-31 | N/A | 2014-08-13 | 2015-01-13 |  |  |  |  | 2015-11-16 | 2016-05-16
VA | Hampton City, VA, Coastal PMR | 51650 |  | 12-03-0379S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | kdunn@dewberry.com | RAMPP | N/A | RAMPP | 2012-02-29 | 2013-12-05 | 2014-07-31 | 2017-04-27 | 2014-08-13 | 2015-01-13 |  | 2015-02-27 | 2015-05-27 |  | 2015-11-16 | 2016-05-16
VA | Hanover County, VA | 51085 |  | MICS_16485 | [9 empty] | N/A | N/A | 2007-02-14 | N/A | N/A | N/A |  |  |  |  | 2008-06-02 | 2008-12-02
VA | Harrisonburg City (Ind), VA | 51660 |  | MICS_10093 | [9 empty] | N/A | N/A | 2005-09-02 | N/A | N/A | N/A |  |  |  |  | 2007-08-06 | 2008-02-06
VA | Henrico County, VA | 51087 |  | MICS_11997 | [9 empty] | N/A | N/A | 2005-09-29 | N/A | N/A | N/A |  |  |  |  | 2007-06-18 | 2007-12-18
VA | Henry County Greater, VA (Incl Martinsville) | 51690 |  | 07-03-0454S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2007-12-14 | N/A | N/A | N/A |  |  |  |  | 2008-03-26 | 2008-09-26
VA | Henry County Greater, VA (Incl Martinsville) | 51089 |  | 07-03-0454S |  |  | 3 | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2007-12-14 | N/A | N/A | N/A |  |  |  |  | 2008-03-26 | 2008-09-26
VA | Highland County, VA | 51091 |  | 08-03-0126S |  |  | 2 | Tiffany Keane | [5 empty] | N/A | N/A | 2008-03-18 | N/A | N/A | N/A |  |  |  |  | 2008-10-02 | 2009-04-02
VA | Hopewell City (Ind), VA | 51670 |  | 07-03-0859S | None |  | 1 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2010-05-26 | N/A | 2010-08-05 | N/A |  |  |  |  | 2010-12-16 | 2011-06-16
VA | Hopewell City, VA, Coastal PMR | 51670 |  | 12-03-0381S | Restudy |  | 1 | Bob Pierson | Darlene Messina | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-16 | 2013-08-27 | 2013-11-04 | 2016-07-12 | 2013-12-10 | 2014-09-10 |  | 2014-05-08 | 2014-08-05 |  | 2015-01-16 | 2015-07-16
VA | Isle of Wight County, VA | 51093 |  | MICS_10066 |  |  | 3 | [6 empty] | N/A | N/A | 2001-08-31 | N/A | N/A | N/A |  |  |  |  | N/A | 2002-09-04
VA | Isle of Wight County, VA, Coastal PMR | 51093 |  | 12-03-0383S | Restudy |  | 2 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-02-28 | 2013-12-03 | 2014-03-07 | 2017-04-27 | 2014-04-08 | 2014-08-11 |  | 2014-09-18 | 2014-12-16 |  | 2015-06-02 | 2015-12-02 |  | Revised preliminaries issued 2/23/2015 under 15-03-0815S and 12/12/2014 under 14-03-2691S.
VA | James City County, VA (Including Williamsburg) | 51830 |  | MICS_17724 | [9 empty] | N/A | N/A | 2006-09-06 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | James City County, VA (Including Williamsburg) | 51095 |  | MICS_17724 | [9 empty] | N/A | N/A | 2006-09-06 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | James City County, VA (Including Williamsburg), Coastal PMR | 51095 |  | 11-03-0554S | Restudy |  | 2 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | USACE | RAMPP | 2011-04-06 | 2013-04-23 | 2014-03-28 | 2017-04-27 | 2014-04-09 | 2014-08-13 |  | 2014-10-08 | 2015-01-05 |  | 2015-06-16 | 2015-12-16
VA | King and Queen County, VA | 51097 |  | 08-03-0210S | None |  | 1 | Bob Pierson | Ed Copeland |  | AMEC | N/A | AMEC | N/A | N/A | 2008-06-20 | N/A | N/A | N/A |  |  |  |  | 2008-12-16 | 2009-06-16
VA | King and Queen County, VA - Pamunkey Basin-Wide Study | 51097 | 02080106 | 19-03-0008S | Zone A |  | 1 | John Luff | Charlie Baker | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-20 | 2019-02-25 | 2019-10-15 |  | 2019-12-17 |  |  | 2020-09-09 | 2020-12-08 | TBD | 2021-04-21 | 2021-10-21
VA | King and Queen County, VA, Coastal PMR | 51097 |  | 12-03-0385S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | kdunn@dewberry.com | RAMPP | N/A | RAMPP | 2012-01-12 | 2013-08-14 | 2014-08-29 | 2017-04-26 | 2013-12-11 | 2014-11-20 |  | 2014-04-02 | 2014-06-30 |  | 2015-11-16 | 2016-05-16
VA | King George County, VA | 51099 |  | 08-03-0219S |  |  | 1 | Bob Pierson | Gene Gruber |  |  |  |  | N/A | N/A | 2008-06-06 | N/A | N/A | N/A |  |  |  |  | 2008-09-16 | 2009-03-16
VA | King George County, VA - Lower Potomac Basin-Wide Study | 51099 | 02070011 | 19-03-0009S | Zone A |  | 1 | John Luff | Charlie Baker | agilman@tandmassociates.com | Compass/ STARR II | N/A | Compass | 2017-09-19 | 2019-02-25 | 2019-12-23 | N/A | 2020-02-18 | N/A |  | 2020-09-30 | 2020-12-29 | N/A | 2021-06-02 | 2021-12-02
VA | King George County, VA, Coastal PMR | 51099 |  | 12-03-0387S | Restudy |  | 0 | Bob Pierson | Darlene Messina | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-01-11 | 2013-07-10 | 2013-08-09 | 2016-11-30 | 2013-09-19 | 2014-08-27 |  | 2014-03-19 | 2014-06-16 |  | 2014-08-18 | 2015-02-18 |  | Archived per direction of Lee Brancheau 3/6/19
VA | King William County, VA | 51101 |  | 08-03-0209S | None |  | 2 | Bob Pierson | Ed Copeland |  | AMEC | N/A | AMEC | N/A | N/A | 2008-08-15 | N/A | N/A | N/A |  |  |  |  | 2009-01-20 | 2009-07-20 |  | Archived per direction of Lee Brancheau 3/6/19
VA | King William County, VA, Coastal PMR | 51101 |  | 12-03-0389S | Restudy |  | 2 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-01-12 | 2013-08-15 | 2013-10-03 | 2017-04-26 | 2013-12-10 | 2014-07-10 |  | 2014-05-21 | 2014-08-18 |  | 2015-03-02 | 2015-09-02
VA | Lancaster County, VA | 51103 |  | 08-03-1628S | None |  | 4 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-09-24 | N/A | 2009-12-07 | N/A |  |  |  |  | 2010-03-17 | 2010-09-17
VA | Lancaster County, VA - Countywide | 51103 | 02080104 | 18-03-0032S | Zone A |  | 4 | John Luff | Kristen Jones | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-19 | 2018-12-06 | 2019-07-01 |  | 2019-08-26 |  |  | 2021-03-26 | 2021-06-24 |  | 2022-01-05 | 2022-07-05 |  | Original appeals period was from 3/26/2020 to 6/24/2020
VA | Lancaster County, VA, Coastal PMR | 51103 |  | 11-03-0555S | Restudy |  | 4 | Robin Danforth | Mari Radford |  | RAMPP | USACE | RAMPP | 2011-03-30 | 2013-01-28 | 2013-03-22 | 2015-04-02 | 2013-05-22 | 2014-09-11 |  | 2013-10-10 | 2014-01-07 |  | 2014-04-02 | 2014-10-02
VA | Lee County, VA | 51105 |  | 06-03-B480S | None |  | 4 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2010-03-15 | N/A | 2010-04-20 | N/A |  |  |  |  | 2010-08-18 | 2011-02-18
VA | Lee County, VA, Scoping (See 06-03-B480S) | 51105 |  | 06-03-B469S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Lexington City, VA (Part of MICS_12599) | 51678 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1999-10-06 | 2000-04-06
VA | Loudoun County, VA | 51107 |  | 11-03-2001S | Restudy | 1 | 8 | Bob Pierson | Mari Radford | spaul@mbakerintl.com; bill.cain@loudoun.gov | Loudoun County CTP | N/A | Loudoun County CTP | 2012-09-26 | 2014-03-13 | 2014-05-23 | 2016-11-15 | 2014-07-11 | 2014-09-08 | 2014-12-12 | 2015-09-23 | 2015-12-21 |  | 2016-08-17 | 2017-02-17
VA | Loudoun County, VA | 51107 |  | MICS_12603 | [9 empty] | N/A | N/A | 2000-07-05 | N/A | N/A | N/A |  |  |  |  | N/A | 2001-07-05
VA | Loudoun County, VA (Revised Prelim for 11-03-2001S) | 51107 |  | 15-03-0815S |  |  |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2015-02-23 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Loudoun County, VA (Revised Prelim for 11-03-2001S) | 51107 |  | 16-03-1167S |  |  |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2016-04-08 | N/A | N/A | N/A |  |  |  |  | 2016-11-02 | 2017-05-02
VA | Loudoun County, VA (Revised Prelim for 11-03-2001S) | 51107 |  | 14-03-2691S |  |  |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2014-12-12 | N/A | N/A | N/A |  |  |  |  | 2015-11-02 | 2016-05-02
VA | Louisa County, VA | 51109 |  | MICS_12601 | [9 empty] | N/A | N/A | 1996-11-05 | N/A | N/A | N/A |  |  |  |  | N/A | 1997-11-05
VA | Louisa County, VA - Pamunkey Basin-Wide Study | 51109 | 02080106, 02080204 | 18-03-0010S | Zone A |  | 4 | Lee Brancheau | Zane Hadzick | matt.witosky@stantec.com | STARR II | TBD | STARR II/ Compass | 2017-09-20 | 2018-02-14 | 2018-08-30 | N/A | 2018-12-13 | N/A |  | 2019-05-16 | 2019-08-14 | TBD | 2020-01-22 | 2020-07-22
VA | Lower Dan HUC8 - Discovery |  | 03010104 | 19-03-0032S | Restudy |  | N/A | Valerie Panacio | Zane Hadzick | Rebecca.Wetzler@mbakerintl.com | N/A | N/A | N/A | 2019-08-13 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
VA | Lower James Basin- Charles City | 51036 | 02080206 | 16-03-2426S | Restudy |  | 1 | Amanuel Ghebreegziabher | Kristen Jones | Donald.syriani@stantec.com | STARR II | TBD | STARR II/ Compass | 2016-08-25 | 2019-08-14 | 2020-05-29 |  | 2020-07-13 |  |  | 2021-02-11 | 2021-05-12 |  | 2021-10-20 | 2022-04-20
VA | Lower James Basin- Surry County | 51181 | 02080206 | 16-03-2426S | Restudy |  | 4 | Amanuel Ghebreegziabher | Kristen Jones | errol.dufour@stantec.com | STARR II | TBD | STARR II/ Compass | 2016-08-25 | 2019-08-13 | 2020-05-29 |  | 2020-07-15 |  |  | 2021-02-10 | 2021-05-11 |  | 2021-10-06 | 2022-04-06
VA | Lower James Basin-Wide Study (Discovery) |  | 02080206 | 16-03-2426S | TBD |  | 0 | Bob Pierson | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | TBD | TBD | 2016-08-25 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Lower Potomac Basin-Wide Study (Discovery) |  | 02070011 | 17-03-1358S | TBD |  | 0 | Lee Brancheau | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-09-19 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Lower Rappahannock Basin-Wide Study (Discovery) |  | 02080104 | 17-03-1358S | TBD |  | 0 | Lee Brancheau | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-09-19 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Lunenburg County, VA | 51111 |  | 08-03-0127S | None |  | 3 | Tiffany Keane | Richard Sobota |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-07-31 | N/A | N/A | N/A |  |  |  |  | 2009-01-20 | 2009-07-20
VA | Lynchburg City (Ind), VA | 51680 |  | 06-03-B005S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-08-23 | N/A | N/A | N/A |  |  |  |  | 2007-12-03 | 2008-06-03
VA | Madison County, VA | 51113 |  | 06-03-A723S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-03-14 | N/A | N/A | N/A |  |  |  |  | 2006-07-05 | 2007-01-05
VA | Madison County, VA -Rapidan-Rappahannock Basin-Wide Study (Countywide) | 51113 | 02080103 | 18-03-0007S | Zone A |  | 2 | Lee Brancheau | Zane Hadzick | gjones@dewberry.com | STARR II | TBD | STARR II/ Compass | 2017-09-21 | 2018-02-05 | 2018-07-23 | N/A | 2018-12-11 | N/A | N/A | 2019-06-27 | 2019-09-25 | TBD | 2020-03-18 | 2020-09-18
VA | Manassas City, VA (Part of MICS_30900) | 51683 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1994-07-05 | 1995-01-05
VA | Manassas Park City, VA (Part of MICS_30900) | 51685 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1994-07-05 | 1995-01-05
VA | Martinsville City, VA (MM) | 51690 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2008-03-26 | 2008-09-26 |  | 1/14/2013: Delays with LIDAR may cause schedule to be pushed back.
VA | Mathews County, VA | 51115 |  | MICS_18487 | [9 empty] | N/A | N/A | 2007-03-30 | N/A | N/A | N/A |  |  |  |  | 2007-05-16 | 2007-11-16
VA | Mathews County, VA, Coastal PMR | 51115 |  | 11-03-0556S |  |  | 0 | Robin Danforth | Mari Radford |  |  |  |  | 2011-03-29 | 2013-01-29 | 2013-03-05 | 2015-05-04 | 2013-05-20 | 2014-04-08 |  |  |  |  | 2014-06-09 | 2014-12-09
VA | Mattaponi Basin-Wide Study (Discovery) |  | 02080105 | 17-03-1358S | TBD |  | 0 | Lee Brancheau | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-09-20 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Mecklenburg County, VA | 51117 |  | 08-03-0128S | None |  | 7 | Tiffany Keane | Richard Sobota |  | Dewberry | N/A | Dewberry | N/A | N/A | 2008-09-09 | N/A | N/A | N/A |  |  |  |  | 2009-03-11 | 2009-09-11
VA | Middle James Buffalo & Willis - HUC8 |  | 02080205, 02080203 | 18-03-0031S | Restudy | N/A | 16 | Lee Brancheau | Charlie Baker | Sabu.Paul@atkinsglobal.com | STARR II | TBD | N/A | 2018-11-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA | Middle James River - Detailed H&H |  | 02080203, 02080205 | 18-03-0031S | Restudy |  | N/A | Lee Brancheau | Zane Hadzick | Rajendra.Rachamalla@atkinsglobal.com | STARR II | TBD | TBD | 2018-11-27 | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | N/A
VA | Middle James-Willis HUC8 |  | 02080205 | 18-03-0031S | Restudy |  | N/A | Amanuel Ghebreegziabher | Charlie Baker | Rajendra.Rachamalla@atkinsglobal.com | STARR II | TBD | TBD | 2018-11-27 | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
VA | Middlesex County, VA | 51119 |  | 08-03-1630S | None |  | 2 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-06-12 | N/A | N/A | N/A |  |  |  |  | 2009-11-03 | 2010-05-03
VA | Middlesex County, VA - Lower Rappahannock Basin-Wide Study | 51119 | 02080104 | 19-03-0011S | Zone A |  | 2 | John Luff | Kristen Jones | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-19 | 2018-12-19 | 2019-09-16 | N/A | 2019-11-07 | N/A |  | 2020-11-19 | 2021-02-17 | N/A | 2021-11-17 | 2022-05-17
VA | Middlesex County, VA, Coastal PMR | 51119 |  | 12-03-0391S | Restudy |  | 2 | Bob Pierson | Zane Hadzick | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-03 | 2013-08-26 | 2013-10-17 | 2017-04-26 | 2013-12-09 | TBD |  | 2014-05-01 | 2014-07-29 |  | 2014-11-18 | 2015-05-18
VA | Montgomery County (Uninc Areas), VA, PMR | 51121 |  | 10-03-2084S | None |  | 1 | Bob Pierson | Richard Sobota |  | RAMPP | N/A | RAMPP | N/A | N/A | 2011-04-13 | N/A | N/A | N/A |  |  |  |  | 2011-07-06 | 2012-01-06
VA | Montgomery County, VA | 51121 |  | 06-03-B356S | Restudy |  | 3 | Nikki Roberts | Terese Grubb |  | VA DCR / Virginia Tech | AMEC | AMEC | N/A | N/A | 2008-06-30 | N/A | N/A | N/A |  | 2008-10-24 | 2009-02-10 |  | 2009-03-25 | 2009-09-25
VA | Montgomery County, VA (SEE 06-03-B356S) | 51121 |  | 06-03-B925S | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Montgomery County, VA, Scoping (MM) | 51121 |  | 07-03-0188S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Montgomery County, VA, Scoping (REMOVE) | 51121 |  | 06-03-B646S | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Nelson County, VA | 51125 |  | 06-03-A731S | Restudy | 1 | 1 | Bob Pierson | David Odegard |  | AMEC | N/A | AMEC | N/A | N/A | 2007-07-06 | N/A | N/A | N/A | 2008-09-15 | 2009-06-17 | 2009-10-02 |  | 2009-12-18 | 2010-06-18
VA | Nelson County, VA, Rev Prel (SEE 06-03-A731S) | 51125 |  | 08-03-1702S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2008-09-15 | N/A | N/A | N/A |  |  |  |  | 2009-12-18 | 2010-06-18
VA | New Kent County, VA | 51127 |  | 08-03-0220S |  |  | 1 | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2008-09-30 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
VA | New Kent County, VA - Pamunkey Basin-Wide Study | 51127 | 02080106 | 19-03-0012S | Restudy, Zone A |  | 1 | John Luff | Charlie Baker | agilman@tandmassociates.com | Compass | N/A | Compass | 2016-08-25 | 2019-03-07 | 2019-11-29 |  | 2019-12-17 |  |  | 2020-09-09 | 2020-12-08 | TBD | 2021-04-21 | 2021-10-21
VA | New Kent County, VA, Coastal PMR | 51127 |  | 12-03-0393S | Restudy |  | 1 | Bob Pierson | Darlene Messina | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-15 | 2013-11-22 | 2014-01-31 | 2016-07-12 | 2014-02-06 | 2014-08-26 |  | 2014-06-26 | 2014-09-23 |  | 2015-02-03 | 2015-08-03
VA | Newport News City (Ind), VA | 51700 |  | 06-03-A674S |  |  |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | 2013-01-30 | 2010-09-17 | 2015-04-16 | 2013-05-17 | 2014-11-17 |  |  |  |  | 2014-06-09 | 2014-12-09 |  | Archived per direction of Lee Brancheau 3/6/19
VA | Newport News City (Ind), VA PMR (Lucas Creek) | 51700 |  | 11-03-2208S |  |  |  | Nikki Roberts | Mari Radford |  |  |  |  | N/A | N/A | 2012-06-14 | N/A | N/A | N/A |  |  |  |  | 2015-04-02 | 2015-10-02 |  | Archived per direction of Lee Brancheau 3/6/19
VA | Newport News City (Ind), VA, Coastal PMR | 51700 |  | 11-03-0557S |  |  |  | Robin Danforth | Mari Radford |  |  |  |  | N/A | N/A | 2013-03-08 | N/A | N/A | N/A |  |  |  |  | 2014-07-07 | 2015-01-07
VA | Norfolk City (Ind), VA | 51710 |  | MICS_30222 |  |  | 1 | Jon Janowicz | Richard Sobota |  |  |  |  | N/A | N/A | 2008-03-31 | N/A | N/A | N/A |  |  |  |  | 2009-03-02 | 2009-09-02
VA | Norfolk City (Ind), VA, PMR (PAL) | 51710 |  | 11-03-0524S |  | 1 |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | N/A | 2012-08-15 | N/A | N/A | N/A | 2014-01-22 |  |  |  | 2014-06-16 | 2014-12-16
VA | Norfolk City (Ind), VA, PMR (PAL) (Revised Prelim for 11-03-0524S) | 51710 |  | 14-03-0979S |  |  |  | Nikki Roberts | Richard Sobota |  |  |  |  | N/A | N/A | 2014-01-22 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Norfolk City, VA, Coastal PMR | 51710 |  | 12-03-0395S | Restudy | 2 | 1 | Bob Pierson | Zane Hadzick | christine.estes@aecom.com | RAMPP | N/A | RAMPP/ Compass | 2012-02-29 | 2013-12-04 | 2014-08-14 | 2017-04-27 | 2014-09-09 | 2014-11-19 | 2016-04-15 | 2015-06-15 | 2015-09-12 |  | 2016-08-17 | 2017-02-17
VA | Norfolk City, VA, Coastal PMR (Revised Prelim for 12-03-0395S) | 51710 |  | 16-03-1265S |  |  |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2016-04-15 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Norfolk City, VA, Coastal PMR (Revised Prelim for 12-03-0395S) | 51710 |  | 15-03-0743S |  |  |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2015-01-16 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Northampton County, VA | 51131 |  | 07-03-1065S | [9 empty] | N/A | N/A | 2006-03-31 | N/A | N/A | N/A |  |  |  |  | 2008-02-28 | 2008-08-28
VA | Northampton County, VA, Coastal PMR | 51131 |  | 11-03-0558S | Restudy |  | 6 | Robin Danforth | Mari Radford | dsyriani@dewberry.com | RAMPP | USACE | RAMPP | 2011-03-23 | 2013-04-24 | 2013-07-01 | 2015-05-02 | 2013-07-31 | 2014-05-12 |  | 2014-03-19 | 2014-06-16 |  | 2014-09-02 | 2015-03-02 |  | Preliminary delayed until late spring 2020 due to the new LiDAR being acquired and the modeling of the Nottoway River
VA | Northumberland County, VA | 51133 |  | 08-03-1629S | None |  | 1 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2009-09-28 | N/A | 2009-12-07 | N/A |  |  |  |  | 2010-03-17 | 2010-09-17
VA | Northumberland County, VA - FY18 RTO | 51133 |  | 18-03-0033S | Zone A |  | 1 | John Luff | Charlie Baker | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-19 | 2019-04-18 | 2019-12-23 | N/A | 2020-02-19 | N/A |  | 2020-09-30 | 2020-12-29 | N/A | 2021-06-30 | 2021-12-30
VA | Northumberland County, VA, Coastal PMR | 51133 |  | 11-03-0559S | Restudy |  | 2 | Bob Pierson | Darlene Messina | mshultz@dewberry.com | RAMPP | N/A | RAMPP | 2011-03-30 | 2013-04-22 | 2013-05-21 | 2016-09-14 | 2013-08-15 | 2014-08-28 |  | 2014-02-12 | 2014-05-12 |  | 2014-08-18 | 2015-02-18 |  | 1st revised prelim date is 11/15/2019
VA | Nottoway County, VA | 51135 |  | 08-03-0130S |  |  | 4 | Tiffany Keane | [5 empty] | N/A | N/A | 2008-07-01 | N/A | N/A | N/A |  |  |  |  | 2008-12-02 | 2009-06-02
VA | Nottoway County, VA - Nottoway, Appomattox Basin Study | 51135 | 03010201, 02080207 | 19-03-0017S | Zone A |  | 4 | John Luff | Kristen Jones | matt.cobb@stantec.com | STARR II | TBD | STARR II/ Compass | 2018-09-11 | 2019-04-30 | 2020-08-28 | N/A | 2020-10-13 | N/A |  | 2021-03-23 | 2021-06-21 | N/A | 2021-11-03 | 2022-05-03
VA | Nottoway HUC8 |  | 03010201 | 19-03-0003S | Restudy, Zone A | N/A | N/A | Lee Brancheau | Julius Lockhart | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | N/A | 2018-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 1/14/2013: Delays with LIDAR may cause schedule to be pushed back.
VA | Orange County, VA | 51137 |  | 07-03-0461S | [9 empty] | N/A | N/A | 2007-03-08 | N/A | N/A | N/A |  |  |  |  | 2007-07-02 | 2008-01-02
VA | Orange County,VA - Rapidan-Rappahannock Basin-Wide Study | 51137 | 02080103, 02080106, 02080105 | 18-03-0009S | Zone A |  | 3 | Lee Brancheau | Kristen Jones | Russell.Remy@stantec.com | STARR II | TBD | STARR II/ Compass | 2017-09-21 | 2018-02-14 | 2019-05-30 | N/A | 2019-07-12 | N/A | 2021-06-30 | 2020-09-03 | 2020-12-02 | N/A | 2021-11-17 | 2022-05-17
VA | Page County, VA | 51139 |  | 06-03-A727S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-04-19 | N/A | N/A | N/A |  |  |  |  | 2006-07-05 | 2007-01-05
VA | Pamunkey Basin-Wide Study (Discovery) |  | 02080106 | 17-03-1358S | TBD |  | 0 | Lee Brancheau | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-09-20 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Pamunkey Basin-Wide Study (Discovery) |  | 02080106 | 17-03-1358S | TBD |  | 0 | Lee Brancheau | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-09-20 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Patrick County, VA | 51141 |  | 07-03-0460S |  |  | 2 | [6 empty] | N/A | N/A | 2007-12-07 | N/A | N/A | N/A |  |  |  |  | 2008-02-19 | 2008-08-19
VA | Petersburg City (Ind), VA | 51730 |  | 07-03-1031S | None |  | 1 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2009-11-19 | N/A | 2010-01-19 | N/A |  |  |  |  | 2010-08-04 | 2011-02-04 |  | Archived per direction of Lee Brancheau 3/6/19
VA | Pittsylvania County, VA (Incl Danville) | 51143 |  | 08-03-1797S | None |  | 5 | Tiffany Keane | Richard Sobota |  | Dewberry / VGIN (Topo) | N/A | Dewberry | N/A | N/A | 2009-09-30 | N/A | 2009-11-18 | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
VA | Pittsylvania County, VA (Incl Danville) | 51590 |  | 08-03-1797S |  |  |  | Tiffany Keane | Richard Sobota |  |  |  |  | N/A | N/A | 2009-09-30 | N/A | N/A | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
VA | Poquoson City (Ind), VA | 51735 |  | 05-03-A545S | Other BFE |  | 1 | Tiffany Keane | Richard Sobota |  | USACE | N/A | RAMPP | N/A | N/A | 2010-04-19 | N/A | 2010-06-02 | N/A |  | 2010-09-01 | 2010-12-01 |  | 2011-05-02 | 2011-11-02
VA | Poquoson City (Ind), VA, Coastal PMR | 51735 |  | 11-03-0560S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2011-03-29 | 2013-01-30 | 2013-02-20 | 2017-04-27 | 2013-05-16 | 2014-07-08 |  | 2013-09-26 | 2013-12-24 |  | 2014-06-16 | 2014-12-16
VA | Portsmouth City, VA | 51740 |  | 05-03-A547S | None |  | 1 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2008-02-28 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25 |  | 9/4/2013: Project will need new LFD due to question re accreditation. 6/13/2013: Mapping partner requested move to 10/2/2013 LFD.
VA | Portsmouth City, VA, Coastal PMR | 51740 |  | 12-03-0397S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-02-29 | 2013-12-04 | 2014-01-13 | 2017-04-27 | 2014-02-05 | 2014-07-09 |  | 2014-06-13 | 2014-09-10 |  | 2015-02-03 | 2015-08-03
VA | Powhatan County, VA | 51145 |  | 07-03-0459S |  |  | 1 | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2007-06-12 | N/A | N/A | N/A |  |  |  |  | 2007-08-06 | 2008-02-06
VA | Prince Edward County, VA | 51147 |  | 08-03-0221S | None |  | 3 | Bob Pierson | Ed Copeland |  | AMEC | N/A | AMEC | N/A | N/A | 2008-12-08 | N/A | N/A | N/A |  |  |  |  | 2009-04-02 | 2009-10-02 |  | 12/23/2013: FR for appeals published.
VA | Prince George County, VA | 51149 |  | 07-03-0457S | Other BFE |  | 1 | Bob Pierson | Michelle Harel |  | USACE | N/A | AMEC | N/A | N/A | 2010-09-30 | N/A | 2010-11-03 | N/A |  |  | 2011-08-09 |  | 2011-11-16 | 2012-05-16
VA | Prince George County, VA, Coastal PMR | 51149 |  | 12-03-0399S | Restudy |  | 1 | Bob Pierson | Darlene Messina | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-16 | 2013-08-27 | 2013-11-04 | 2016-07-12 | 2013-12-10 | 2014-09-10 |  | 2014-06-05 | 2014-09-02 |  | 2014-12-02 | 2015-06-02
VA | Prince William County, VA | 51153 |  | MICS_13001 | [9 empty] | N/A | N/A | 1994-01-05 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-03-11
VA | Prince William County, VA (MM) | 51153 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1994-07-05 | 1995-01-05
VA | Prince William County, VA, Coastal PMR | 51153 |  | 12-03-0401S | Restudy |  | 3 | Bob Pierson |  | dsyriani@dewberry.com | RAMPP | N/A | RAMPP | 2012-01-11 | 2013-07-29 | 2013-08-23 | 2015-07-16 | 2013-09-16 | 2014-05-15 |  | 2014-05-21 | 2014-08-18 |  | 2015-02-03 | 2015-08-03
VA | Pulaski County, VA | 51155 |  | 07-03-0455S |  |  | 3 | Bob Pierson | [5 empty] | N/A | N/A | 2007-09-07 | N/A | N/A | N/A |  |  |  |  | 2008-03-26 | 2008-09-26
VA | Radford City (Ind), VA | 51750 |  | 07-03-0545S | Restudy |  | 1 | Nikki Roberts | Terese Grubb |  | VA DCR / Virginia Tech | AMEC | AMEC | N/A | N/A | 2008-06-30 | N/A | N/A | N/A |  | 2008-10-24 | 2009-02-10 |  | 2009-03-25 | 2009-09-25
VA | Radford City, VA - Upper New Basin-Wide Study | 51750 | 05050001 | 18-03-0015S | Zone A |  | 1 | Lee Brancheau | Zane Hadzick | matt.witosky@stantec.com | STARR II | TBD | STARR II/ Compass | N/A | 2018-06-08 | 2018-09-28 |  | 2018-11-01 | N/A |  | 2019-05-01 | 2019-08-09 | TBD | 2019-12-19 | 2020-06-19
VA | Rapidan-Upper Rappahannock Basin-Wide Study (Discovery) |  | 02080103 | 17-03-1358S | TBD |  | 0 | Lee Brancheau | Zane Hadzick | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-09-21 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
VA | Rappahannock County, VA | 51157 |  | 06-03-A725S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-03-23 | N/A | N/A | N/A |  |  |  |  | 2006-07-05 | 2007-01-05
VA | Rappahannock County, VA - Rapidan-Rappahannock Basin-Wide Study (Countywide) | 51157 | 02080103 | 18-03-0006S | Zone A |  | 2 | Lee Brancheau | Zane Hadzick | gjones@dewberry.com | STARR II | TBD | STARR II/ Compass | 2017-09-21 | 2018-02-05 | 2018-07-23 | N/A | 2018-12-12 |  |  | 2019-07-25 | 2019-10-24 |  | 2020-08-26 | 2021-02-26 |  | 9/4/2013: Project will need new LFD due to question re accreditation. 6/13/2013: Mapping partner requested move to 10/2/2013 LFD.
VA | REG Virginia Automated Engineering (Plus) Project EAST |  |  | 17-03-0914S | Zone A | N/A | N/A | Lee Brancheau | Zane Hadzick | kevin.donnelly@stantec.com | STARR II | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | N/A | N/A | N/A
VA | REG Virginia Automated Engineering (Plus) Project WEST |  |  | 17-03-0960S | Zone A | N/A | N/A | Lee Brancheau | Zane Hadzick | kevin.donnelly@stantec.com | STARR II | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A | N/A | N/A | N/A
VA | Richmond City (Ind), VA | 51760 |  | 06-03-B185S |  |  | 1 | Nikki Roberts | [5 empty] | N/A | N/A | 2007-11-07 | N/A | N/A | N/A |  |  |  |  | 2008-10-02 | 2009-04-02
VA | Richmond City, VA, PMR (PAL) | 51760 |  | 11-03-0168S | PAL/Restudy |  | 1 | Nikki Roberts | Mari Radford |  | GG3 | N/A | GG3 | N/A | N/A | 2013-04-26 | N/A | N/A | N/A |  |  |  |  | 2014-01-16 | 2014-07-16
VA | Richmond County, VA | 51159 |  | 08-03-0214S |  |  | 2 | Bob Pierson | Gene Gruber |  |  |  |  | N/A | N/A | 2008-01-30 | N/A | N/A | N/A |  |  |  |  | 2008-06-16 | 2008-12-16
VA | Richmond County, VA - Countywide | 51159 | 02080104 | 18-03-0034S | Zone A |  | 2 | John Luff | Kristen Jones | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-19 | 2018-12-06 | 2019-07-19 |  | 2019-08-27 |  |  | 2021-03-25 | 2021-06-23 |  | 2022-01-05 | 2022-07-05 |  | Original appeals period from 3/25/2020 to 6/23/2020
VA | Richmond County, VA, Coastal PMR | 51159 |  | 12-03-0403S | Restudy |  | 1 | Bob Pierson | Mari Radford | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-02 | 2013-07-30 | 2013-09-06 | 2016-09-14 | 2013-09-19 | 2015-01-14 |  | 2014-02-26 | 2014-05-26 |  | 2014-10-16 | 2015-04-16
VA | Roanoke City, VA (Part of MICS_30900A) | 51770 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2004-08-04 | 2005-02-04
VA | Roanoke County, VA | 51770 |  | 07-03-1064S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2006-07-31 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Roanoke County, VA | 51161 |  | 07-03-1064S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2006-07-31 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Roanoke County, VA | 51775 |  | 07-03-1064S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | 2006-07-31 | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Roanoke County, VA (MM) | 51161 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2004-08-04 | 2005-02-04
VA | Roanoke County, VA (SEE 07-03-1064S) | 51161 |  | MICS_11962 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Roanoke County, VA (SEE 07-03-1064S) | 51775 |  | MICS_11962 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Roanoke County, VA (SEE 07-03-1064S) | 51770 |  | MICS_11962 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2007-03-28 | 2007-09-28
VA | Rockbridge County, VA (Incl Buena Vista and Lexington) | 51163 |  | MICS_12599 | [9 empty] | N/A | N/A | 1998-12-23 | N/A | N/A | N/A |  |  |  |  | N/A | 2000-04-06
VA | Rockingham County, VA | 51165 |  | 06-03-A738S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2007-04-30 | N/A | N/A | N/A |  |  |  |  | 2007-08-06 | 2008-02-06
VA | Rockingham County, VA, PMR (PAL) | 51165 |  | 11-03-0169S | PAL/Restudy |  | 3 | Nikki Roberts | Mari Radford |  | GG3 | N/A | GG3 | N/A | N/A | 2012-05-09 | N/A | N/A | N/A |  | 2013-03-01 | 2013-05-29 |  | 2014-02-18 | 2014-08-18
VA | Russell County, VA | 51167 |  | MICS_19793 | None |  | 5 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2009-09-25 | N/A | 2009-11-19 | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
VA | Salem City, VA (Part of MICS_30900A) | 51775 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2004-08-04 | 2005-02-04
VA | Scott County, VA | 51169 |  | 06-03-B482S |  | 1 |  | Bob Pierson | Mari Radford |  |  |  |  | N/A | N/A | 2011-09-09 | N/A | 2011-09-28 | N/A | 2012-12-27 |  |  |  | 2014-07-07 | 2015-01-07 |  | 12/23/2013: FR for appeals published.
VA | Scott County, VA (Revised Prelim for 06-03-B482S) | 51169 |  | 13-03-2709S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2012-12-27 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Shenandoah County, VA (MM) | 51171 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2003-01-16 | 2003-07-16
VA | Shenandoah County, VA, PMR (MM) | 51171 |  | MICS_30493 | [9 empty] | N/A | N/A | 2005-02-08 | N/A | N/A | N/A |  |  |  |  | 2005-08-02 | 2006-02-02
VA | Shenandoah County, VA, PMR (N Fk Shenandoah R & Spring Hollow) | 51171 |  | MICS_10091 |  |  | 7 | [6 empty] | N/A | N/A | 2005-02-08 | N/A | N/A | N/A |  |  |  |  | 2005-08-02 | 2006-02-02
VA | Smyth County, VA | 51173 |  | 06-03-B483S | None |  | 4 | Bob Pierson | Mari Radford |  | USACE / Baker | N/A | AMEC | N/A | N/A | 2011-09-09 | N/A | 2011-09-29 | N/A |  |  |  |  | 2012-02-02 | 2012-08-02
VA | Southampton County, VA | 51175 |  | MICS_10067 |  |  | 5 | [6 empty] | N/A | N/A | 2001-08-30 | N/A | N/A | N/A |  |  |  |  | N/A | 2002-09-04
VA | Spotsylvania County, VA | 51177 |  | 06-03-B647S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Spotsylvania County, VA (MM) | 51177 |  | MICS_30900 | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1997-08-18 | 1998-02-18
VA | Stafford County | 51179 |  | MICS_10084 |  |  | 1 | [6 empty] | N/A | N/A | 2002-01-30 | N/A | N/A | N/A |  |  |  |  | 2004-08-04 | 2005-02-04
VA | Stafford County, VA, Coastal PMR | 51179 |  | 12-03-0405S | Restudy |  | 0 | Bob Pierson | Darlene Messina | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-01-11 | 2013-07-11 | 2013-08-16 | 2016-11-30 | 2013-09-17 | 2014-08-14 |  | 2014-03-26 | 2014-06-23 |  | 2014-08-18 | 2015-02-18 |  | 12/23/2013: FR for appeals published.
VA | Staunton & Waynesboro Cities, VA (Part of Augusta County/06-03-A733S) | 51015 |  | 06-03-A736S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Staunton & Waynesboro Cities, VA (Part of Augusta County/06-03-A733S) | 51790 |  | 06-03-A736S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A |  | Old appeals period dates from 5/29/2018 to 8/27/2019
VA | Staunton & Waynesboro Cities, VA (Part of Augusta County/06-03-A733S) | 51820 |  | 06-03-A736S |  |  |  | Jon Janowicz | [5 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
VA | Suffolk City (Ind), VA | 51800 |  | MICS_19799 | Other BFE |  | 1 | Nikki Roberts | Richard Sobota |  | USACE | N/A | Baker | N/A | N/A | 2010-07-22 | N/A | 2010-11-02 | N/A |  |  |  |  | 2011-05-16 | 2011-11-16
VA | Suffolk City, VA, Coastal PMR | 51800 |  | 12-03-0407S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | gjones@dewberry.com | RAMPP | N/A | RAMPP | 2012-02-28 | 2013-12-03 | 2013-12-09 | 2017-04-27 | 2014-02-04 | 2014-05-14 |  | 2014-05-15 | 2014-08-12 |  | 2015-02-03 | 2015-08-03
VA | Surry County, VA | 51181 |  | 08-03-0216S |  |  | 3 | Bob Pierson | Gene Gruber |  |  |  |  | N/A | N/A | 2008-04-16 | N/A | N/A | N/A |  |  |  |  | 2008-10-02 | 2009-04-02
VA | Surry County, VA, Coastal PMR | 51181 |  | 11-03-0561S | Restudy |  | 3 | Bob Pierson | Mari Radford | fknight@dewberry.com | RAMPP | USACE | RAMPP | 2011-04-05 | 2013-04-23 | 2013-05-21 | 2016-07-12 | 2013-08-14 | 2014-02-03 |  | 2014-02-19 | 2014-05-19 |  | 2014-11-04 | 2015-05-04
VA | Sussex County, VA | 51183 |  | 08-03-0217S | None |  | 4 | Bob Pierson | Ed Copeland |  | AMEC | N/A | AMEC | N/A | N/A | 2008-08-12 | N/A | N/A | N/A |  |  |  |  | 2009-01-07 | 2009-07-07
VA | Tazewell County, VA | 51185 |  | MICS_12777 | Restudy |  | 6 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2010-03-31 | N/A | 2010-04-22 | N/A |  |  |  |  | 2010-08-18 | 2011-02-18
VA | Upper Dan & Upper Yadkin HUC8 - Discovery |  | 03010103, 03040101 | 19-03-0032S | Discovery |  | N/A | John Luff | Kristen Jones | christine.estes@aecom.com | Compass | TBD | TBD | 2020-07-09 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
VA | Upper Roanoke HUC8 - Discovery |  | 03010101 | 19-03-0032S | Discovery |  | N/A | John Luff | Kristen Jones | kdunn@tandmassociates.com | Compass | TBD | TBD | 2020-07-09 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A
VA | Virginia Beach City (Ind), VA | 51810 |  | MICS_12602 | [9 empty] | N/A | N/A | 2003-10-09 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-03-11
VA | Virginia Beach City (Ind), VA, Citywide Revision | 51810 |  | 06-03-B186S |  |  | 1 | Nikki Roberts | [5 empty] | N/A | N/A | 2007-12-31 | N/A | N/A | N/A |  |  |  |  | 2008-11-04 | 2009-05-04
VA | Virginia Beach City (Ind), VA, Coastal PMR | 51810 |  | 11-03-0562S |  |  | 0 | Robin Danforth | Mari Radford |  |  |  |  | 2011-03-22 | 2013-01-31 | 2013-05-17 | 2015-04-02 | 2013-05-23 | N/A |  |  |  |  | 2014-07-16 | 2015-01-16 |  | Original appeals period from 3/26/2020 to 6/24/2020
VA | Virginia Beach City, VA (MM) | 51810 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 1996-06-05 | 1996-12-05
VA | Warren County, VA | 51187 |  | 06-03-A740S |  |  |  | Michael Craghan | [5 empty] | N/A | N/A | 2006-07-18 | N/A | N/A | N/A |  |  |  |  | 2007-12-03 | 2008-06-03
VA | Washington County, VA | 51191 |  | 06-03-B484S | None |  | 5 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2009-09-02 | N/A | 2009-11-19 | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
VA | Westmoreland County, VA | 51193 |  | 08-03-0218S | None |  | 3 | Bob Pierson | Richard Sobota |  | AMEC | N/A | AMEC | N/A | N/A | 2008-09-29 | N/A | N/A | N/A |  |  |  |  | 2009-02-18 | 2009-08-18
VA | Westmoreland County, VA - Countywide | 51193 |  | 19-03-0001S | Zone A |  | 3 | John Luff | Kristen Jones | agilman@tandmassociates.com | Compass | N/A | Compass | 2017-09-19 | 2018-11-16 | 2019-07-01 | N/A | 2019-08-27 | N/A |  | 2021-03-26 | 2021-06-24 | N/A | 2021-11-17 | 2022-05-17
VA | Westmoreland County, VA, Coastal PMR | 51193 |  | 12-03-0409S | Restudy |  | 2 | Bob Pierson | Mari Radford | christine.estes@aecom.com | RAMPP | N/A | RAMPP | 2012-02-02 | 2013-07-29 | 2013-09-12 | 2016-09-14 | 2013-09-18 | N/A |  | 2014-03-12 | 2014-06-09 |  | 2014-10-16 | 2015-04-16
VA | Williamsburg City, VA, Coastal PMR | 51830 |  | 12-03-0411S |  |  |  | Robin Danforth | [5 empty] | 2012-02-14 | 2013-04-22 | 2014-03-28 | 2015-05-06 | 2014-04-09 | 2014-08-13 |  |  |  |  | 2015-08-03 | 2016-02-03
VA | Winchester City, VA - Conococheague-Opequon Basin-Wide Study | 51840 | 02070004 | 12-03-0413S | Restudy |  | 1 | Bob Pierson | Zane Hadzick | errol.dufour@stantec.com | RAMPP / STARR II | TBD | STARR II/ Compass | 2012-05-30 | 2016-11-16 | 2017-09-12 | N/A | 2017-11-27 |  | 2019-05-14 | 2019-11-06 | 2020-02-04 | 2020-09-16 | 2020-07-29 | 2021-01-29
VA | Wise County, VA (Incl Norton) | 51195 |  | 06-03-B485S | None |  | 8 | Bob Pierson | Richard Sobota |  | USACE | N/A | AMEC | N/A | N/A | 2010-01-28 | N/A | 2010-04-21 | N/A |  |  |  |  | 2010-08-18 | 2011-02-18
VA | Wise County, VA (Incl Norton) | 51720 |  | 06-03-B485S |  |  |  | Bob Pierson | Richard Sobota |  |  |  |  | N/A | N/A | 2010-01-28 | N/A | 2010-04-21 | N/A |  |  |  |  | 2010-08-18 | 2011-02-18 |  | On-hold Jul-2010 pending resolution of QR-2 issue (pending SPR)
VA | Wythe County, VA | 51197 |  | 07-03-0453S |  |  | 5 | [6 empty] | N/A | N/A | 2007-07-06 | N/A | N/A | N/A |  |  |  |  | 2007-11-02 | 2008-05-02
VA | York County, VA | 51199 |  | 05-03-A548S | None |  | 1 | Bob Pierson | Ed Copeland |  | USACE | N/A | AMEC | N/A | N/A | 2008-02-28 | N/A | N/A | N/A |  |  |  |  | 2008-12-16 | 2009-06-02
VA | York County, VA, Coastal PMR | 51199 |  | 11-03-0563S |  |  | 0 | Robin Danforth | Mari Radford |  |  |  |  | 2011-04-05 | 2013-01-29 | 2013-05-10 | 2015-04-02 | 2013-05-16 | 2014-02-05 |  |  |  |  | 2014-07-16 | 2015-01-16
VA, WV | Middle New HUC8 - Discovery |  | 05050002 | 19-03-0005S | Restudy |  | N/A | Valerie Panacio | Zane Hadzick | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | TBD | 2019-08-06 | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  |  |  | Grant is deobligated in MAS 2020 Realignment, and funding is now assigned to new counties.
WV | Barbour County, WV | 54001 |  | 09-03-0138S | Restudy |  | 4 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-07-02 | N/A | N/A | N/A |  | 2010-05-05 | 2010-08-19 |  | 2010-11-03 | 2011-05-03
WV | Barbour County, WV (SEE 09-03-0138S) | 54001 |  | 06-03-A681S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-07-02 | N/A | N/A | N/A |  |  |  |  | 2010-11-03 | 2011-05-03 |  | Greenbrier PMR will be synchronized with Countywide Study under 19-03-0028S
WV | Berkeley County, WV | 54003 |  | 06-03-A675S | None |  | 3 | Bob Pierson | David Odegard |  | WVU | N/A | AMEC | N/A | N/A | 2008-06-30 | N/A | N/A | N/A |  |  |  |  | 2009-01-07 | 2009-07-07
WV | Berkeley County, WV, PMR (Evans Run) | 54003 |  | MICS_10070 |  |  | 1 | [6 empty] | N/A | N/A | 2001-09-13 | N/A | N/A | N/A |  |  |  |  | 2002-02-06 | 2002-08-06
WV | Boone County, WV | 54005 |  | 06-03-B012S | None |  | 5 | Nikki Roberts | Mari Radford |  | USGS WV | N/A | GG3 | N/A | N/A | 2012-03-30 | N/A | 2012-05-11 | N/A |  |  |  |  | 2012-11-16 | 2013-05-16
WV | Braxton County, WV | 54007 |  | 07-03-0219S | None |  | 5 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2009-03-31 | N/A | N/A | N/A |  |  |  |  | 2009-10-19 | 2010-04-19
WV | Brooke County, WV | 54009 |  | 07-03-0220S | None |  | 6 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2009-01-30 | N/A | N/A | N/A |  |  |  |  | 2009-10-19 | 2010-04-19
WV | Cabell County, WV | 54011 |  | MICS_11359 |  |  | 4 | [6 empty] | N/A | N/A | 2004-04-21 | N/A | N/A | N/A |  |  |  |  | 2004-12-16 | 2005-06-16 |  | Recent flooding as of 5/19/2009
WV | Cabell County, WV, PMR (PAL) | 54011 |  | 11-03-0170S | PAL/Restudy |  | 3 | Nikki Roberts | Mari Radford |  | GG3 | N/A | GG3 | N/A | N/A | 2013-01-31 | N/A | N/A | N/A |  |  |  |  | 2013-08-19 | 2014-02-19
WV | Cacapon-Town HUC8 |  | 02070003 | 19-03-0004S | Restudy |  | TBD | Bob Pierson | Heather Davis-Jenkins | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | TBD | 2018-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WV | Calhoun County, WV | 54013 |  | 07-03-0221S | None |  | 2 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2009-06-30 | N/A | N/A | N/A |  |  |  |  | 2009-12-18 | 2010-06-18
WV | Clay County, WV | 54015 |  | 07-03-0439S | None |  | 2 | Nikki Roberts | Henry Chau |  | USGS WV | N/A | GG3 | N/A | N/A | 2012-01-31 | N/A | 2012-03-29 | N/A |  |  |  |  | 2012-08-06 | 2013-02-06
WV | Doddridge County, WV | 54017 |  | 07-03-0222S | None |  | 2 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2010-02-19 | N/A | 2010-04-29 | N/A |  |  |  |  | 2011-04-04 | 2011-10-04
WV | Fayette County, WV | 54019 |  | MICS_30223 | Other BFE |  | 12 | Bob Pierson | Nicole Lick |  | R1 PDC | N/A | Baker | N/A | N/A | 2009-05-29 | N/A | N/A | N/A |  |  |  |  | 2010-03-03 | 2010-09-03 |  | 12/14/2012: 2/19/2013 LFD dropped; Mapping partner proposing 10/16/2013.
WV | Gilmer County, WV | 54021 |  | MICS_30129 |  |  | 3 | Tiffany Keane | Nicole Lick |  |  |  |  | N/A | N/A | 2008-05-07 | N/A | N/A | N/A |  |  |  |  | 2008-12-16 | 2009-06-16
WV | Grant County, WV | 54023 |  | 06-03-A682S |  |  | 3 | Bob Pierson | Nicole Lick |  |  |  |  | N/A | N/A | 2008-07-31 | N/A | N/A | N/A |  |  |  |  | 2009-03-02 | 2009-09-02
WV | Grant County, WV - Countywide | 54023 |  | 19-03-0004S |  |  | 3 | Bob Pierson | Betsy Ranson | jason.sevanick@woodplc.com | Wood | TBD | TBD | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A |  | Archived per direction of Lee Brancheau 3/6/19
WV | Grant County, WV, (LAMP Bayard Levees) | 54023 |  | 11-03-0525S | Levee |  | 2 | Bob Pierson | Heather Davis-Jenkins | christine.estes@aecom.com | RAMPP / STARR II | N/A | Compass | N/A | TBD | 2017-01-06 |  | 2017-02-22 |  |  | 2017-12-19 | 2018-03-19 |  | 2018-08-01 | 2019-02-01 |  | Required new A Zones
WV | Greenbrier County- WV Disaster County PMR | 54025 | 05050003 | 19-03-0002S |  |  | 8 | Bob Pierson | Betsy Ranson | jason.sevanick@woodplc.com | Wood | TBD | TBD | N/A | 2019-05-29 | 2020-02-03 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
WV | Greenbrier County, WV | 54025 |  | 07-03-0442S | None |  | 8 | Bob Pierson | Mari Radford |  | R1 PDC | N/A | AMEC | N/A | N/A | 2011-09-20 | N/A | 2011-11-15 | N/A |  |  |  |  | 2012-04-16 | 2012-10-16
WV | Greenbrier HUC8 |  | 05050003 | 19-03-0005S | Restudy |  | TBD | Bob Pierson | Betsy Ranson | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | TBD | 2018-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | On-hold Jul-2010 pending SPR to complete preliminary work
WV | Hampshire County, WV | 54027 |  | MICS_10040 |  |  | 3 | [6 empty] | N/A | N/A | 2000-07-21 | N/A | N/A | N/A |  |  |  |  | 2002-05-07 | 2002-11-07
WV | Hancock County, WV | 54029 |  | 07-03-0223S | None |  | 4 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2009-01-30 | N/A | N/A | N/A |  |  |  |  | 2009-10-19 | 2010-04-19
WV | Hardy County, WV | 54031 |  | 06-03-A683S | PAL |  | 3 | Bob Pierson | Nicole Lick |  | WVU | N/A | AMEC | N/A | N/A | 2008-09-17 | N/A | N/A | N/A |  |  |  |  | 2009-03-02 | 2009-09-02
WV | Harrison County, WV | 54033 |  | MICS_12686 | Restudy |  | 11 | Bob Pierson | Mari Radford |  | USACE | N/A | RAMPP | N/A | N/A | 2010-12-13 | N/A | 2011-01-25 | N/A |  |  | 2012-01-07 |  | 2012-04-02 | 2012-10-02 |  | Revised preliminary
WV | Jackson County, WV | 54035 |  | MICS_10300 |  |  | 2 | [6 empty] | N/A | N/A | 2003-01-28 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-02-18 |  | 6/13/2013: will not make 10/2/2013 LFD date; mapping partner has requested new LFD date. 11/2012: Mapping Partner updated LFD date in MIP, from 5/17/2013
WV | Jefferson County, WV | 54037 |  | MICS_30414 | None |  | 6 | Bob Pierson | Nicole Lick |  | WVU | N/A | AMEC | N/A | N/A | 2008-12-31 | N/A | N/A | N/A |  |  |  |  | 2009-06-18 | 2009-12-18
WV | Kanawha County, WV | 54039 |  | MICS_12683 | [9 empty] | N/A | N/A | 2006-09-29 | N/A | N/A | N/A |  |  |  |  | 2007-08-06 | 2008-02-06
WV | Lewis County, WV | 54041 |  | 09-03-0139S | None |  | 3 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-05-20 | N/A | N/A | N/A |  |  |  |  | 2009-10-19 | 2010-04-19
WV | Lewis County, WV (SEE 09-03-0139S) | 54041 |  | 06-03-A684S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-05-20 | N/A | N/A | N/A |  |  |  |  | 2009-10-19 | 2010-04-19
WV | Lincoln County, WV | 54043 |  | MICS_16612 | None | 1 | 3 | Nikki Roberts | Henry Chau |  | USGS WV | N/A | GG3 | N/A | N/A | 2012-02-29 | N/A | 2012-05-10 | N/A | 2012-07-16 | 2012-10-24 | 2013-01-21 |  | 2013-04-16 | 2013-10-16
WV | Lincoln County, WV (Rev Prel for MICS_16612) | 54043 |  | 12-03-1933S |  |  |  | Nikki Roberts | Henry Chau |  |  |  |  | N/A | N/A | 2012-07-16 | N/A | N/A | N/A |  |  |  |  | N/A | N/A
WV | Logan County, WV | 54045 |  | MICS_11968 | [9 empty] | N/A | N/A | 2007-01-22 | N/A | N/A | N/A |  |  |  |  | 2007-08-06 | 2008-02-06 |  | On-hold Jul-2010 pending resolution of QR-2 issue (pending SPR)
WV | Lower Guyandotte Basin-Wide Study (Discovery) |  | 05070102 | 17-03-1357S | TBD |  | 0 | Bob Pierson | Heather Davis-Jenkins | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-08-22 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
WV | Marion County, WV | 54049 |  | MICS_16611 | Restudy |  | 12 | Bob Pierson | Mari Radford |  | USACE | N/A | RAMPP | N/A | N/A | 2010-09-28 | N/A | 2010-12-07 | N/A |  |  | 2011-10-12 |  | 2011-12-19 | 2012-06-19
WV | Marion County, WV - PMR | 54049 | 05020003 | 14-03-2356S | Zone A |  | 12 | Bob Pierson | Heather Davis-Jenkins | Gjones@dewberry.com | STARR | TBD | STARR II | 2014-06-09 | 2016-04-11 | 2017-07-31 |  | 2017-09-12 |  |  | 2018-02-07 | 2018-05-07 |  | 2018-10-05 | 2019-04-05
WV | Marshall County, WV | 54051 |  | 06-03-A642S |  |  | 6 | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2008-09-30 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
WV | Mason County, WV | 54053 |  | 06-03-A646S | Other BFE |  | 7 | Nikki Roberts | Henry Chau |  | USACE | N/A | GG3 | N/A | N/A | 2012-04-20 | N/A | N/A | N/A |  | 2012-11-08 | 2013-02-05 |  | 2013-06-03 | 2013-12-03
WV | McDowell County, WV | 54047 |  | MICS_11309 |  |  | 10 | [6 empty] | N/A | N/A | 2004-05-15 | N/A | N/A | N/A |  |  |  |  | 2004-12-16 | 2005-06-16
WV | McDowell County, WV - Tug Basin-Wide Study | 54047 |  | 17-03-0980S | Restudy |  | 11 | Lee Brancheau | Heather Davis-Jenkins | errol.dufour@stantec.com | STARR II | TBD | STARR II | 2012-06-13 | TBD | TBD | TBD | TBD | N/A |  | TBD | TBD |  | TBD | TBD
WV | Mercer County, WV | 54055 |  | MICS_19007 | [9 empty] | N/A | N/A | 2004-05-12 | N/A | N/A | N/A |  |  |  |  | 2004-09-02 | 2005-03-02
WV | Mineral County, WV | 54057 |  | 06-03-A685S | PAL |  | 7 | Bob Pierson | Mari Radford |  | WVU | N/A | AMEC | N/A | N/A | 2010-11-30 | N/A | 2011-02-23 | N/A |  |  |  |  | 2012-09-19 | 2013-03-19
WV | Mingo County, WV | 54059 |  | MICS_18125 | PAL |  | 6 | Jon Janowicz | Mari Radford |  | USACE | RAMPP | RAMPP | N/A | N/A | 2011-03-30 | N/A | 2011-06-14 | N/A |  |  | 2011-12-26 |  | 2012-04-02 | 2012-10-02
WV | Mingo County, WV - Tug Basin-Wide Study/R3 | 54059 |  | 12-03-0532S | Restudy |  | 4 | Lee Brancheau | Sarah Wolfe | kdunn@dewberry.com | Kentucky CTP | N/A | RAMPP | 2012-06-13 | 2014-03-31 | 2014-08-08 | 2014-03-31 | 2014-09-25 | N/A |  | 2015-04-24 | 2015-07-22 |  | 2016-02-17 | 2016-08-17
WV | Monongalia County, WV | 54061 |  | 09-03-0137S | None |  | 6 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-03-05 | N/A | N/A | N/A |  |  |  |  | 2009-07-20 | 2010-01-20
WV | Monongalia County, WV - PMR | 54061 | 05020003 | 14-03-2356S | Zone A |  | 6 | Bob Pierson | Heather Davis-Jenkins | Gjones@dewberry.com | STARR | TBD | STARR II | 2014-06-10 | 2016-04-12 | 2017-07-24 |  | 2017-09-12 |  |  | 2018-02-07 | 2018-05-07 |  | 2018-10-05 | 2019-04-05
WV | Monongalia County, WV (SEE 09-03-0137S) | 54061 |  | MICS_30415 |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-03-05 | N/A | N/A | N/A |  |  |  |  | 2009-07-20 | 2010-01-20
WV | Monroe County - WV Disaster County PMR | 54063 |  | 19-03-0002S | Restudy | 1 | 2 | Bob Pierson | Betsy Ranson | jason.sevanick@woodplc.com | Wood | USACE | Wood | N/A | 2019-05-29 | 2019-11-22 | N/A | 2019-12-10 | N/A | 2020-04-09 |  |  |  | TBD | TBD |  | Merged with Countywide Update (21-03-0007S)
WV | Monroe County, WV (MM) | 54063 |  | MICS_30900A | [9 empty] | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | 2001-12-17 | 2002-06-17
WV | Morgan County, WV | 54065 |  | 06-03-A686S | None |  | 3 | Bob Pierson | David Odegard |  | WVU | N/A | AMEC | N/A | N/A | 2008-02-28 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
WV | Nicholas County - WV Disaster County PMR | 54067 | 05050005 | 19-03-0002S | PENDING |  | 2 | Bob Pierson | Betsy Ranson | jason.sevanick@woodplc.com | Wood | TBD | TBD | N/A | 2019-05-29 | 2019-11-22 | N/A | 2019-12-10 |  |  | 2020-08-06 | 2020-11-04 |  | 2021-03-24 | 2021-09-24
WV | Nicholas County, WV | 54067 |  | 07-03-0224S | None |  | 3 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2009-09-30 | N/A | 2009-12-10 | N/A |  |  |  |  | 2011-01-04 | 2011-07-04
WV | Ohio County, WV | 54069 |  | MICS_11980 | [9 empty] | N/A | N/A | 2005-07-15 | N/A | N/A | N/A |  |  |  |  | 2006-01-17 | 2006-07-17
WV | Pendleton County, WV | 54071 |  | 09-03-0482S | None |  | 2 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-04-23 | N/A | N/A | N/A |  |  |  |  | 2009-09-02 | 2010-03-02
WV | Pendleton County, WV (SEE 09-03-0482S) | 54071 |  | 06-03-A688S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-04-23 | N/A | N/A | N/A |  |  |  |  | 2009-09-02 | 2010-03-02
WV | Pleasants County, WV | 54073 |  | 07-03-0229S |  |  | 3 | Nikki Roberts | Henry Chau |  | USACE | N/A | GG3 | N/A | N/A | 2012-04-30 | N/A | 2012-08-15 | N/A |  | 2013-05-01 | 2013-07-29 |  | 2013-11-05 | 2014-05-05
WV | Pocahontas County, WV | 54075 |  | 09-03-0348S | None |  | 4 | Nikki Roberts | Nicole Lick |  | GG3 | N/A | GG3 | N/A | N/A | 2009-10-16 | N/A | 2009-12-09 | N/A |  |  |  |  | 2010-05-04 | 2010-11-04
WV | Preston County, WV | 54077 |  | 07-03-0441S | Other BFE |  | 9 | Tiffany Keane | Nicole Lick |  | CVI / AECOM | N/A | RAMPP | N/A | N/A | 2010-06-21 | N/A | 2010-07-19 | N/A |  |  |  |  | 2011-12-05 | 2012-06-05 |  | Archived per direction of Lee Brancheau 3/6/19
WV | Putnam County, WV | 54079 |  | 09-03-1861S | Restudy |  | 8 | Nikki Roberts | Nicole Lick |  | USGS WV | N/A | GG3 | N/A | N/A | 2009-09-30 | N/A | 2009-12-11 | N/A |  |  |  |  | 2011-08-02 | 2012-02-02
WV | Putnam County, WV (FOR 09-03-1861S) | 54079 |  | MICS_11364 |  |  |  | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2009-09-30 | N/A | N/A | N/A |  |  |  |  | 2011-08-02 | 2012-02-02
WV | Raleigh County, WV | 54081 |  | MICS_11315 | [9 empty] | N/A | N/A | 2005-04-25 | N/A | N/A | N/A |  |  |  |  | 2006-03-29 | 2006-09-29
WV | Raleigh County, WV, PMR | 54081 |  | 08-03-0555S | Other BFE |  | 2 | Bob Pierson | David Odegard |  | Dewberry | N/A | AMEC | N/A | N/A | 2008-02-27 | N/A | N/A | N/A |  | 2008-04-07 | 2008-08-19 |  | 2008-12-16 | 2009-06-16
WV | Randolph County, WV | 54083 |  | 09-03-0141S | PAL/Other BFE |  | 8 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-05-27 | N/A | N/A | N/A |  | 2009-10-07 | 2010-01-19 |  | 2010-03-29 | 2010-09-29
WV | Randolph County, WV (SEE 09-03-0141S) | 54083 |  | 06-03-A689S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-05-27 | N/A | N/A | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
WV | Reedy Town, WV, PMR | 54087 |  | MICS_10087 |  |  | 1 | [6 empty] | N/A | N/A | 2002-12-02 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-03-02
WV | Ritchie County, WV | 54085 |  | 07-03-0227S | None |  | 7 | Nikki Roberts | Mari Radford |  | USACE | N/A | GG3 | N/A | N/A | 2010-07-30 | N/A | 2010-09-30 | N/A |  |  |  |  | 2011-08-02 | 2012-02-02
WV | Roane County, WV | 54087 |  | 07-03-0440S | Other BFE |  | 3 | Nikki Roberts | Mari Radford |  | USGS WV | N/A | GG3 | N/A | N/A | 2010-08-31 | N/A | N/A | N/A |  |  |  |  | 2011-09-02 | 2012-03-02 |  | Recent flooding as of 5/19/2009
WV | Smithers City, WV, PMR | 54019 |  | MICS_11597 |  |  | 2 | [6 empty] | N/A | N/A | 2002-11-27 | N/A | N/A | N/A |  |  |  |  | N/A | 2003-07-16 |  | Apr-2015: Case No. 14-03-2053S was rolled into this project; 30 day comment period ended 4/19/15.
WV | South Branch Potomac HUC8 |  | 02070001 | 19-03-0004S | Restudy |  | TBD | Bob Pierson | Darlene Messina | Rebecca.Wetzler@mbakerintl.com | TBD | TBD | TBD | 2018-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WV | Summers County - WV Disaster County PMR | 54089 | 05050004 | 19-03-0002S | PENDING |  | 2 | Bob Pierson | Betsy Ranson | jason.sevanick@woodplc.com | Wood | TBD | TBD | N/A | 2019-05-29 | 2019-11-22 | N/A | 2019-12-10 |  |  | 2020-08-12 | 2020-11-10 |  | 2021-04-07 | 2021-10-07
WV | Summers County, WV | 54089 |  | MICS_30127 | None |  | 2 | Bob Pierson | Nicole Lick |  | R1 PDC | N/A | Baker | N/A | N/A | 2008-10-31 | N/A | N/A | N/A |  |  |  |  | 2009-08-03 | 2010-02-03
WV | Taylor County, WV | 54091 |  | 06-03-A690S |  |  | 3 | Bob Pierson | Nicole Lick |  |  |  |  | N/A | N/A | 2008-02-28 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
WV | Taylor County, WV, PMR | 54091 |  | 10-03-0293S | Restudy |  | 3 | Bob Pierson | Nicole Lick |  | RAMPP | N/A | RAMPP | N/A | N/A | 2010-03-01 | N/A | 2010-05-26 | N/A |  | 2010-07-01 | 2010-10-01 |  | 2011-02-02 | 2011-08-02 |  | On-hold Jul-2010 pending SPR to complete preliminary work
WV | Tucker County, WV | 54093 |  | 09-03-0143S | None |  | 6 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-06-10 | N/A | N/A | N/A |  |  |  |  | 2010-01-06 | 2010-07-06 |  | On-hold Jul-2010 pending SPR to complete preliminary work
WV | Tucker County, WV (SEE 09-03-0143S) | 54093 |  | 06-03-A691S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-06-10 | N/A | N/A | N/A |  |  |  |  | 2010-01-06 | 2010-07-06
WV | Twelvepole Basin-Wide Study (Discovery) |  | 05090102 | 17-03-1356S | TBD |  | 0 | Bob Pierson | Heather Davis-Jenkins | Toni.Pignatelli@mbakerintl.com | RAP / Compass | N/A | N/A | 2017-08-22 | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A
WV | Tyler County, WV | 54095 |  | 07-03-0226S | None |  | 5 | Nikki Roberts | Nicole Lick |  | USACE | N/A | GG3 | N/A | N/A | 2009-04-30 | N/A | N/A | N/A |  |  |  |  | 2009-11-03 | 2010-05-03
WV | Upper Potomac, WV Hydrology | 54023 |  | 14-03-3023S |  |  |  | Bob Pierson | Ed Aquino |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
WV | Upper Potomac, WV Hydrology | 54031 |  | 14-03-3023S |  |  |  | Bob Pierson | Ed Aquino |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
WV | Upper Potomac, WV Hydrology | 54057 |  | 14-03-3023S |  |  |  | Bob Pierson | Ed Aquino |  |  |  |  | N/A | N/A | TBD | N/A | N/A | N/A |  |  |  |  | N/A | N/A
WV | Upshur County, WV | 54097 |  | 09-03-0144S | Other BFE |  | 2 | Bob Pierson | Nicole Lick |  | AMEC | N/A | AMEC | N/A | N/A | 2009-05-20 | N/A | N/A | N/A |  | 2009-10-23 | 2010-01-21 |  | 2010-03-29 | 2010-09-29
WV | Upshur County, WV (SEE 09-03-0144S) | 54097 |  | 06-03-A692S |  |  |  | Bob Pierson | [5 empty] | N/A | N/A | 2009-05-20 | N/A | N/A | N/A |  |  |  |  | 2010-03-29 | 2010-09-29
WV | Upshur County, WV, PMR (Fink Run) | 54097 |  | MICS_10621 |  |  | 1 | [6 empty] | N/A | N/A | 2001-12-20 | N/A | N/A | N/A |  |  |  |  | N/A | 2002-12-20
WV | Wayne County, WV | 54099 |  | MICS_16610 | PAL |  | 6 | Bob Pierson | Mari Radford |  | USACE | Dewberry | RAMPP | N/A | N/A | 2011-08-29 | N/A | 2011-09-27 | N/A |  |  |  |  | 2012-07-02 | 2013-01-02 |  | Preliminary delayed until late spring 2020 due to the new LiDAR being acquired and the modeling of the Nottoway River
WV | Wayne County, WV - Tug Basin-Wide Study/R3 | 54099 |  | 12-03-0532S | Restudy, Levee |  | 2 | Lee Brancheau | Sarah Wolfe | kdunn@dewberry.com | Kentucky CTP | N/A | RAMPP | 2012-06-13 | 2014-03-31 | 2014-08-08 | 2014-03-31 | 2014-09-25 | N/A |  | 2015-09-23 | 2015-12-21 |  | 2016-03-02 | 2016-09-02
WV | Wayne County, WV (PAL Ceredo and Kenova Levee Systems) | 54099 |  | 14-03-2053S |  |  | 0 | Bob Pierson | Sarah Wolfe |  |  |  |  | N/A | N/A | 2015-03-20 | N/A | TBD | N/A |  | TBD | TBD |  | 2016-05-04 | 2016-09-02
WV | Webster County - WV Disaster County PMR | 54101 | 05050005 | 19-03-0002S | Restudy |  | 2 | Bob Pierson | Betsy Ranson | jason.sevanick@woodplc.com | Wood | USACE | Wood | N/A | 2019-05-29 | 2019-11-22 | N/A | 2019-12-10 | N/A |  | 2020-11-12 | 2021-02-10 | N/A | 2021-11-03 | 2022-05-03
WV | Webster County, WV | 54101 |  | 07-03-1032S | None |  | 4 | Bob Pierson | Mari Radford |  | R1 PDC | N/A | AMEC | N/A | N/A | 2010-12-28 | N/A | N/A | N/A |  |  |  |  | 2011-07-06 | 2012-01-06
WV | Wetzel County, WV | 54103 |  | 06-03-A638S |  |  | 7 | Nikki Roberts | Nicole Lick |  |  |  |  | N/A | N/A | 2008-09-30 | N/A | N/A | N/A |  |  |  |  | 2009-03-25 | 2009-09-25
WV | White Sulphur Springs City, WV, PMR | 54025 |  | MICS_12605 |  |  | 1 | [6 empty] | N/A | N/A | 2003-01-02 | N/A | N/A | N/A |  |  |  |  | N/A | 2004-01-02
WV | Wirt County, WV | 54105 |  | 07-03-0225S | None |  | 2 | Nikki Roberts | Mari Radford |  | USACE | N/A | GG3 | N/A | N/A | 2011-02-04 | N/A | 2011-03-29 | N/A |  |  | 2011-08-08 |  | 2012-02-02 | 2012-08-02
WV | Wood County, WV | 54107 |  | 06-03-A644S | Other BFE |  | 5 | Nikki Roberts | Mari Radford |  | USACE | N/A | GG3 | N/A | N/A | 2012-03-30 | N/A | 2012-06-04 | N/A |  | 2012-11-08 | 2013-02-05 |  | 2013-05-06 | 2013-11-06
WV | Wyoming County, WV (Incl Oceana) | 54109 |  | MICS_30417 | [9 empty] | N/A | N/A | 2005-04-25 | N/A | N/A | N/A |  |  |  |  | 2005-11-16 | 2006-05-16

## SID Letters
STATE | PROJECT | MIP CASE NO | Study Manager | Engineering Model Notification (SID 620) | Flood Risk Review | Data Submission Notification (SID 621) | Preliminary | CCO Meeting | PSA (SID 622) | SID 622 Media Publish Date | Appeal Start
MD | Baltimore County, MD - Gunpowder-Patapsco Basin-Wide Study (24 Communities) | 11-03-2204S | dave.guignet@maryland.gov | N/A | 2019-11-22 | 2019-12-09 | 2020-08-12 | 2020-09-23 | 2021-07-08 | N/A | 2021-07-08
MD | Frederick County, MD - Monocacy Basin-Wide Study | 14-03-1939S | Brett.Holthaus@atkinsglobal.com | N/A | 2018-01-30 | N/A | 2018-09-28 | 2018-11-27 | 2021-04-29 | N/A | 2021-06-01
MD | Garrett County, MD - Kitzmiller and Blaine Levee PMR | 21-03-0011S | Craig.M.Thomas@usace.army.mil | 2019-03-07 | TBD | TBD | TBD | N/A | 2020-11-12 | TBD | TBD
MD | Howard County, MD - Countywide | 19-03-0041S | jonathan.langley@woodplc.com | 2021-01-22 | 2023-01-20 | TBD | TBD | TBD | TBD | TBD | TBD
MD | Montgomery County, MD - Middle Potomac-Catoctin Basin-Wide Study | 12-03-0415S | dave.guignet@maryland.gov | N/A | 2021-04-27 | TBD | 2023-01-31 | TBD | Future | N/A | TBD
MD | St. Mary's County, MD - Riverine Update | 19-03-0027S | dave.guignet@maryland.gov | 2019-01-11 | 2021-11-22 | Future | 2022-11-29 | 2023-01-15 | Future | N/A | TBD
NY, PA, OH, WV | Ohio River - Technical Data and Hydrology Investigation | 19-03-0042S | TBD | TBD | N/A | TBD | N/A | N/A | N/A | N/A | N/A
PA | Bedford County, PA (LAMP Everett Levee) | 14-03-2043S | james.barbis@woodplc.com | N/A | N/A | N/A | TBD | N/A | N/A | N/A | TBD
PA | Bradford County, PA - Upper Susquehanna River PMR - Bradford and Wyoming Counties | 16-03-0615S | justin.king@stantec.com | N/A | 2017-09-06 | PENDING | 2018-08-30 | 2018-12-12 | 6/12/2019 & 4/5/2021 | Future | 2021-04-01
PA | Bradford County, PA (LAMP Sayre PMR) | 16-03-0615S | justin.king@stantec.com | PENDING | 2019-06-25 | Future | N/A | N/A | N/A | N/A | TBD
PA | Carbon County, PA - Countywide (Lehigh) ¦ Weissport Pre-LAMP | 16-03-2422S | Rajendra.Rachamalla@atkinsglobal.com | 12/8/2017; 1/30/2020 | TBD | Future | TBD | TBD | Future | Future | TBD
PA | Columbia County, PA - Upper Susquehanna-Lackawanna Basin-wide | 15-03-0227S | matt.witosky@stantec.com | N/A | 2017-08-17 | N/A | 2019-05-31 | 2019-07-10 | Future | Future | 4/29/2021 & 5/19/2021
PA | Cumberland County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 15-03-0142S | brett.holthaus@atkinsglobal.com | N/A | 2016-12-05 | N/A | 2019-05-14 | 2019-06-26 | 2/3/2020 & 7/8/2021 | 2021-08-06 | 7/8/2021 & 8/5/2021
PA | Dauphin County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 15-03-0142S | matt.breen@wsp.com | N/A | 2018-06-04 | N/A | 2023-12-29 | TBD | Future | Future | TBD
PA | Eastwick - Darby Creek & Cobbs Creek Detailed Study | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
PA | Indiana County, PA (LAMP Cherry Tree Levees) | 14-03-2057S | mike.seering@aecom.com | N/A | TBD | N/A | TBD | N/A | N/A | N/A | TBD
PA | Lackawanna County - LAMP for Seclusion Areas for Scranton/Olyphant PMR | 17-03-0973S | brian.lee@stantec.com | 2018-04-19 | 2017-09-27 | PENDING | TBD | N/A | N/A | N/A | TBD
PA | Lackawanna County - LAMP for Seclusion Areas Spring Brook/Moosic | 17-03-0973S | kevin.donnelly@stantec.com | 2019-03-27 | 2019-02-26 | PENDING | TBD | N/A | N/A | N/A | TBD
PA | Lackawaxen Basin-Wide: Pike County | 16-03-2420S | Rajendra.Rachamalla@atkinsglobal.com | 2018-01-03 | 2018-11-19 | PENDING | TBD | TBD | Future | Future | TBD
PA | Lackawaxen Basin-Wide: Wayne County | 16-03-2420S | Rajendra.Rachamalla@atkinsglobal.com | 2018-01-03 | TBD | Future | TBD | TBD | Future | Future | TBD
PA | Lehigh County, PA - Countywide (Lehigh) | 16-03-2422S | Gjones@dewberry.com | 12/1/2017; 2/7/2020 | TBD | Future | 2020-07-18 | TBD | Future | Future | TBD
PA | Lehigh River - Updated Detailed Study | PENDING | Jason.F.Miller@usace.army.mil | 2019-03-06 | TBD | TBD | TBD | TBD | TBD | TBD | TBD
PA | Lower Juniata HUC8 - Discovery (Juniata River Basin) | 20-03-0001S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
PA | Luzerne County, PA - Upper Susquehanna-Lackawanna basin-wide | 15-03-0227S | matt.witosky@stantec.com | N/A | 2017-08-17 | N/A | 2020-09-15 | 2020-11-05 | 2021-07-01 | Future | 2021-07-02
PA | Luzerne County, PA (LAMP Duryea PMR) | 15-03-0227S | kevin.donnelly@stantec.com | N/A | 2020-07-07 | N/A | TBD | N/A | N/A | N/A | TBD
PA | Luzerne County, PA (LAMP Plymouth PMR) | 15-03-0227S | John.Shirley@stantec.com | N/A | 2020-01-24 | N/A | TBD | N/A | N/A | N/A | TBD
PA | Luzerne County, PA (LAMP Wilkes Barre Mill Creek PMR) | 15-03-0227S | kevin.donnelly@stantec.com | 2019-04-16 | 2019-08-29 | N/A | N/A | N/A | N/A | N/A | TBD
PA | Luzerne County, PA (LAMP Wilkes Barre, Hanover Twp. PMR) | 15-03-0227S | John.Shirley@stantec.com | N/A | 2020-01-24 | N/A | TBD | N/A | N/A | N/A | TBD
PA | Monroe County, PA - Countywide (Lehigh) ¦ Stroudsburg Pre-LAMP | 16-03-2422S | Rajendra.Rachamalla@atkinsglobal.com | 12/8/2017; 1/30/2020 | TBD | Future | TBD | TBD | Future | Future | TBD
PA | Montour County , PA (LAMP Danville - Mahoning Creek PMR) | 15-03-0227S | kevin.donnelly@stantec.com | N/A | 2020-10-28 | N/A | TBD | N/A | N/A | N/A | TBD
PA | Montour County , PA (LAMP Danville - State Hospital PMR) | 15-03-0227S | kevin.donnelly@stantec.com | N/A | 2020-10-28 | N/A | TBD | N/A | N/A | N/A | TBD
PA | Montour County , PA (LAMP Danville - Susq. River PMR) | 15-03-0227S | kevin.donnelly@stantec.com | N/A | 2020-10-28 | N/A | TBD | N/A | N/A | N/A | TBD
PA | Northampton County, PA | 21-03-0001S | pmadduri@tandmassociates.com | 2/4/2021; 7/7/2022 | N/A | TBD | N/A | TBD | TBD | TBD | TBD
PA | Northumberland County, PA - Lower Susquehanna-Penns Basin-Wide Study | 15-03-0140S | errol.dufour@stantec.com | N/A | 2017-08-17 | N/A | 2019-04-09 | 2019-07-09 | 2020-02-27 | Future | 2020-02-28
PA | Raystown HUC8 - Discovery (Juniata River Basin) | 20-03-0001S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
PA | Tioga County, PA (LAMP Tioga River Levee) | 15-03-0310S | james.barbis@woodplc.com | N/A | 2018-02-12 | N/A | TBD | TBD | Future | Future | TBD
PA | Upper Juniata HUC8 - Discovery (Juniata River Basin) | 20-03-0001S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
VA | Albemarle County and Charlottesville Ind City, VA - FIRM Update ¦ Scottsville Pre-LAMP | 20-03-0030S | noah.porter@aecom.com | 2019-05-28 | 2022-05-13 | Future | 2023-01-30 | 2023-03-01 | TBD | TBD | TBD
VA | Alexandria City, VA - Middle Potomac Anacostia Basin-Wide Study (Community Based) | 14-03-3327S | kevin.donnelly@stantec.com | 2019-04-24 | 2020-04-06 | N/A | 2020-09-30 | 2020-10-29 | 2021-07-21 | Future | 2022-12-12
VA | Amherst County, VA - FIRM Update | 20-03-0032S | boudjemaam@cdmsmith.com | 2018-11-01 | 2022-09-15 | Future | 2023-02-28 | 2023-04-14 | TBD | TBD | TBD
VA | Appomattox County, VA - FIRM Update | 20-03-0035S | agilman@tandmassociates.com | 2019-11-22 | TBD | Future | 2023-06-01 | 2023-07-16 | TBD | TBD | TBD
VA | Arlington County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | kevin.donnelly@stantec.com | 2019-04-24 | 2020-04-06 | N/A | 2020-09-18 | 2020-11-09 | 2021-07-22 | Future | 2022-10-06
VA | Banister HUC8 | 19-03-0032S | kdunn@tandmassociates.com | 2019-12-04 | TBD | N/A | N/A | N/A | N/A | N/A | N/A
VA | Brunswick County, VA - FIRM Update | 20-03-0040S | noah.porter@aecom.com | 2018-11-01 | 2022-09-15 | Future | 2023-01-31 | 2023-05-15 | TBD | TBD | TBD
VA | Buckingham County, VA - FIRM Update | 20-03-0041S | boudjemaam@cdmsmith.com | 2019-11-22 | 2022-09-09 | Future | 2023-02-28 | 2023-07-01 | TBD | TBD | TBD
VA | Caroline County, VA - Mattaponi Basin-Wide Study | 19-03-0013S | kdunn@tandmassociates.com | 2017-10-23 | 2020-09-17 | 2020-09-29 | 2021-06-01 | 2021-07-20 | 2022-02-22 | Future | 2022-02-22
VA | Charlotte County, VA - FIRM Update | 20-03-0042S | agilman@tandmassociates.com | 2019-12-04 | TBD | Future | 2023-06-01 | 2023-07-16 | TBD | TBD | TBD
VA | Cumberland County, VA - FIRM Update | 20-03-0026S | agilman@tandmassociates.com | 2019-05-25 | 2021-11-12 | 2021-11-19 | 2022-04-14 | 2022-09-19 | TBD | TBD | TBD
VA | Fairfax City, VA - Middle Potomac Anacostia Basin-Wide Study (Community Based) | 14-03-3327S | kevin.donnelly@stantec.com | 2019-03-18 | 2020-04-06 | N/A | 2020-09-25 | 2020-10-27 | 2021-07-09 | Future | 2022-10-06
VA | Fairfax County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | kevin.donnelly@stantec.com | 2019-03-18 | 2020-04-06 | N/A | 2021-04-30 | 2021-08-05 | Future | Future | TBD
VA | Falls Church City, VA - Middle Potomac Anacostia Basin-Wide Study (Community Based) | 14-03-3327S | errol.dufour@stantec.com | 2019-04-24 | 2020-04-06 | N/A | 2020-09-18 | 2020-10-21 | 2021-07-22 | Future | 2022-11-03
VA | Fauquier County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | matt.witosky@stantec.com | N/A | 2018-02-23 | N/A | 2020-09-15 | 2020-10-28 | 2021-05-12 | Future | 2021-05-11
VA | Fluvanna County, VA - FIRM Update | 20-03-0031S | noah.porter@aecom.com | TBD | 2022-05-13 | Future | 2022-11-30 | 2023-04-01 | TBD | TBD | TBD
VA | Franklin Independent City, VA - FIRM Update | 20-03-0036S | boudjemaam@cdmsmith.com | 2018-11-01 | TBD | Future | 2023-04-01 | 2023-07-02 | TBD | TBD | TBD
VA | Fredericksburg City, VA - Lower Rappahannock | 18-03-0012S | gjones@dewberry.com | 10/23/2017 (Zone A BLE only) | 2019-05-28 | 2019-06-11 | 2020-01-31 | 2020-03-03 | 2020-12-02 | Future | 2020-12-02
VA | Goochland County, VA - FIRM Update | 20-03-0027S | noah.porter@aecom.com | 2019-05-28 | 2021-11-12 | 2021-11-19 | 2022-05-24 | 2022-09-19 | TBD | TBD | TBD
VA | Greensville County and Emporia Independent City, VA - FIRM Update | 20-03-0043S | noah.porter@aecom.com | 2018-11-01 | 2022-09-15 | Future | 2023-01-31 | 2023-03-17 | TBD | TBD | TBD
VA | Hanover County, VA - Pamunkey Basin-Wide Study | 19-03-0021S | agilman@tandmassociates.com | 2019-02-01 | 2020-09-17 | 2020-09-29 | 2022-03-24 | 2022-09-19 | Future | Future | TBD
VA | Isle of Wight County, VA - Data Development & FIRM Update | 20-03-0037S | noah.porter@aecom.com | 2019-12-04 | 2023-03-01 | Future | 2023-04-01 | 2023-07-02 | N/A | N/A | TBD
VA | King William County, VA - Pamunkey Basin-Wide Study | 19-03-0010S | kdunn@tandmassociates.com | 2017-10-03 | 2020-09-17 | PENDING | 2021-06-01 | 2021-08-03 | 2022-02-24 | Future | 2022-02-09
VA | Lower Dan HUC8 - Data Development | 19-03-0032S | benjamin.kaiser@aecom.com | 2020-10-02 | N/A | TBD | N/A | N/A | TBD | TBD | N/A
VA | Lower James Basin- Chesterfield County | 16-03-2426S | errol.dufour@stantec.com | 2018-10-12 | 2020-04-28 | 2020-05-06 | 2021-06-14 | 2021-07-22 | Future | Future | 2022-12-12
VA | Lower James Basin- City of Colonial Heights | 16-03-2426S | errol.dufour@stantec.com | 2018-10-12 | 2020-04-28 | 2020-05-06 | 2021-02-12 | 2021-04-01 | 2021-10-21 | Future | 2022-12-12
VA | Lower James Basin- City of Hopewell | 16-03-2426S | Donald.syriani@stantec.com | 2018-04-09 | 2020-04-28 | 2020-05-06 | 2021-02-12 | 2021-03-31 | 2021-09-30 | Future | 2021-09-24
VA | Lower James Basin- City of Petersburg | 16-03-2426S | errol.dufour@stantec.com | 2018-04-09 | 2020-04-28 | 2020-05-06 | 2021-02-12 | 2021-03-25 | 2021-09-03 | Future | 2021-09-02
VA | Lower James Basin- City of Richmond | 16-03-2426S | kevin.donnelly@stantec.com | 2018-10-12 | 2021-07-28 | 2019-01-07 | 2022-02-02 | 2022-04-18 | Future | Future | TBD
VA | Lower James Basin- Henrico County | 16-03-2426S | Donald.syriani@stantec.com | 2019-04-05 | 2021-04-27 | 2021-05-06 | 2021-11-12 | 2021-12-09 | Future | Future | 2022-08-10
VA | Lower James Basin- Prince George County | 16-03-2426S | errol.dufour@stantec.com | 2018-04-09 | 2019-08-14 | 2019-09-06 | 2021-02-26 | 2021-03-29 | 2021-10-21 | Future | 2021-10-22
VA | Lunenburg County, VA - FIRM Update | 20-03-0028S | boudjemaam@cdmsmith.com | 2020-10-02 | 2022-09-15 | Future | 2023-01-31 | 2023-05-15 | TBD | TBD | TBD
VA | Lynchburg Independent City, VA - FIRM Update | 20-03-0033S | agilman@tandmassociates.com | 2019-11-22 | 2022-09-15 | Future | 2023-02-28 | 2023-04-14 | TBD | TBD | TBD
VA | Manassas City, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | matt.witosky@stantec.com | N/A | 2018-02-23 | N/A | 2020-09-30 | 2020-10-28 | 2021-05-12 | Future | 2021-05-13
VA | Manassas Park City, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | matt.witosky@stantec.com | N/A | 2018-02-23 | N/A | 2020-09-30 | 2020-10-28 | 2021-05-12 | Future | 2021-05-13
VA | Meherrin HUC8 | 19-03-0032S | mike.seering@aecom.com | 2019-12-04 | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A
VA | Middle James-Buffalo HUC8 | 18-03-0031S | Rajendra.Rachamalla@atkinsglobal.com | 2019-11-22 | 2022-09-09 | TBD | N/A | N/A | N/A | N/A | N/A
VA | Middle New HUC8 - Data Development | 19-03-0005S | mike.seering@aecom.com | 2020-10-02 | N/A | TBD | N/A | N/A | TBD | TBD | N/A
VA | Montgomery County, VA - Upper New Basin-Wide Study | 17-03-0960S | kevin.donnelly@stantec.com | 2017-10-04 | N/A | TBD | TBD | TBD | Future | Future | TBD
VA | Nelson County, VA - FIRM Update | 20-03-0034S | noah.porter@aecom.com | 2019-11-22 | 2022-09-09 | Future | 2023-02-28 | 2023-04-14 | TBD | TBD | TBD
VA | North Anna Pamunkey - Detailed H&H Study | 17-03-1358S | kdunn@tandmassociates.com | 2018-10-03 | N/A | TBD | N/A | N/A | N/A | N/A | N/A
VA | Powhatan County, VA - FIRM Update | 20-03-0029S | noah.porter@aecom.com | 2020-10-02 | 2021-11-12 | 2021-11-19 | 2022-05-24 | TBD | TBD | TBD | TBD
VA | Prince Edward County, VA - Countywide | 19-03-0018S | errol.dufour@stantec.com | 1/30/19 (Zone AE only) & PENDING (Zone A BLE & Zone AE) | 2020-07-10 | PENDING | 2021-04-14 | 2021-04-28 | 2022-02-07 | Future | 2022-02-16
VA | Prince William County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | matt.witosky@stantec.com | N/A | 2018-02-23 | N/A | 2020-09-30 | 2020-10-28 | 2021-05-12 | Future | 2021-05-13
VA | Pulaski County, VA - Upper New Basin-Wide Study | 18-03-0014S | Russell.Remy@stantec.com | 10/4/2017 (Zone A BLE only); 3/27/2019 | 2019-06-03 | 2019-06-18 | 2020-01-31 | 2020-02-20 | 2020-08-31 | Future | 2022-12-18
VA | REG Virginia Automated Engineering - FY18 BLE | 17-03-0914S | Daniel.Ahn@stantec.com | 2018-12-17 | N/A | TBD | N/A | N/A | N/A | N/A | N/A
VA | Rivanna HUC8 | 18-03-0031S | justin.king@stantec.com | 2019-12-23 | 2022-05-13 | TBD | N/A | N/A | N/A | N/A | N/A
VA | Roanoke Rapids HUC8 | 19-03-0032S | christine.estes@aecom.com | 2019-12-04 | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A
VA | Southampton County, VA - FIRM Update | 20-03-0038S | boudjemaam@cdmsmith.com | 2020-10-02 | TBD | Future | 2023-04-01 | 2023-07-02 | TBD | TBD | TBD
VA | Spotsylvania County, VA - Mattaponi Basin-Wide Study | 18-03-0011S | gjones@dewberry.com | 10/3/2017 (Zone A BLE only) | 2019-05-28 | 2019-06-11 | 2020-01-31 | 2020-03-03 | 12/2/2020 & 2/18/2022 | Future | 2022-02-22
VA | Stafford County, VA - Lower Potomac Basin | 18-03-0002S | agilman@tandmassociates.com | 2019-10-03 | 2019-03-11 | 2019-03-21 | 2019-12-23 | 2020-02-19 | 2020-09-30 | Future | 2022-03-25
VA | Suffolk City, VA - Data Development & FIRM Update | 20-03-0039S | noah.porter@aecom.com | 2019-12-04 | TBD | Future | 2023-04-01 | 2023-07-02 | N/A | N/A | TBD
VA | Sussex County VA - Data Development | 20-03-0025S | rebecca.starosta@aecom.com | 2020-10-02 | N/A | TBD | N/A | N/A | TBD | TBD | N/A
VA | Upper (Partial) and Middle Roanoke HUC8 | 19-03-0032S | kdunn@tandmassociates.com | 2019-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA | Upper Dan & Upper Yadkin HUC8 - Discovery | 19-03-0032S | christine.estes@aecom.com | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA | Upper Dan HUC8 - Data Development | 19-03-0032S | benjamin.kaiser@aecom.com | 2020-10-02 | N/A | TBD | N/A | N/A | TBD | TBD | N/A
VA | Upper Roanoke HUC8 - Data Development | 19-03-0032S | kdunn@tandmassociates.com | 2020-10-02 | N/A | TBD | N/A | N/A | TBD | TBD | N/A
VA | Upper Roanoke HUC8 - Discovery | 19-03-0032S | kdunn@tandmassociates.com | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VA | Upper Yadkin HUC8 - Data Development | 20-03-0023S | celiko@cdmsmith.com | 2020-10-02 | N/A | TBD | N/A | N/A | TBD | TBD | N/A
VA, WV | Tug HUC8 Flood Studies | 21-03-0025S | benjamin.kaiser@aecom.com | 2021-08-31 | 2022-06-23 | TBD | N/A | TBD | TBD | TBD | TBD
WV | Berkeley County, WV - Countywide Study | 21-03-0021S | brandon.cramer@woodplc.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Big Sandy HUC8 Flood Studies | 21-03-0025S | heather.zhao@aecom.com | 2021-08-30 | N/A | TBD | N/A | TBD | TBD | TBD | TBD
WV | Coal HUC8 - Discovery (Kanawha River Basin) | 21-03-0026S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Elk HUC8 - Discovery (Kanawha River Basin) | 19-03-0005S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Gauley HUC8 - Discovery (Kanawha River Basin) | 19-03-0005S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Greenbrier County, WV Countywide | 19-03-0028S | jonathan.langley@woodplc.com | 2019-02-19 | 2020-09-15 | 2020-09-18 | 2021-09-30 | 2021-10-25 | TBD | TBD | 2022-05-13
WV | Hampshire County, WV - Countywide | 21-03-0004S | jonathan.langley@woodplc.com | 2021-05-27 | TBD | Future | 2023-04-15 | TBD | TBD | TBD | TBD
WV | Hardy County, WV - Countywide | 21-03-0002S | brandon.cramer@woodplc.com | 2020-07-08 | 2021-09-15 | 2021-09-23 | 2022-04-14 | 2022-06-21 | TBD | TBD | TBD
WV | Hardy County, WV, (LAMP Moorefield Levees) | 11-03-0526S | james.barbis@woodplc.com | N/A | N/A | N/A | TBD | N/A | N/A | N/A | TBD
WV | Huntington, WV, LPP - Guyandotte | PENDING | TBD | 2019-03-09 | TBD | TBD | TBD | N/A | TBD | TBD | TBD
WV | Huntington, WV, LPP (Ohio River Floodwall) | PENDING | TBD | 2019-03-06 | 2019-08-27 | TBD | TBD | TBD | TBD | TBD | TBD
WV | Jefferson County, WV - Countywide | 21-03-0006S | yukun.xing@woodplc.com | Future | 2023-01-15 | Future | 2023-06-30 | TBD | TBD | TBD | TBD
WV | Kanawha County - WV Disaster County PMR | 19-03-0002S | jonathan.langley@woodplc.com | 2019-03-05 | 2019-05-30 | 2019-06-03 | 2019-12-13 | 2021-03-23 | Future | Future | 2022-05-20
WV | Lower Guyandotte HUC8 Flood Studies | 21-03-0026S | boudjemaam@cdmsmith.com | 2021-08-30 | N/A | TBD | N/A | TBD | TBD | TBD | TBD
WV | Lower Kanawha HUC8 - Discovery (Kanawha River Basin) | 19-03-0005S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Lower New HUC8 - Discovery (Kanawha River Basin) | 19-03-0005S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Mercer County Flood Studies | 19-03-0005S | mike.seering@aecom.com | 2021-08-30 | TBD | TBD | N/A | N/A | TBD | TBD | N/A
WV | Mineral County, WV - Kitzmiller and Blaine Levee PMR | 21-03-0011S | Craig.M.Thomas@usace.army.mil | 2019-03-06 | TBD | TBD | TBD | N/A | 2020-11-11 | TBD | TBD
WV | Mineral County, WV (LAMP Ridgeley Levee) | 14-03-1666S | james.barbis@woodplc.com | N/A | 2018-03-01 | N/A | TBD | N/A | N/A | N/A | TBD
WV | Monroe County WV - Countywide Update | 21-03-0007S | yukun.xing@woodplc.com | 2020-04-20 | 2022-05-31 | Future | 2022-10-31 | 2022-12-01 | TBD | TBD | TBD
WV | Monroe County WV - Countywide Update | 21-03-0007S | yukun.xing@woodplc.com | 2020-04-20 | 2022-05-31 | Future | 2022-10-31 | 2022-12-01 | TBD | TBD | TBD
WV | Morgan County, WV - Countywide Study | 21-03-0020S | jonathan.langley@woodplc.com | TBD | 2021-11-15 | TBD | TBD | TBD | TBD | TBD | TBD
WV | Pendleton County, WV - Countywide | 21-03-0003S | tyler.bruce@woodplc.com | 2020-04-20 | 2021-04-15 | 2021-04-26 | 2021-09-07 | 2021-09-14 | Future | Future | 2022-03-03
WV | Pocahontas County, WV - Countywide | 21-03-0005S | david.cooper@woodplc.com | 2021-05-27 | 2022-11-14 | Future | 2023-10-01 | TBD | TBD | TBD | TBD
WV | Raccoon-Symmes HUC8 Flood Studies | 21-03-0024S | rebecca.starosta@aecom.com | 2021-08-30 | N/A | TBD | N/A | N/A | TBD | TBD | TBD
WV | Summers County, WV - Countywide | 21-03-0008S | brandon.cramer@woodplc.com | 2020-04-22 | 2022-02-17 | Future | 2022-09-30 | TBD | TBD | TBD | TBD
WV | Twelvepole HUC8 Flood Studies | 21-03-0024S | rebecca.starosta@aecom.com | 2021-08-30 | N/A | TBD | N/A | TBD | TBD | TBD | TBD
WV | Upper Guyandotte HUC8 - Discovery | 19-03-0005S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Upper Guyandotte HUC8 Flood Studies | 21-03-0026S | heather.zhao@aecom.com | 2021-08-30 | N/A | TBD | N/A | TBD | TBD | TBD | TBD
WV | Upper Kanawha HUC8 - Discovery (Kanawha River Basin) | 19-03-0005S | matt.breen@wsp.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
WV | Upper Kanawha HUC8 - Discovery (Kanawha River Basin) | 19-03-0005S | william.jiang@aecom.com | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD

## MIP Hydraulic Locations
State | MIP Project Name | MIP Case # | PM / Provider | Project Name | Hydraulics Deliverable MIP Location
MD | Frederick County, MD - Monocacy Basin-Wide Study | 14-03-1939S | Brett Holthaus / STARR II | Monocacy Basin-Wide Study | K:/FY2014/14-03-1939S/Hydraulics - Frederick County, MD - 16/Hydraulic Data Capture - Hydraulic Data Capture 24021C - 1/Hydraulics Data Capture
PA | Adams County, PA - Monocacy Basin-Wide Study | 14-03-1939S | Gib Jones / STARR II | Monocacy Basin-Wide Study | K:/FY2014/14-03-1939S/Hydraulics - Adams County, PA - 12/Hydraulic Data Capture - Hydraulic Data Capture 42001C - 1/Hydraulics Data Capture
PA | Bradford County, PA - Upper Susquehanna River PMR - Bradford and Wyoming Counties | 16-03-0615S | Justin King / STARR II | Upper Susquehanna River PMR - Bradford and Wyoming Counties | K:/FY2016/16-03-0615S/Hydraulics(PMR) - Bradford County, PA - 10/Hydraulic Data Capture - Hydraulic Data Capture 42015C - 1
PA | Bradford County, PA (LAMP Sayre PMR) | 16-03-0615S | Justin King / STARR II | LAMP Sayre PMR | K:/FY2016/16-03-0615S/Hydraulics(PMR) - Bradford County, PA - 10/Hydraulic Data Capture - Hydraulic Data Capture 42015C - 1
PA | Columbia County, PA - Upper Susquehanna-Lackawanna basin-wide | 15-03-0227S | Matt Witosky / STARR II | Upper Susquehanna-Lackawanna basin-wide | K:/FY2015/15-03-0227S/Hydraulics - Columbia County, PA - 19/Hydraulic Data Capture - Hydraulic Data Capture 42037C - 1
PA | Cumberland County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 15-03-0142S | Brett Holthaus / STARR II | Lower Susquehanna-Swatara Basin-Wide Study | K:/FY2015/15-03-0142S/Hydraulics - Cumberland County, PA - 34/Hydraulic Data Capture - Hydraulic Data Capture 42041C - 1
PA | Dauphin County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 15-03-0142S | Brett Holthaus / STARR II | Lower Susquehanna-Swatara Basin-Wide Study | K:/FY2015/15-03-0142S/Hydraulics - Dauphin County, PA 95/Hydraulic Data Capture - USACE - Bullfrog Valley Creek - Hydraulics - 01
PA | Juniata County, PA - Lower Susquehanna-Penns Basin-Wide Study | 15-03-0140S | Errol Dufour / STARR II | Lower Susquehanna-Penns Basin-Wide Study | Hydraulics task not scoped for Juniata County, PA
PA | Lackawanna County - LAMP for Seclusion Areas for Scranton/Olyphant PMR | 17-03-0973S | Brian Lee / STARR II | LAMP for Seclusion Areas for Scranton/Olyphant PMR | J:/FY2017/17-03-0973S/Hydraulics - Lackawanna County, PA - 3/Hydraulic Data Capture - Hydraulic Data Capture 42069C - 1
PA | Lackawanna County - LAMP for Seclusion Areas Spring Brook/Moosic | 17-03-0973S | Brian Lee / STARR II | LAMP for Seclusion Areas Spring Brook/Moosic | J:/FY2017/17-03-0973S/Hydraulics - Lackawanna County, PA - 3/Hydraulic Data Capture - Hydraulic Data Capture 42069C - 1
PA | Lackawaxen Basin-Wide: Pike County | 16-03-2420S | Sabu Paul / STARR II | Lackawaxen Basin-Wide | K:/FY2016/16-03-2420S/Hydraulics - Pike County, PA - 42103C - Countywide 08/Hydraulic Data Capture - Hydraulic Data Capture - Pike County, PA - 42103C - Countywide - 01
PA | Lackawaxen Basin-Wide: Wayne County | 16-03-2420S | Sabu Paul / STARR II | Lackawaxen Basin-Wide | K:/FY2016/16-03-2420S/Hydraulics - Wayne County, PA - 42127C - Countywide 19/Hydraulic Data Capture - Hydraulics Data Capture - Wayne County, PA - 42127C - Countywide - 01
PA | Lehigh Watershed - Carbon County | 16-03-2422S | Sabu Paul / STARR II | Lehigh Watershed | K:/FY2016/16-03-2422S/Hydraulics - Carbon County, PA - 42025C - Countywide 23/Hydraulic Data Capture - Hydraulics Data Capture - Carbon County, PA - 42025C - 01
PA | Lehigh Watershed - Lehigh County | 16-03-2422S | Gib Jones / STARR II | Lehigh Watershed | K:/FY2016/16-03-2422S/Hydraulics - Lehigh County, PA - 42077C - Countywide 11/Hydraulic Data Capture - Hydraulic Data Capture - Lehigh County, PA - Countywide - 01/02040106
PA | Lehigh Watershed - Monroe County | 16-03-2422S | Sabu Paul / STARR II | Lehigh Watershed | K:/FY2016/16-03-2422S/Hydraulics - Monroe County, PA - 42089C - Countywide 34/Hydraulic Data Capture - Hydraulic Data Capture - Monroe County, PA - 42089C - Countywide - 01/Hydraulics Data Capture
PA | Luzerne County, PA - Upper Susquehanna-Lackawanna basin-wide | 15-03-0227S | Matt Witosky / STARR II | Upper Susquehanna-Lackawanna basin-wide | K:/FY2015/15-03-0227S/Hydraulics - Columbia County, PA - 19/Hydraulic Data Capture - Hydraulic Data Capture 42037C - 1/02050107
PA | Luzerne County, PA (LAMP Duryea PMR) | 15-03-0227S | Brian Lee / STARR II | LAMP Duryea PMR | K:/FY2015/15-03-0227S/Hydraulics - Luzerne County, PA - 42079C - Duryea Flood Protection Project 70/Hydraulic Data Capture - Hydraulic Data Capture - Duryea Flood Protection Project - 2305410001 - 01
PA | Luzerne County, PA (LAMP Plymouth PMR) | 15-03-0227S | Brian Lee / STARR II | LAMP Plymouth PMR | K:/FY2015/15-03-0227S/Hydraulics - Luzerne County, PA - 42079C - Plymouth Levee System 62/Hydraulic Data Capture - Hydraulic Data Capture - Plymounth Levee System - 2305330002 - 01
PA | Luzerne County, PA (LAMP Wilkes Barre Mill Creek PMR) | 15-03-0227S | Prabha Madduri / STARR II | LAMP Wilkes Barre Mill Creek PMR | K:/FY2015/15-03-0227S/Hydraulics - Luzerne County, PA - 42079C - Wilkes-Barre - Mill Creek Levee System 79/Hydraulic Data Capture - Hydraulics Data Capture - Wilkes-Barre - Mill Creek Levee System - 1305000359 - 01
PA | Luzerne County, PA (LAMP Wilkes Barre, Hanover Twp. PMR) | 15-03-0227S | Brian Lee / STARR II | LAMP Wilkes Barre, Hanover Twp. PMR | K:/FY2015/15-03-0227S/Hydraulics - Luzerne County, PA - 42079C - Wilkes-Barre - Hanover Levee System 66/Hydraulic Data Capture - Hydraulic Data Capture - Wilkes-Barre - Hanover Levee System - 2305330003 - 01
PA | Montour County , PA (LAMP Danville - Mahoning Creek PMR) | 15-03-0227S | Brian Lee / STARR II | LAMP Danville - Mahoning Creek PMR | J:/FY2015/15-03-0227S/Hydraulics - Montour County, PA - 42093C - Mahoning Creek Levee System 51/Hydraulic Data Capture - Hydraulic DCS-Mahoning Creek Levee System (Danville - Mahoning Creek - RB)-2305400004 - 01
PA | Montour County , PA (LAMP Danville - State Hospital PMR) | 15-03-0227S | Brian Lee / STARR II | LAMP Danville - State Hospital PMR | J:/FY2015/15-03-0227S/Hydraulics - Montour County, PA - 42093C - State Hospital Levee System 47/Hydraulic Data Capture - Hydraulic DCS-State Hospital Levee System (Danville Upper Susq-Hospital Run LB)-2305400003 - 01
PA | Montour County , PA (LAMP Danville - Susq. River PMR) | 15-03-0227S | Brian Lee / STARR II | LAMP Danville - Susq. River PMR | J:/FY2015/15-03-0227S/Floodplain Mapping - Montour County, PA - 42093C - Susquehanna River Levee System 56/Floodplain Mapping Data Capture - Floodplain Mapping DCS-Susq River Levee System (Danville - Lower Susq-Mahoning Cr)-2305400001 - 01
PA | Montour County, PA - Upper Susquehanna-Lackawanna basin-wide | 15-03-0227S | Matt Witosky / STARR II | Upper Susquehanna-Lackawanna basin-wide | K:/FY2015/15-03-0227S/Hydraulics - Columbia County, PA - 19/Hydraulic Data Capture - Hydraulic Data Capture 42037C - 1/02050107
PA | Northumberland County, PA - Lower Susquehanna-Penns Basin-Wide Study | 15-03-0140S | Errol Dufour / STARR II | Lower Susquehanna-Penns Basin-Wide Study | K:/FY2015/15-03-0140S/Hydraulics - Northumberland County, PA - 37/Hydraulic Data Capture - Hydraulic Data Capture 42097C - 1 K:/FY2015/15-03-0140S/Hydraulics - Northumberland County, PA - 37/Hydraulic Data Capture - Hydraulic Data Capture 42097C - 1/02050301/Shamokin_Creek
PA | Perry County, PA - Lower Susquehanna-Swatara Basin-Wide Study | 15-03-0142S | Brett Holthaus / STARR II | Lower Susquehanna-Swatara Basin-Wide Study | K:/FY2015/15-03-0142S/Hydraulics - Adams County, PA - 31/Hydraulic Data Capture - Hydraulic Data Capture 42001C - 1
PA | Schuylkill County, PA - Schuylkill Basin-Wide Study | 11-03-2055S | Gib Jones / STARR II | Schuylkill Basin-Wide Study | K:/FY2011/11-03-2055S/Hydraulics - Schuylkill County, PA - 15/Hydraulic Data Capture - Hydraulic Data Capture 42107C - 1/Schuylkill_County
PA | Snyder County, PA - Lower Susquehanna-Penns Basin-Wide Study | 15-03-0140S | Errol Dufour / STARR II | Lower Susquehanna-Penns Basin-Wide Study | K:/FY2015/15-03-0140S/Hydraulics - Centre County, PA - 36/Hydraulic Data Capture - Hydraulic Data Capture 42097C – 5
PA | Union County, PA - Lower Susquehanna-Penns Basin-Wide Study | 15-03-0140S | Errol Dufour / STARR II | Lower Susquehanna-Penns Basin-Wide Study | K:/FY2015/15-03-0140S/Hydraulics - Centre County, PA - 36/Hydraulic Data Capture - Hydraulic Data Capture 42097C – 5
PA | Wyoming County, PA - Upper Susquehanna River PMR - Bradford and Wyoming Counties | 16-03-0615S | Justin King / STARR II | Upper Susquehanna River PMR - Bradford and Wyoming Counties | K:/FY2016/16-03-0615S/Hydraulics(PMR) - Bradford County, PA - 10/Hydraulic Data Capture - Hydraulic Data Capture 42015C - 1
VA | Albemarle County, VA | 20-03-0030S | Noah Porter / Compass | STARR FY17 BLE STARR MJW STARR Rivanna | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03 K:/FY2018/18-03-0031S/Hydraulics - STARR Rivanna HUC 8 - 02080204 33/Hydraulic Data Capture - Hydraulic Data Capture - STARR Rivanna HUC 8 - 02080204 - 03
VA | Alexandria City, VA - STARR Middle Potomac Anacostia Basin-Wide Study (Community Based) | 14-03-3327S | Brian Lee / STARR II | STARR Middle Potomac Anacostia Basin-Wide Study | K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3 K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/Four_Mile_Run
VA | Amelia County, VA - STARR Appomattox Basin Study | 19-03-0015S | Matt Witosky / STARR II | STARR Appomattox Basin Study | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Amherst County, VA | 20-03-0032S | Scott Yi / Compass | STARR FY18 BLE STARR MJB | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Appomatox County, VA | 20-03-0035S | Alex Gilman / Compass | STARRFY17BLE STARR MJB Compass Upper/Middle Roanoke | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2019/19-03-0032S/Hydraulics - Compass Upper (Partial) and Middle Roanoke HUC8 - 03010102 - 26/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Upper (Partial) and Middle Roanoke HUC8 - 01
VA | Arlington County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | Brian Lee / STARR II | STARR Middle Potomac Anacostia Basin-Wide / FY15 LSAE | K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/02070010 K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/Four_Mile_Run
VA | Banister HUC8 | 19-03-0032S | Kim Dunn / Compass | Compass Banister HUC8 | K:/FY2019/19-03-0032S/Hydraulics - Banister HUC8 - 03010105 11/Hydraulic Data Capture - Hydraulic Data Capture Task - Banister HUC8 - 01
VA | Brunswick County, VA | 20-03-0040S | Noah Porter / Compass | STARR FY18 BLE Compass Roanoke Rapids Compass Meherrin | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01 K:/FY2019/19-03-0032S/Hydraulics - Compass Roanoke Rapids HUC8 - 03010106 - 17/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Roanoke Rapids HUC8 - 03010106 - 01 K:/FY2019/19-03-0003S/Hydraulics - Compass Meherrin HUC8 - 03010204 - 13/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Meherrin HUC8 - 01
VA | Buckingham County, VA | 20-03-0041S | Scott Yi / Compass | STARR FY18 BLE STARR MJB | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01
VA | Campbell County, VA | TBD | TBD | STARR FY18 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Caroline County, VA - Mattaponi Basin-Wide Study | 19-03-0013S | Kim Dunn / Compass | STARR FY16 LSAE East Compass Caroline County detailed H&H Compass North Anna Pamunkey Detailed H&H | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2019/19-03-0013S/Hydraulics - Caroline County, VA - 51033C 05/Hydraulic Data Capture - Hydraulic Data Capture - Caroline County, VA - 51033C - 01 K:/FY2017/17-03-1358S/Hydraulics - North Anna and Pamunkey Riverine H and H 14/Hydraulic Data Capture - Hydraulics Data Capture - North Anna and Pamunkey Riverine H and H - 01
VA | Charlotte County, VA | 20-03-0042S | Alex Gilman / Compass | STARRFY17BLE STARR MJB Compass Upper/Middle Roanoke | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2019/19-03-0032S/Hydraulics - Compass Upper (Partial) and Middle Roanoke HUC8 - 03010102 - 26/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Upper (Partial) and Middle Roanoke HUC8 - 01
VA | Charlottesville Ind City, VA | 20-03-0030S | Noah Porter / Compass | STARR FY17 BLE STARR MJW STARR Rivanna | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03 K:/FY2018/18-03-0031S/Hydraulics - STARR Rivanna HUC 8 - 02080204 33/Hydraulic Data Capture - Hydraulic Data Capture - STARR Rivanna HUC 8 - 02080204 - 03
VA | Emporia Independent City, VA | 20-03-0043S | Noah Porter / Compass | STARR FY18 BLE Compass Roanoke Rapids Compass Meherrin | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01 K:/FY2019/19-03-0032S/Hydraulics - Compass Roanoke Rapids HUC8 - 03010106 - 17/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Roanoke Rapids HUC8 - 03010106 - 01 K:/FY2019/19-03-0003S/Hydraulics - Compass Meherrin HUC8 - 03010204 - 13/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Meherrin HUC8 - 01
VA | Cumberland County, VA | 20-03-0026S | Alex Gilman / Compass | STARR FY17 BLE STARR MJW | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03
VA | Culpeper County, VA - Rapidan-Rappahannock Basin-Wide Study (Countywide) | 18-03-0004S | Gib Jones / STARR II | STARR Rapidan-Rappahannock Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Dinwiddie County, VA - Nottoway Basin-Wide Study | 19-03-0016S | Matt Witosky / STARR II | Nottoway Basin-Wide Study / STARR FY17 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | Essex County, VA | 19-03-0006S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Fairfax City, VA - STARR Middle Potomac Anacostia Basin-Wide Study (Community Based) | 14-03-3327S | Brian Lee / STARR II | STARR Middle Potomac Anacostia Basin-Wide / FY15 LSAE | K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/02070010
VA | Fairfax County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | Brian Lee / STARR II | STARR Middle Potomac Anacostia Basin-Wide / FY15 LSAE | K:/FY2014/14-03-3327S/Hydraulics - Fairfax County, VA - Zone AE 85/Hydraulic Data Capture - Hydraulic Data Capture - Fairfax County, VA - 51059C - Zone AE - 01
VA | Falls Church City, VA - STARR Middle Potomac Anacostia Basin-Wide Study (Community Based) | 14-03-3327S | Brian Lee / STARR II | STARR Middle Potomac Anacostia Basin-Wide / FY15 LSAE | K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/02070010 K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/Four_Mile_Run
VA | Fauquier County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | Matt Witosky / STARR II | STARR Middle Potomac Anacostia Basin-Wide / FY15 LSAE | K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/02070010 K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3/02080103/Craig_Run
VA | Fluvanna County, VA | 20-03-0031S | Noah Porter / Compass | STARR FY17 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01
VA | Frederick County, VA - STARR Conococheague-Opequon Basin-Wide Study | 12-03-0413S | Errol Dufour / STARR II | STARR Conococheague-Opequon Basin-Wide Study | K:/FY2012/12-03-0413S/Hydraulics - Frederick County, VA - 66/Hydraulic Data Capture - Hydraulic Data Capture 51069C - 1
VA | Fredericksburg City, VA - Lower Rappahannock | 18-03-0012S | Gib Jones / STARR II | STARR Lower Rappahannock / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2018/18-03-0012S/Hydraulics - City of Fredericksburg, VA - 510065 07/Hydraulic Data Capture - Hydraulics - Fredericksburg, VA - 510065 - Hazel Run - 01/Hydraulics Data Capture
VA | Gloucester County, VA | 19-03-0007S | Alex Gilman / Compass | STARR STARR FY16 LSAE East / STARR FY17 LSAE | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02
VA | Goochland County, VA | 20-03-0027S | Noah Porter / Compass | STARR FY17 BLE STARR MJW | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03
VA | Greene County, VA - Rapidan-Rappahannock Basin-Wide Study | 18-03-0008S | Brian Lee / STARR II | STARR Rapidan-Rappahannock Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Greensville County, VA | 20-03-0043S | Noah Porter / Compass | STARR FY18 BLE Compass Roanoke Rapids Compass Meherrin | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01 K:/FY2019/19-03-0032S/Hydraulics - Compass Roanoke Rapids HUC8 - 03010106 - 17/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Roanoke Rapids HUC8 - 03010106 - 01 K:/FY2019/19-03-0003S/Hydraulics - Compass Meherrin HUC8 - 03010204 - 13/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Meherrin HUC8 - 01
VA | Hanover County, VA | 19-03-0021S | Justin King / STARR II; Alex Gilman / Compass | STARR STARR FY16 LSAE East / STARR FY17 LSAE Compass North Anna Pamunkey detailed H&H STARR Detailed H&H | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02 K:/FY2017/17-03-1358S/Hydraulics - North Anna and Pamunkey Riverine H and H 14/Hydraulic Data Capture - Hydraulics Data Capture - North Anna and Pamunkey Riverine H and H - 01 K:/FY2019/19-03-0021S/Hydraulics - Hanover County, VA - 51085C 06/Hydraulic Data Capture - Hydraulic Data Capture - Hanover County, VA - 51085C - 01
VA | James City, County | TBD | TBD | STARR FY17 LSAE | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02
VA | King and Queen County, VA | 19-03-0008S | Alex Gilman / Compass | STARR STARR FY16 LSAE East / STARR FY17 LSAE | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02
VA | King George County, VA - Lower Potomac Basin-Wide Study | 19-03-0009S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | King William County, VA | 19-03-0010S | Kim Dunn / Compass | STARR STARR FY16 LSAE East / STARR FY17 LSAE Compass North Anna Pamunkey detailed H&H | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1 K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02 K:/FY2017/17-03-1358S/Hydraulics - North Anna and Pamunkey Riverine H and H 14/Hydraulic Data Capture - Hydraulics Data Capture - North Anna and Pamunkey Riverine H and H - 01
VA | Lancaster County, VA | 18-03-0032S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Louisa County, VA - Pamunkey Basin-Wide Study | 18-03-0010S | Matt Witosky / STARR II | STARR Pamunkey Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | STARR Lower James Basin- Charles City | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- Chesterfield County | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- City of Colonial Heights | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- City of Hopewell | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- City of Petersburg | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- City of Richmond | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- Henrico County | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- Prince George County | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | STARR Lower James Basin- Surry County | 16-03-2426S | Donald Syriani / STARR II | STARR Lower James Basin | J:/FY2016/16-03-2426S/Hydraulics - Lower James Watershed - Multi County and Ind City Deliverable 08/Hydraulic Data Capture - Hydraulic Data Capture - Lower James Watershed - Multi County and Ind City - 01/LowerJamesWatershed
VA | Lunenburg County, VA | 20-03-0028S | Scott Yi / Compass | STARR FY18 BLE Compass Roanoke Rapids Compass Meherrin | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01 K:/FY2019/19-03-0032S/Hydraulics - Compass Roanoke Rapids HUC8 - 03010106 - 17/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Roanoke Rapids HUC8 - 03010106 - 01 K:/FY2019/19-03-0003S/Hydraulics - Compass Meherrin HUC8 - 03010204 - 13/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Meherrin HUC8 - 01
VA | Lynchburg Independent City, VA | 20-03-0033S | Alex Gilman / Compass | STARR FY18 BLE STARR MJB | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Madison County, VA -Rapidan-Rappahannock Basin-Wide Study (Countywide) | 18-03-0007S | Gib Jones / STARR II | STARR Rapidan-Rappahannock Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Mathews County, VA | TBD | TBD | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Compass Meherrin HUC8 | 19-03-0003S | Mike Seering/Compass | Compass Meherrin HUC8 | K:/FY2019/19-03-0003S/Hydraulics - Compass Meherrin HUC8 - 03010204 - 13/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Meherrin HUC8 - 01
VA | Middlesex County, VA | 19-03-0011S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | STARR Middle James River - Detailed H&H | 18-03-0031S | Sabu Paul / STARR II | STARR Middle James River - Detailed H&H | K:/FY2018/18-03-0031S/Hydraulics - MIDDLE JAMES RIVER - ZONE AE RESTUDY - Multi HUC8 and County 16/Hydraulic Data Capture - Hydraulic Data Capture - MIDDLE JAMES RIVER - ZONE AE RESTUDY - 01
VA | Middle James-STARR Buffalo HUC8 | 18-03-0031S | Sabu Paul / STARR II | STARR Buffalo HUC8 | K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03
VA | Middle James-STARR Willis HUC8 | 18-03-0031S | Sabu Paul / STARR II | STARR Willis HUC8 | K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03
VA | Montgomery County, VA - Upper New Basin-Wide Study | 17-03-0960S | Kevin Donnelly / STARR II | STARR Upper New Basin-Wide Study / FY16 LSAE West | K:/FY2017/17-03-0960S/Hydraulics - Pulaski County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51155C - 1
VA | Nelson County, VA | 20-03-0034S | Noah Porter / Compass | STARR FY18 BLE STARR MJB | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | New Kent County, VA | 19-03-0012S | Noah Porter / Compass | STARR FY17 LSAE | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02
VA | Northumberland County, VA | 18-03-0033S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Nottoway County, VA - Nottoway, STARR Appomattox Basin Study | 19-03-0017S | Matt Witosky / STARR II | STARR Appomattox Basin Study / STARR FY17 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01
VA | Orange County,VA - Rapidan-Rappahannock Basin-Wide Study | 18-03-0009S | Matt Witosky / STARR II | STARR Rapidan-Rappahannock Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02 K:/FY2018/18-03-0009S/Hydraulics - Orange County, VA - 51137C 08/Hydraulic Data Capture - Hydraulic Data Capture - Orange County, VA - 51137C - 01/Orange_County_Watershed
VA | Powhatan County, VA | 20-03-0029S | Noah Porter / Compass | STARR FY17 BLE STARR MJW | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2018/18-03-0031S/Hydraulics - Middle James - Willis HUC 8 - 02080205 40/Hydraulic Data Capture - Hydraulic Data Capture - Middle James - Willis HUC 8 - 02080205 - 03
VA | STARR Prince Edward County, VA - Countywide | 19-03-0018S | Errol Dufour / STARR II | STARR Prince Edward County, VA - Countywide | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County and HUC8 - STARR FY17 BLE 23/Hydraulic Data Capture - Hydraulics Data Capture - Multi County, VA - Auto Eng - STARR FY17 BLE - STARR II - 01 K:/FY2019/19-03-0018S/Hydraulics - Prince Edward County, VA - 51147C 07/Hydraulic Data Capture - Hydraulics Data Capture - Prince Edward County, VA - 51147C - 01
VA | Prince William County, VA - Middle Potomac Anacostia Basin-Wide (Countywide) 14-03-3327S | 14-03-3327S | Matt Witosky / STARR II | STARR Middle Potomac Anacostia Basin-Wide / FY15 LSAE | K:/FY2014/14-03-3327S/Hydraulics - Arlington County, VA - 17/Hydraulic Data Capture - Hydraulic Data Capture 51013C - 3 K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Pulaski County, VA - Upper New Basin-Wide Study | 18-03-0014S | Matt Witosky / STARR II | STARR Upper New Basin-Wide Study / FY16 LSAE West | K:/FY2017/17-03-0960S/Hydraulics - Pulaski County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51155C - 1 K:/FY2018/18-03-0014S/Hydraulics - Pulaski County, VA - 51155C 06/Hydraulic Data Capture - Hydraulic Data Capture - Pulaski County, VA - 51155C - 01
VA | Radford City, VA - Upper New Basin-Wide Study | 18-03-0015S | Matt Witosky / STARR II | STARR Upper New Basin-Wide Study / FY16 LSAE West | K:/FY2017/17-03-0960S/Hydraulics - Pulaski County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51155C - 1
VA | Rappahannock County, VA - Rapidan-Rappahannock Basin-Wide Study (Countywide) | 18-03-0006S | Gib Jones / STARR II | STARR Rapidan-Rappahannock Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | REG Virginia Automated Engineering - STARR FY18 BLE | 17-03-0914S | Daniel Ahn / STARR II | STARR FY18 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Richmond County, VA | 18-03-0034S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | STARR Rivanna HUC8 | 18-03-0031S | Justin King / STARR II | STARR Rivanna HUC8 | K:/FY2018/18-03-0031S/Hydraulics - STARR Rivanna HUC 8 - 02080204 33/Hydraulic Data Capture - Hydraulic Data Capture - STARR Rivanna HUC 8 - 02080204 - 03
VA | Roanoke County, VA | TBD | TBD | STARR FY16 LSAE West Compass Upper Roanoke HUC8 | K:/FY2017/17-03-0960S/Hydraulics - Pulaski County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51155C - 1
VA | Compass Roanoke Rapids HUC8 | 19-03-0032S | Christine Estes/Compass | Compass Roanoke Rapids HUC8 | K:/FY2019/19-03-0032S/Hydraulics - Compass Roanoke Rapids HUC8 - 03010106 - 17/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Roanoke Rapids HUC8 - 03010106 - 01
VA | Southhampton County, VA | 20-03-0038S | Scott Yi / Compass | STARR FY18 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Spotsylvania County, VA - Mattaponi Basin-Wide Study | 18-03-0011S | Gib Jones / STARR II | STARR Mattaponi Basin-Wide Study / STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Stafford County, VA - Lower Potomac Basin | 18-03-0002S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Sussex County, VA | 20-03-0025S | Rebecca Starosta / Compass | STARR FY18 BLE | K:/FY2017/17-03-0914S/Hydraulics - VA South East - Multi County and HUC8 - STARR FY18 BLE 29/Hydraulic Data Capture - Hydraulic Data Capture - FY18 SE VA BLE - Multi County and HUC8 - 01
VA | Compass Upper (Partial) and Middle Roanoke HUC8 | 19-03-0032S | Kim Dunn / Compass | Compass Upper (Partial) and Middle Roanoke HUC8 | K:/FY2019/19-03-0032S/Hydraulics - Compass Upper (Partial) and Middle Roanoke HUC8 - 03010102 - 26/Hydraulic Data Capture - Hydraulic Data Capture Task - Compass Upper (Partial) and Middle Roanoke HUC8 - 01
VA | Westmoreland County, VA | 19-03-0001S | Alex Gilman / Compass | STARR FY16 LSAE East | K:/FY2017/17-03-0914S/Hydraulics - Spotsylvania County, VA - 7/Hydraulic Data Capture - Hydraulic Data Capture 51177C - 1
VA | Winchester City, VA - STARR Conococheague-Opequon Basin-Wide Study | 12-03-0413S | Errol Dufour / STARR II | STARR Conococheague-Opequon Basin-Wide Study | K:/FY2012/12-03-0413S/Hydraulics - Frederick County, VA - 66/Hydraulic Data Capture - Hydraulic Data Capture 51069C - 1
VA | York County, VA | TBD | TBD | STARR FY17 LSAE | K:/FY2017/17-03-0914S/Hydraulics - VA Automated Engineering - Multi County - Addl Data Dev 17/Hydraulic Data Capture - Hydraulic Data Capture - Multi-County, VA - Auto Eng - Addl Data Dev - STARR II - 02
WV | McDowell County, WV - Tug Basin-Wide Study | 17-03-0980S | Errol Dufour / STARR II | Tug Basin-Wide Study | Hydraulics task not scoped for McDowell County, WV

## FBS Tracker (hidden)
Legend
COMPLETED
NEED ATTENTION - ALREADY PRELIM 30+ days - PAST DUE
RECENTLY PRELIMINARY - NEED FBS CERTIFICATION
UPCOMING PRELIMINARY - FBS DUE NEXT MONTH
FUTURE PRELIMINARY - FBS CERTS > 1 MONTH OUT
FBS NOT REQUIRED
Region III FBS Tracker
| STATE | PROJECT | MIP Case No. | Study Manager | PRELIMINARY | Certification Form | Date Submitted to FEMA Region III | Date Loaded to the MIP
4 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-01-08 | 2019-01-08
5 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-09-22 | 2020-09-22
6 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-11-06 | 2018-11-06
135 | #N/A | #N/A | #N/A | #N/A | #REF!
8 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-11-06 | 2018-11-06
133 | #N/A | #N/A | #N/A | #N/A | #REF!
9 | #N/A | #N/A | #N/A | #N/A | #REF!
134 | #N/A | #N/A | #N/A | #N/A | #REF!
11 | #N/A | #N/A | #N/A | #N/A | #REF!
12 | #N/A | #N/A | #N/A | #N/A | #REF!
13 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-08-13 | 2018-09-18
14 | #N/A | #N/A | #N/A | #N/A | #REF!
15 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 10/25/2018 & 6/5/2019 | 11/2/2018 & 6/5/2019
16 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-06-26 | 2020-12-08
17 | #N/A | #N/A | #N/A | #N/A | #REF!
18 | #N/A | #N/A | #N/A | #N/A | #REF!
19 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2016-06-15 | 2016-06-15
21 | #N/A | #N/A | #N/A | #N/A | #REF!
22 | #N/A | #N/A | #N/A | #N/A | #REF!
24 | #N/A | #N/A | #N/A | #N/A | #REF!
25 | #N/A | #N/A | #N/A | #N/A | #REF!
27 | #N/A | #N/A | #N/A | #N/A | #REF!
28 | #N/A | #N/A | #N/A | #N/A | #REF!
29 | #N/A | #N/A | #N/A | #N/A | #REF!
30 | #N/A | #N/A | #N/A | #N/A | #REF!
31 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-09-25 | 2020-09-25
32 | #N/A | #N/A | #N/A | #N/A | #REF!
33 | #N/A | #N/A | #N/A | #N/A | #REF!
34 | #N/A | #N/A | #N/A | #N/A | #REF!
35 | #N/A | #N/A | #N/A | #N/A | #REF!
36 | #N/A | #N/A | #N/A | #N/A | #REF!
37 | #N/A | #N/A | #N/A | #N/A | #REF!
38 | #N/A | #N/A | #N/A | #N/A | #REF!
39 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 3/22/2019 & 11/6/2020 | 3/22/2019 & 11/6/2020
180 | #N/A | #N/A | #N/A | #N/A | #REF!
40 | #N/A | #N/A | #N/A | #N/A | #REF!
148 | #N/A | #N/A | #N/A | #N/A | #REF!
42 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-28 | 2018-09-28
43 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2016-06-15 | 2016-06-15
45 | #N/A | #N/A | #N/A | #N/A | #REF!
46 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2016-06-15 | 2016-06-15
48 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-08-13 | 2018-09-18
154 | #N/A | #N/A | #N/A | #N/A | #REF!
49 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2017-12-18 | 2017-12-18
50 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2017-12-18 | 2017-12-18
156 | #N/A | #N/A | #N/A | #N/A | #REF!
160 | #N/A | #N/A | #N/A | #N/A | #REF!
52 | #N/A | #N/A | #N/A | #N/A | #REF!
127 | #N/A | #N/A | #N/A | #N/A | #REF!
166 | #N/A | #N/A | #N/A | #N/A | #REF!
157 | #N/A | #N/A | #N/A | #N/A | #REF!
54 | #N/A | #N/A | #N/A | #N/A | #REF!
161 | #N/A | #N/A | #N/A | #N/A | #REF!
55 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-08-17 | 2018-09-18
151 | #N/A | #N/A | #N/A | #N/A | #REF!
56 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 9/21/2018 & 10/12/2020 | 9/21/2018 & 10/12/2020
57 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
58 | #N/A | #N/A | #N/A | #N/A | #REF!
59 | #N/A | #N/A | #N/A | #N/A | #REF!
60 | #N/A | #N/A | #N/A | #N/A | #REF!
61 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-09-24 | 2020-09-25
155 | #N/A | #N/A | #N/A | #N/A | #REF!
162 | #N/A | #N/A | #N/A | #N/A | #REF!
62 | #N/A | #N/A | #N/A | #N/A | #REF!
63 | #N/A | #N/A | #N/A | #N/A | #REF!
64 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
152 | #N/A | #N/A | #N/A | #N/A | #REF!
65 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2019-06-14
167 | #N/A | #N/A | #N/A | #N/A | #REF!
66 | #N/A | #N/A | #N/A | #N/A | #REF!
143 | #N/A | #N/A | #N/A | #N/A | #REF!
67 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
68 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
69 | #N/A | #N/A | #N/A | #N/A | #REF!
70 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
171 | #N/A | #N/A | #N/A | #N/A | #REF!
72 | #N/A | #N/A | #N/A | #N/A | #REF!
73 | #N/A | #N/A | #N/A | #N/A | #REF!
74 | #N/A | #N/A | #N/A | #N/A | #REF!
75 | #N/A | #N/A | #N/A | #N/A | #REF!
76 | #N/A | #N/A | #N/A | #N/A | #REF!
77 | #N/A | #N/A | #N/A | #N/A | #REF!
78 | #N/A | #N/A | #N/A | #N/A | #REF!
79 | #N/A | #N/A | #N/A | #N/A | #REF!
80 | #N/A | #N/A | #N/A | #N/A | #REF!
168 | #N/A | #N/A | #N/A | #N/A | #REF!
158 | #N/A | #N/A | #N/A | #N/A | #REF!
82 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-10-12 | 2020-10-12
83 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-10-12 | 2020-10-12
129 | #N/A | #N/A | #N/A | #N/A | #REF!
147 | #N/A | #N/A | #N/A | #N/A | #REF!
140 | #N/A | #N/A | #N/A | #N/A | #REF!
141 | #N/A | #N/A | #N/A | #N/A | #REF!
173 | #N/A | #N/A | #N/A | #N/A | #REF!
87 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
88 | #N/A | #N/A | #N/A | #N/A | #REF!
159 | #N/A | #N/A | #N/A | #N/A | #REF!
89 | #N/A | #N/A | #N/A | #N/A | #REF!
90 | #N/A | #N/A | #N/A | #N/A | #REF!
91 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
92 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-09-08 | 2020-09-08
94 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-06-05 | 2019-06-05
153 | #N/A | #N/A | #N/A | #N/A | #REF!
95 | #N/A | #N/A | #N/A | #N/A | #REF!
96 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-10-12 | 2020-10-12
97 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2020-02-03 | 2020-02-03
99 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2019-06-14
139 | #N/A | #N/A | #N/A | #N/A | #REF!
102 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
142 | #N/A | #N/A | #N/A | #N/A | #REF!
131 | #N/A | #N/A | #N/A | #N/A | #REF!
164 | #N/A | #N/A | #N/A | #N/A | #REF!
104 | #N/A | #N/A | #N/A | #N/A | #REF!
105 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
144 | #N/A | #N/A | #N/A | #N/A | #REF!
174 | #N/A | #N/A | #N/A | #N/A | #REF!
130 | #N/A | #N/A | #N/A | #N/A | #REF!
150 | #N/A | #N/A | #N/A | #N/A | #REF!
170 | #N/A | #N/A | #N/A | #N/A | #REF!
172 | #N/A | #N/A | #N/A | #N/A | #REF!
149 | #N/A | #N/A | #N/A | #N/A | #REF!
169 | #N/A | #N/A | #N/A | #N/A | #REF!
106 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2018-09-19 | 2020-12-24
107 | #N/A | #N/A | #N/A | #N/A | #REF!
126 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2021-11-30 | 2021-11-30
138 | #N/A | #N/A | #N/A | #N/A | #REF!
137 | #N/A | #N/A | #N/A | #N/A | #REF!
112 | #N/A | #N/A | #N/A | #N/A | #REF!
145 | #N/A | #N/A | #N/A | #N/A | #REF!
146 | #N/A | #N/A | #N/A | #N/A | #REF!
177 | #N/A | #N/A | #N/A | #N/A | #REF!
113 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-12-18 | 2019-12-18
117 | #N/A | #N/A | #N/A | #N/A | #REF!
120 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-12-18 | 2019-12-18
175 | #N/A | #N/A | #N/A | #N/A | #REF!
121 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-12-18 | 2019-12-18
179 | #N/A | #N/A | #N/A | #N/A | #REF!
178 | #N/A | #N/A | #N/A | #N/A | #REF!
123 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-12-18 | 2019-12-18
176 | #N/A | #N/A | #N/A | #N/A | #REF!
125 | #N/A | #N/A | #N/A | #N/A | #REF! | FORM B | 2019-12-18 | 2019-12-18

## Appeals (hidden)
FMPU_ID | STATE | PROJECT | MIP CASE NO | FEMA ENG | STUDY MANAGER | PRELIMINARY | REVISED PRELIM_1 | REVISED PRELIM | APPEAL PERIOD STARTS | LFD ISSUANCE | Sum of Resolved | Sum of Not Resolved | Total Resolved | Total Not Resolved
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6 | 2 | 8 | 15
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 9
32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1
40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
154 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
156 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
160 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 4
166 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
157 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
161 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
151 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1
68 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
155 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
162 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
152 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
167 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
143 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
88 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
89 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
90 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
92 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
74 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
112 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
117 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
168 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
121 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
123 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
125 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
158 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
127 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
130 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
131 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
134 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
135 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
137 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
82 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
139 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
140 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
141 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
142 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2
87 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
146 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
147 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
148 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
149 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
150 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
159 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
94 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
95 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
96 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
97 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
102 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
164 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
104 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
105 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
144 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
106 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
126 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
138 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
177 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1
113 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
169 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
170 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
171 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
172 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
173 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
174 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
175 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
120 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
179 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
178 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
176 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
180 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
181 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
182 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
183 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
184 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
185 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
186 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
187 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
188 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
189 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
190 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
191 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
192 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
193 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
194 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
195 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
196 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
197 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
198 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
199 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
200 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
201 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
202 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
203 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## NFIP_Workbook_Reviews (hidden)
FMPU_ID | STATE | PROJECT | MIP CASE NO | # ORDINANCE UPDATES | STUDY MANAGER | FLD RSK RVW MTG | PRELIMINARY | LFD ISSUANCE | EFFECTIVE DATES | Received | Reviewed | Errors | Uploaded to RMD Sharepoint?
62 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
107 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
99 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
94 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
106 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
102 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
87 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
120 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
121 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
123 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
125 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
89 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
113 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
105 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
97 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
104 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
110 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
92 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-15
61 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-15 | 2020-09-16 | No | Yes
52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-15 | 2020-09-16 | No | Yes
60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-15 | 2020-09-16 | No | Yes
58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-15 | 2020-09-16 | No | Yes
49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-15 | 2020-09-16 | No | Yes
56 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-21
82 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
96 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2020-09-21
74 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
95 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
126 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
151 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
152 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
154 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
155 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
156 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
157 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
158 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
159 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
160 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
161 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
162 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
143 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
164 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
144 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
166 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
167 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
168 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
133 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
134 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
148 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
127 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
171 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
147 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
140 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
141 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
173 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
90 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
139 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
142 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
131 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
174 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
130 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
150 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
170 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
172 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
149 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
169 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
135 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
88 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
136 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
138 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
137 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
112 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
146 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
117 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
175 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## LFD Dates (hidden)
New Projected Dates
LFD | Effective | LFD | Effective
2020-01-08 | 2020-07-08 | 2021-01-06 | 2021-07-06
2020-01-22 | 2020-07-22 | 2021-01-20 | 2021-07-20
2020-02-05 | 2020-08-05 | 2021-02-10 | 2021-08-10
2020-02-19 | 2020-08-19 | 2021-02-24 | 2021-08-24
2020-03-04 | 2020-09-04 | 2021-03-10 | 2021-09-10
2020-03-18 | 2020-09-18 | 2021-03-24 | 2021-09-24
2020-04-01 | 2020-10-01 | 2021-04-07 | 2021-10-07
2020-04-15 | 2020-10-15 | 2021-04-21 | 2021-10-21
2020-05-06 | 2020-11-06 | 2021-05-05 | 2021-11-05
2020-05-20 | 2020-11-20 | 2021-05-19 | 2021-11-19
2020-06-03 | 2020-12-03 | 2021-06-02 | 2021-12-02
2020-06-17 | 2020-12-17 | 2021-06-16 | 2021-12-16
2020-06-30 | 2020-12-30 | 2021-06-30 | 2021-12-30
2020-07-15 | 2021-01-15 | 2021-07-14 | 2022-01-14
2020-07-29 | 2021-01-29 | 2021-07-28 | 2022-01-28
2020-08-12 | 2021-02-12 | 2021-08-11 | 2022-02-11
2020-08-26 | 2021-02-26 | 2021-08-25 | 2022-02-25
2020-09-09 | 2021-03-09 | 2021-09-08 | 2022-03-08
2020-09-23 | 2021-03-23 | 2021-09-22 | 2022-03-22
2020-10-07 | 2021-04-07 | 2021-10-06 | 2022-04-06
2020-10-21 | 2021-04-21 | 2021-10-20 | 2022-04-20
2020-11-04 | 2021-05-04 | 2021-11-03 | 2022-05-03
2020-11-18 | 2021-05-18 | 2021-11-17 | 2022-05-17
2020-12-02 | 2021-06-02 | 2021-12-01 | 2022-06-01
2020-12-16 | 2021-06-16 | 2021-12-15 | 2022-06-15